## Sheet1
Discipline | Project Description/Activity Name | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable0 | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implement | End of Activity report
1. DEPARTMENT OF FINANCE & DEVELOPMENT PLANNING
LTC/FDP/01/2024--Supplies | Suply and delivery of office stationery for Lobatse Town Council | 956830 | 956830 | RDB | Running tender until 2027 | [12 empty] | 31/03/2027 | 01/04/2027
LTC/FDP/02/2024--Supplies | Supply and delivery of uniform and protective clothing,and footwear | 1 616 660.00 | 1216770 | RDB | Running tender until 2027 | [12 empty] | 31/03/2027 | 01/04/2027
LTC/FDP/03/2024--Supplies | Supply and delivery of domestic requisites | 2 635 860.00 | 1952280 | RDB | 2025-02-02 | 10/02/2025 | 26/02/2025 | 01/03/2025 | 16/03/2025 | 20/03/2025 | 29/03/2025 | 30/03/2025 | 02/04/2025 | 04/04/2025 | 16/04/2025 | 22/04/2025 | 23/04/2025 | 25/04/2025 | 01/04/2027
LTC/FDP/04/2024--Supplies | Supply and delivery of food office commodities for Lobatse Town Council | 213640 | 213640 | RDB | Running tender until 2027
1170470
2. DEPARTMENT OF CIVIL & MECHNICAL
A. TRANSPORT DIVISION
TM01-Supplies+A10:A19 | Supply of vehicle spare parts | 689000 | P689000 | ODB | N/A | N/A | USER DEPARTMENT DIVERTED FUNDS DUE TO EMERGENCY VEHICLE MAINTENANCE SERVICES, HENCE WILL PREPARE RFQ FOR SPARE PARTS. | [7 empty] | Funds depleted, no tender running. | N/A | N/A | N/A | N/A
TM02-Supplies | Supply & delivery of wet cell batteries | 35800 | P35800 | RFQ | 2024-08-28 | 05/09/2024 | 12/09/2024 | 17/09/2024 | 20/09/2024 | 25/09/2024 | 07/10/2024 | 08/10/2024 | 09/10/2024 | 14/10/2024 | 15/10/2024 | 16/10/2024 | 17/10/2024 | 18/10/2024 | N/A
TM03-Supplies | Fuel, Oil, lubriicants | 1642040 | P1,642, 040.00 | Selective | 2024-02-22 | 2024-03-04 | 20/03/2024 | 26/03/2024 | 28/03/2024 | 09/04/2024 | 12/04/2024 | 05/05/2024 | 06/05/2024 | 07/05/2024 | 07/06/2024 | 10/06/2024 | 14/06/2024 | 19/06/2024 | N/A
TM04-Service | Air refrigerant refil | 3900 | P3,900.00 | Micro | 2024-05-20 | 2024-05-22 | 2024-05-29 | 2024-05-31 | 2024-06-21 | 2024-07-05 | 10/07/2024 | 24/07/2024 | 28/07/2024 | 29/07/2024 | 07/06/2024 | 10/06/2024 | 14/06/2024 | 19/06/2024 | N/A
TM05-Service | Maintenance of primary school pots & airconditioner | P237,600.00 | P237,600.00 | RFQ | 2024-11-11 | 25/11/2024 | 03/12/2024 | 05/12/2024 | 09/12/2024 | 09/12/2024 | 09/12/2024 | 12/12/2024 | 13/12/2024 | 24/12/2024 | 06/01/2025 | 07/01/2025 | 08/01/2025 | 31/01/2025 | N/A
TM06-Supplies | First Aid Kit Refill | P400.00 | P400.00 | Micro | 2024-10-21 | 22/10/2024 | 24/10/2024 | 25/10/2024 | 28/10/2024 | 29/10/2024 | 22/11/2024 | 26/11/2024 | 28/11/2024 | 03/12/2024 | 17/12/2024 | 22/01/2025 | 23/01/2025 | 31/03/2025 | N/A
TM07-Supplies | Small Tools & Plants | P104,200.00 | P104,200.00 | RFQ | 2024-11-11 | 25/11/2024 | 03/12/2024 | 05/12/2024 | 09/12/2024 | 20/12/2024 | 22/11/2024 | 26/11/2024 | 28/11/2024 | 03/12/2024 | 17/12/2024 | 22/01/2025 | 23/01/2025 | 31/03/2025 | N/A
TM08-Service | Fleet Maintenance | P134,800.00 | P134,800.00 | RFQ | 2024-10-21 | 22/10/2024 | 24/10/2024 | 25/10/2024 | 28/10/2024 | 29/10/2024 | 22/11/2024 | 26/11/2024 | 28/11/2024 | 03/12/2024 | 17/12/2024 | 22/01/2025 | 23/01/2025 | 31/03/2025 | N/A
TM009-Service | Purchase of Office Furniture & Equipment | P215,800.00 | P215,800.00 | RFQ | 2024-09-16 | 04/10/2024 | 18/10/2024 | 22/10/2024 | 24/10/2024 | 14/11/2024 | 22/11/2024 | 26/11/2024 | 28/11/2024 | 03/12/2024 | 17/12/2024 | 22/01/2025 | 23/01/2025 | 31/03/2025 | N/A
TM10-Service | Maintenance of stationery Equipment | P16,360.00 | P16,360.00 | RFQ | 2024-09-16 | 04/10/2024 | 18/10/2024 | 22/10/2024 | 24/10/2024 | 14/11/2024 | 22/11/2024 | 26/11/2024 | 28/11/2024 | 03/12/2024 | 17/12/2024 | 22/01/2025 | 23/01/2025 | 31/03/2025 | N/A
TM11-Supplies | Supply & fitting of Tyres Tubes & Flaps | 117040 | P117040 | RDB | 2024-09-16 | 04/10/2024 | 18/10/2024 | 22/10/2024 | 24/10/2024 | 14/11/2024 | 22/11/2024 | 26/11/2024 | 28/11/2024 | 03/12/2024 | 17/12/2024 | 22/01/2025 | 23/01/2025 | 31/03/2025 | N/A
2487780
B. ELECTRICAL DIVISION
ELECT 01-Supplies | Maintenance of Streetlights | 318465.7 | 318465.7 | ODB | 2024-03-04 | 2024-03-15 | 2024-03-22 | 2024-04-05 | 2024-04-11 | 2024-04-25 | ITT PREPARED LATE AFTER CANCELLATION AND HAD BEEN RE SUBMITTED FOR RE-EVALUATION, EXPECTED TO BE COMPLETE ON FEB 2025 | [7 empty] | N/A
ELEC02-Supplies | Maintenance of Grounds and Buildings | 135023.4 | 135023.4 | ODB | 2024-03-04 | 2024-03-15 | 2024-03-22 | 2024-04-05 | 2024-04-11 | 2024-04-25 | PENDING WITH USER DEPARTMENT FOR ITT CORRECTIONS, FUNDS SOURCING | [6 empty] | N/A | N/A
ELEC03-Supplies | Small Tools and Plants | 21900 | 21900 | RFQ | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-11-06 | 2024-11-20 | 2024-11-29 | 2025-01-10 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | N/A
ELECT 04-Supplies | Plant Hire | 35750 | 35750 | RFQ | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-11-06 | 2024-11-20 | 2024-11-29 | 2025-01-10 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | N/A
ELECT 05-Supplies | Maintenance of Radio communication Equipment | 5000 | 5000 | Micro | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-11-06 | 2024-11-20 | 2024-11-29 | 2025-01-10 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | N/A
ELECT06-Supplies | Radio Communication Licencing | 5750 | 5750 | Micro | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-29 | 2024-11-06 | 2024-11-20 | 2024-11-29 | 2025-01-10 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | N/A
521889.1
C. ROADS
Discipline | Project Description/Activity Name | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable0 | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implement | End of Activity report
ROADS 001-Works | Reinstatement of Road markings and replacement of road signs, desilting of culverts and vegetation control. (Road Fund Levy) | 5 000 000.00 | 5 000 000.00 | Open Domestic | 2024-09-27 | 2024-10-11 | 2024-10-22 | 2024-10-24 | 2024-10-28 | 2024-11-15 | 2024-11-30 | 2024-12-03 | 2024-12-04 | 2024-12-06 | 10/12/2024 | 06/01/2025 | 20/01/2025 | 31/03/2025 | N/A
ROADS 002-Works | Road paving, Edge Protection, Patching, Kerb-lining & construction of drainage systems. (CCP 24) | 10000000 | 2000000 | Open Domestic | 2024-09-27 | 2024-10-11 | 2024-10-22 | 2024-10-24 | 2024-10-28 | 2024-11-15 | 2024-11-30 | 2024-12-03 | 2024-12-04 | 2024-12-06 | 10/12/2024 | 06/01/2025 | 20/01/2025 | 31/03/2025 | N/A
ROADS 003-Supplies | PROCUREMENT OF ROADS MAINTENANCE MATERIAL | 246472.5 | 246472.5 | Restricted Domestic Bidding | 2024-04-17 | 2024-05-19 | 2024-06-05 | 2024-06-06 | 2024-06-09 | 2024-07-03 | 2024-08-30 | 2024-09-12 | 2024-09-26 | 2024-10-04 | 2024-10-17 | 06/01/2025 | 20/01/2025 | 31/03/2025 | N/A
10246472.5
3. DEPARTMENT OF HR & ADMINISTRATION
A. ICT DIVISION
ICT 01-Supplies | Laptops (for Councillors) | 210000 | 210000.00 | RFP | 2024-04-17: 2024-07-03; 2024-05-19: 2024-08-30; 2024-06-05: PROCURED THROUGH A RUNNING TENDER WHICH IS EXPECTED TO END IN NOVEMBER 2024.; 2024-09-26: 30/11/2024; 2024-10-04: 2024-12-03; 2024-10-17: 2024-12-09 | 2024-12-14 | 2024-12-15 | 2024-12-16 | N/A
ICT 02-Supplies | Computers Desktop | 60000 | 60000.00 | RDB | 2024-04-17: 2024-07-03; 2024-05-19: 2024-08-30; 2024-06-05: PROCURED THROUGH A RUNNING TENDER WHICH IS EXPECTED TO END IN NOVEMBER 2024.; 2024-09-26: 30/11/2024; 2024-10-04: 2024-12-03; 2024-10-17: 2024-12-09 | 2024-12-14 | 2024-12-15 | 2024-12-16 | N/A
ICT 03-Supplies | MicroSoft Office Software licences | 160000 | 160000 | Open Tender | 2024-07-03 | 2024-08-30 | 2024-11-11 | 2024-11-22 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 30/11/2024 | 2024-12-03 | 2024-12-05 | 2024-12-06 | 2024-12-09 | 2024-12-13 | 2025-03-31 | N/A
ICT 04-Services | MicroSoft Windows Operating System Software licences | 160000 | 160000 | Open Tender | 2024-07-03 | 2024-08-30 | 2024-11-11 | 2024-11-21 | 2024-12-03 | 2024-12-05 | 2024-12-06 | 2024-12-09 | 2024-12-12 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2025-03-31 | N/A
ICT 05-Services | Window Server 2022 Licences, WinQS, Autho CAD, Anti Virus software Licenses | 316000 | 316000 | RDB | 2024-07-03 | 2024-08-30 | 2024-11-11 | 2024-11-21 | 2024-12-03 | 2024-12-05 | 2024-12-06 | 2024-12-09 | 2024-12-12 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-20 | 2025-03-31 | N/A
ICT 06-Services | Subscription for SMS to Elecronic payslips | 5000 | 5000 | Micro | 2024-04-10 | 2024-05-05 | 2024-05-20 | 2024-05-22 | 2024-05-29 | 2024-05-31 | 2024-06-21 | 2024-07-05 | 2024-07-26 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-20 | 2025-03-31 | N/A
ICT 07-Supplies | Buy New IP Phones from BTCL | 50000 | 50000 | DP | 2024-04-17: 2024-07-03; 2024-05-19: 2024-08-30; 2024-06-05: PROCURED THROUGH AN RFQ DURING AUGUST 2024.; 2024-09-26: 20/11/2024; 2024-10-04: 2024-12-16; 2024-10-17: 2024-12-17 | 2024-12-18 | 2024-12-20 | 2025-04-01 | N/A
961000
B. HR & ADMINISTRATION
HR 01-Services | Training of LTC Employees in various Courses | 160 000.00 | 160 000.00 | DP | 2024-07-25 | 2024-07-26 | 2024-11-11 | 25/11/2024 | 03/12/2024 | 04/12/2024 | 06/12/2024 | 09/12/2024 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-20 | 31/03/2025 | 01/04/2025 | N/A
ADMIN 01-Services | Security Services | 7,088.830.00 | 7,088.830.00 | ODB | 2024-07-25 | 2024-07-26 | RUNNING TENDER | RUNNING TENDER | RUNNING TENDER | RUNNING TENDER | RUNNING TENDER | RUNNING TENDER | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-21 | 31/03/2025 | 01/04/2025 | N/A
7 248 830.00
2 .COUNCIL MANAGEMENT
REFORMS
Discipline | Project Description/Activity Name | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable0 | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implement | End of Activity report
LTC/REFORMS/01/2025-Service | Development of 2025-2026 (Annual Performance Plan) 40 employees. |  | 70000 | DP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 01/03/2025 | N/A | N/A | 01/05/2025 | 31/03/2025 | 31/03/2026
LTC/REFORMS/02/2024-Service | Cascading of Annual performance plan to employees (2024--2025) 718 employees | 107700 | 80000 | RDB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 01/03/2025 | NA | N/A | 01/05/2025 | 31/05/2025 | 31/03/2026
LTC/REFORMS/03/2024-Service | Focal persons and Quality Assurance Team Training (25 employees) |  | 27700 | DP | 2025-06-18 | 21/06/2025 | 25/06/2025 | 26/06/2025 | 10/07/2025 | 11/07/2025 | 16/07/2025 | 17/07/2025 | 20/07/2025 | 21/07/2025 | 08/08/2025 | 09/08/2025 | 09/08/2025 | 20/08/2025 | 31/03/2026
257700
3. DEPARTMENT OF ENVIRONMENTAL HEALTH
Discipline | Project Description/Activity Name | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable0 | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implement | End of Activity report
LTC/ENV/01/2025--2026 Services | Refuse collection, transportation & collection in Lobatse Township | 1320000 | 1320000 | RDB | 2024-12-05 | 2024-12-06 | 2024-12-14 | 2025-01-10 | 2025-01-31 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 24/02/2025 | 2025-03-17 | 2025-04-11 | 2025-04-23 | 2025-06-01 | 2026-06-01 | 31/07/2026
1320000
4. EDUCATION
Discipline | Project Description/Activity Name | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable0 | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implement | End of Activity report
EDU 01-Supplies | Supply & delivery of Sorghum, salt and Samp for Primary Schools | 1,509.668.00 | 1,509.668.00 | RDB | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender, until June 2026
EDU 02-Supplies | Supply & delivery of Jam & Peanut butter spreads for P.S. | 1103307 | 1103307 | RDB | 2025-08-30 | 2025-09-06 | 2025-09-16 | 04/10/2025 | 18/10/2025 | 22/10/2025 | 24/10/2025 | 03/12/2025 | 31/12/2025 | 06/01/2026 | 13/01/2026 | 31/01/2026 | 03/02/2025 | 03/02/2027 | 31/03/2027
EDU 03-Supplies | Supply & delivery of beans for P.S. | 940524 | 940524 | DP | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender, until February 2026
EDU 04-Supplies | Supply & delivery of liquid petrolium gas, empty cylinders | 1 470 000.00 | 1 470 000.00 | RDB | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender, until June 2026
EDU 05-Supplies | Supply & Delivery of 750ml Sunflower cooking oil. | 578784 | 578784 | RDB | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender, until December 2025
EDU 06-Supplies | Supply and delivery of UHT Milk 340ml | 1531224.1 | 1531224.1 | RDB | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender, until December 2025
EDU 07-Supplies | Supply and delivery of White Suga (25kg) & Rooibos Leaves (12x100g) | 1704036.4 | 1704036.4 | RDB | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender, until December 2025
EDU 08-Supplies | Supply & delivery of Stationery, Equipment and consumables for P.S. | 1 013 200.00 | 1 013 200.00 | RDB | 08/06/2025 | 14/06/2025 | 2025-06-20 | 25/06/2025 | 09/07/2025 | 10/07/2025 | 12/07/2025 | 13/07/2025 | 14/07/2025 | 15/07/2025 | 30/07/2025 | 03/08/2025 | 04/08/2025 | 12/08/2025 | 2026-03-31
EDU 09-Supplies | Supply and delivery of school furniture | 135 000.00 | 135 000.00 | RDB | 08/06/2025 | 14/06/2025 | 2025-06-20 | 25/06/2025 | 09/07/2025 | 10/07/2025 | 12/07/2025 | 13/07/2025 | 14/07/2025 | 15/07/2025 | 30/07/2025 | 03/08/2025 | 04/08/2025 | 12/08/2025 | 2026-03-31
EDU 10-Supplies | Supply and delivery of Fruits--Oranges and Apples. | 2 026 400.00 | 2 026 400.00 | EOI | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender | Running tender until 2026
5857875.5
G DEPARTMENT OF SOCIAL & COMMUNITY DEVELOPMENT
Discipline | Project Description/Activity Name | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable0 | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implement | End of Activity report
S&CD 01-Service | Organising of Mini-show | 38400 | 38400 | Quotation | 2024-02-25 | 2024-03-04 | 2024-03-04 | 15/03/2024 | 22/03/2024 | 05/04/2024 | 11/04/2024 | 25/04/2024 | 31/07/2024 | 30/08/2024 |  |  |  |  | N/A
S&CD 02-Supplies | PurchasingTeaching materials | 131 390.00 | 131 390.00 | RDB | 2024-02-26 | 2024-03-04 | 2024-03-04 | 15/03/2024 | 22/03/2024 | 05/04/2024 | 11/04/2024 | 25/04/2024 | 31/07/2024 | 30/08/2024 |  |  |  |  | N/A
S&CD 03-Services | Purchase of Food for Model day care centre | 66520 | 66520 | DP | 2024-02-26 | 2024-03-04 | 2024-03-04 | 15/03/2024 | 22/03/2024 | 05/04/2024 | 11/04/2024 | 25/04/2024 | 31/07/2024 | 30/08/2024 |  |  |  |  | N/A
S&CD 04-Services | Foster care tranining (officers & Parents) | 39500 | 39500 | RFQ | 2024-02-27 | 2024-03-04 | 2024-03-04 | 15/03/2024 | 22/03/2024 | 05/04/2024 | 11/04/2024 | 25/04/2024 | 31/07/2024 | 30/08/2024 |  |  |  |  | N/A
S&CD 05-Services | Beneficiary Workshops & Seminars - Cohorts | 40000 | 40000 | RFQ | 2024-02-28 | 2024-03-04 | CANCELLED | CANCELLED | CANCELLED | CANCELLED | CANCELLED | CANCELLED | CANCELLED | CANCELLED | N/A | N/A | N/A | N/A | N/A
S&CD 06-Services | Beneficiary Workshops & Seminars - Peer leaders | 120000 | 120000 | RDB | 2024-02-26 | 2024-03-04 | 2024-03-04 | 15/03/2024 | 22/03/2024 | 05/04/2024 | 11/04/2024 | 25/04/2024 | 31/05/2024 | 01/06/2024
S&CD 07-Services | Beneficiary Workshops & Seminars - Life skills | 15000 | 15000 | Micro | 2024-02-26 | 2024-03-04 | 2024-03-04 | 15/03/2024 | 22/03/2024 | 05/04/2024 | 11/04/2024 | 25/04/2024 | 31/03/2025 | 01/04/2025
S&CD 08-Services | Officers retreat | 375000 | 375000 | RDB | 2024-02-26 | 2024-03-04 | 2024-03-04 | 15/03/2024 | 22/03/2024 | 05/04/2024 | 11/04/2024 | 25/04/2024 | 31/05/2024 | 01/06/2024
S&CD 09-Services | Celebrations/Commemorations June 16, | 136500 | 136500 | RDB | 2024-02-26 | 2024-03-04 | 2024-03-04 | 15/03/2024 | 22/03/2024 | 05/04/2024 | 11/04/2024 | 25/04/2024 | 31/05/2024 | 01/06/2024
S&CD 10-Servcies | Staff training workshops - SSR | 19774.85 | 19774.85 | Micro | 2024-02-26 | 2024-03-04 | 2024-03-04 | 15/03/2024 | 22/03/2024 | 05/04/2024 | 11/04/2024 | 25/04/2024 | 31/05/2024 | 01/06/2024
S&CD 11-Services | Staff training workshops - Palliative care | 40000 | 40000 | RFQ | 23/08/2024 | 30/08/2024 | 2024-09-18 | 2024-09-29 | 2024-10-06 | 2024-10-12 | 2024-10-13 | 2024-10-30 | 2024-11-30 | 2024-12-22
S&CD 12-Services | Staff training workshops - De-briefing | 45000 | 45000 | RFQ | 23/08/2024 | 30/08/2024 | 2024-09-18 | 2024-09-29 | 2024-10-06 | 2024-10-12 | 2024-10-13 | 2024-10-30 | 2024-11-30 | 2024-12-22
S&CD 13-Services | Staff training workshops - Foster care | 27000 | 27000 | RFQ | 05/05/2024 | 08/05/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
S&CD 14-Supplies | Purchasing of Porta Cabin | 1000000 | 1000000 | ODB | 05/05/2024 | 08/05/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
S&CD 15-Serfvcies | Foster Care (Officers&Parents) | 39500 | 39500 | RFQ | 05/05/2024 | 08/05/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
S&CD 16-Services | Parent Child Sessions | 27000 | 27000 | RFQ | 05/05/2024 | 08/05/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
S&CD 17-Services | Disability Commemoration | 15000 | 15000 | Micro | 05/05/2024 | 08/05/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
S&CD 18-Supplies | Procurement of Beneficiary Private Clothing (Dest & Orphans) | 416000 | 416000 | Tender | 02/06/2024 | 03/06/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
S&CD 19-Services | CHBC Caregivers Workshop | 25000 | 25000 | Micro | 02/06/2024 | 03/06/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
S&CD 20-Services | De-briefing sessions Quarterly | 45000 | 45000 | RFQ | 02/06/2024 | 03/06/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
S&CD 21-Services | Provision of Funeral Services | 50000 | 50000 | RFQ | 02/06/2024 | 03/06/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
S&CD 22-Services | Re-aggregassion | 36000 | 36000 | RFQ | 02/06/2024 | 03/06/2024 | 2024-06-04 | 2024-06-18 | 2024-06-28 | 2024-07-05 | 2024-07-11 | 2024-07-30 | 2024-08-09 | 2024-08-16
2616194.85
H. DEPARTMENT OF ARCHITECTURE & BUILDINGS
A. RE-CURRENT MAINTENANCE BUDGET
Discipline | Project Description/Activity Name | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable0 | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implement | End of Activity report
AB 01-Works | Maintenance Contracts | 500000 | 500000 | RDB | 23/10/2024 | 28/10/2024 | 2024-11-11 | 25/11/2024 | 03/12/2024 | 05/12/2024 | 09/12/2024 | 24/12/2024 | 2024-12-31 | 2025-01-13
AB 02-Works | Maintenance Contracts | 300000 | 300000 | RDB | 23/10/2024 | 28/10/2024 | 2024-11-11 | 25/11/2024 | 03/12/2024 | 05/12/2024 | 09/12/2024 | 24/12/2024 | 2024-12-31 | 2025-01-13
AB 03-Works | Maintenance Contracts | 276 920.00 | 276 920.00 | Quotations | 23/10/2024 | 28/10/2024 | 2024-11-11 | 25/11/2024 | 03/12/2024 | 05/12/2024 | 09/12/2024 | 24/12/2024 | 2024-12-31 | 2025-01-13
AB 04-Supplies | Supply and delivery of stores material & drugs | 59730 | 59730 | Quotations | 07/10/2024 | 11/10/2024 | 2024-10-18 | 2024-10-23 | 2024-10-28 | 2024-10-28 | 2024-11-05 | 2024-11-22 | 2024-12-31 | 2025-01-13
AB 05-Works | Maintenance of 1No. Staff House 4055E and Maintenance of Public Toilet at Cumberland. | 200 000.00 | 200 000.00 | Quotations | 05/09/2024 | 11/09/2024 | 2024-09-16 | 04/10/2024 | 18/10/2024 | 22/10/2024 | 24/10/2024 | 14/11/2024 | 2024-11-14 | 2024-11-21
AB06-Works | Maintenance of 2 No staff houses 2587 74053 | 200 000.00 | 200 000.00 | Quotations | 05/09/2024 | 11/09/2024 | 2024-09-16 | 04/10/2024 | 18/10/2024 | 22/10/2024 | 24/10/2024 | 14/11/2024 | 2024-11-14 | 2024-11-21
#REF!
5. HEALTH CARE
Service | Procurement of DHMT office accomodation for a period of 5 years | 5000000 | 5000000 | Direct Appointment | 2025-11-01 | 2024-11-07 | 2024-11-22 | 2024-11-29 | 2024-12-13 | 2024-12-17 | 2024-12-20 | 2024-12-23 | 2025-02-19 | 2025-03-21 | 2025-04-07 | 2025-04-11 | 2025-04-11 | 2030-04-12 | 2030-04-12
Service | Maintenance of Furniture (Upholstery Works to Government Furniture) | 100000 | 100000 | Direct Appointment | 2025-04-02 | 2025-04-09 | 2025-04-09 | 2025-04-15 | 2025-04-23 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-02 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21
Supply | Procurement of food ration for patients (dhmt) | 100000 | 100000 | RFQ | 2025-05-15 | - | 2025-05-22 | 2025-05-23 | 2025-06-06 | 2025-06-10 | 2025-06-10 | - | - | 2025-06-10 | - | - | - | - | -
Service | Procurement of medical and surgical equipment | 1000000 | 1000000 | Open Domestic Bidding | 2025-08-12 | 03/09/2025 | 2025-09-10 | 2025-09-29 | 2025-10-31 | 2025-02-11 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 2028-11-24 | 10/12/2028
Supply | Furniture | 1, 000,000.00 | 1000000 | RFQ | 20/06/2025 | - | - | 27/06/2025 | 12/07/2025 | 16/07/2025 | 29/07/2025 | - | - | 29/07/2025 | 8/08/2025 | 08/08/2025 | 09/08/2025 | 10/10/2025
Service | Fuel & lubricant services | 200000 | 200000 | RFQ | 2025-03-20 | - | 2025-04-01 | 2025-04-11 | 2025-04-22 | 2025-04-24 | 2025-04-25 | - | - | - | - | - | - | - | -
Service | Medical Equipment and services of equipments (Maintenance) | 1000000 | 1000000 | RFQ | 20/08/2025 | - | 03/09/2025 | 2025-09-10 | 2025-09-29 | 2025-10-31 | 2025-02-11 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 2028-11-24 | 10/12/2028
Works | Maintenance of buildings | 1500000 | 1500000 | Open Domestic Bidding | 2025-07-20 | - | 2025-08-07 | 2025-08-08 | 2025-08-19 | 2025-08-19 | 2025-09-09 | - | - | - | - | - | - | - | -
Works | Minor works | 1000000 | 1000000 | RFQ | 2025-10--20 | - | - | 2025-11-03 | 2025-11-11 | 2025-11-11 | 2025-11-12 | - | - | - | - | - | - | - | -
Supply | Stationery /Office Supplies | 3000000 | 3000000 | RFQ | 15/04/2025 | 22/04/2025 | 05/07/2025 | 2025-07-05 | 2025-08-04 | 2025-08-05 | 13/5/2025 | 20/5/2025 | 31/5/2025 | 31/05/2025
Supplies | Domestic Supplies | 2500000 | 2500000 | RFQ | 03/04/2025 | - | 15/4/2025 | 25/4/2025 | 25/4/2025 | 25/4/2025 | 29/04/2023 | 2025-03-05 | 13/5/2025 | 13/5/2025
Service | Vehicle plant and maintenance | 2000000 | 2000000 | RFQ | 2025-05-16 | - | 2025-05-23 | 2025-05-26 | 2025-06-06 | 2025-06-10 | 2025-06-11 | - | - | - | - | - | - | - | -
Supply | Domestic and Household | 150000 | 150000 | RFQ | 2025-04-20 | - | 2025-05-02 | 2025-05-05 | 2025-05-12 | 2025-05-20 | 2025-05-21 | - | - | - | - | - | - | - | -
Supply | Air conditioners | 100000 | 100000 | RFQ | 2025-06-04 | - | 2025-06-11 | 2025-06-12 | 2025-06-20 | 2025-06-24 | 2025-06-25 | - | - | 2025-06-25 | - | - | - | - | -
Service | Fire extinguishers servicing | 300000 | 300000 | RFQ | 2025-12-04 | - | 2025-12-11 | 2025-12-12 | 2025-12-19 | 2025-12-23 | 2025-12-23 | - | - | 2025-12-23 | - | - | - | - | -
Supply | Drugs | 1000000 | 1000000 | RFQ | 2025-04-07 | - | 2025-04-14 | 2025-04-15 | 2025-04-22 | 2025-04-22 | 2025-04-23 | - | - | 2025-04-23 | - | - | - | - | -
Supply | Computer systems | 732600 | 732600 | RFQ | 2025-04-20 | - | 2025-05-02 | 2025-05-02 | 2025-05-12 | 2025-05-13 | 2025-05-14 | - | - | 2025-05-14 | - | - | - | - | -
Service | Disease & pest control | 100000 | 100000 | RFQ | 2025-12-20 | - | 2026-01-12 | 2026-01-13 | 2025-01-20 | 2025-01-21 | 2025-01-22 | - | - | 2025-01-22 | - | - | - | - | -
Supply | Incidental Expenses | 100000 | 100000 | RFQ | 2025-04-07 | - | 2025-04-14 | 2025-04-15 | 2025-04-23 | 2025-04-24 | 2025-04-25 | - | - | 2025-04-25 | - | - | - | - | -
Supply | National plan of action | 300000 | 300000 | RFQ | 2025-12-20 |  | 2026-01-12 | 2026-01-13 | 2025-01-20 | 2025-01-21 | 2025-01-22 | - | - | 2025-01-22 | - | - | - | - | -
Supply | Uniform & Protective Clothing | 300000 | 300000 | RFQ | 2025-10-15 |  | 2025-10-22 | 2025-10-23 | 2025-10-31 | 2025-11-04 | 2025-11-04 | - | - | 2025-11-04 | - | - | - | - | -
Service | Participatory Methodology | 100000 | 100000 | RFQ | 2025-09-20 | - | 2025-10-02 | 2025-10-03 | 2025-10-10 | 2025-10-14 | 2025-10-15 | - | - | 2025-10-15 | - | - | - | - | -
Service | Family Planning and Cancer screening | 200000 | 200000 | RFQ | 2025-05-08 | - | 2025-05-15 | 2025-05-16 | 2025-05-23 | 2025-05-27 | 2025-05-28 | - | - | 2025-05-28 | - | - | - | - | -
Supply | School Health | 300000 | 300000 | RFQ | 2025-09-05 | - | 2025-09-12 | 2025-09-12 | 2025-09-19 | 2025-09-25 | 2025-09-25 | - | - | 2025-09-25 | - | - | - | - | -
Supply | Infant and Youth Child Feeding | 100000 | 100000 | RFQ | 2025-05-20 | - | 2025-05-23 | 2025-05-26 | 2025-06-06 | 2025-06-10 | 2025-06-11 | - | - | 2025-06-11 | - | - | - | - | -
Supply | Community Home Base Care | 557624 | 557624 | RFQ | 2025-06-08 | - | 2025-06-16 | 2025-06-17 | 2025-06-24 | 2025-06-26 | 2025-06-27 | - | - | 2025-06-27 | - | - | - | - | -
Supply | Prevention of Mother to Child Treatment | 700000 | 700000 | RFQ | 2025-11-20 | - | 2025-12-03 | 2025-12-04 | 2025-12-12 | 2024-12-19 | 2024-12-23 | - | - | 2025-12-23
Supply | Radio & trasmitter equiment | 200000 | 200000 | RFQ | 2025-12-20 | - | 2025-01-12 | 2025-01-13 | 2025-01-20 | 2025-01-21 | 2025-01-22 | - | - | 2025-01-22
Service | Seminars and workshops | 300000 | 300000 | RFQ | 2025-05-13 | - | 2025-05-20 | 2025-05-21 | 2025-05-29 | 2025-06-03 | 2025-06-03 | - | - | 2025-06-03
TOTAL FOR CLINICS |  | 22940224
6. DEPARTMENT OF FIRE SERVICES
Discipline | Project Description/Activity Name | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable0 | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implement | End of Activity report
LTC/FIRE/O1/2025 Services | Maintanance of office furniture and equipment | 11750 | 11750 | RFQ | 02/06/2025 | 09/06/2025 | 2025-06-11 | 12/06/2025 | 18/06/2025 | 19/06/2025 | 23/06/2025 | 24/06/2025 | 26/06/2025 | 27/06/2025 | 08/07/2025 | N/A | 2025-07-10 | 2025-07-25 | N/A
LTC/FIRE/02/2025-Services | Fire Officers Medical Examination | 6480 | 6480 | Micro | 07/06/2025 | 08/06/2025 | N/A | N/A | 12/06/2025 | 30/05/2025 | 03/06/2025 | 06/06/2025 | 06/06/2025 | 10/06/2025 | N/A | N/A | 2025-06-10 | 2025-06-17 | N/A
LTC/FIRE/03/2025-Services | Maintanance of small tools and plants | 63500 | 63500 | RFQ | 02/06/2025 | 09/06/2025 | 2025-06-11 | 12/06/2025 | 18/06/2025 | 19/06/2025 | 23/06/2025 | 24/06/2025 | 2025-06-26 | 2025-06-27 | 08/07/2025 | N/A | 10/07/2025 | 25/07/2025 | N/A
LTC/FIRE/04/2025-Services | Maintenance of fire hydrants/service of fire extinguishers or repair of fire hydrants or fire safety signages and maintenace of fire alarm. | 95000 | 95000 | RFQ | 02/06/2025 | 09/06/2025 | 2025-06-11 | 12/06/2025 | 18/06/2025 | 19/06/2025 | 23/06/2025 | 24/06/2025 | 2025-06-26 | 2025-06-27 | 08/07/2025 | N/A | 10/07/2025 | 25/07/2025 | N/A
LTC/FIRE/05/2025-Services | Television subscription, Sports Equipment and prizes | 23000 | 23000 | Micro | 01/06/2025 | 02/06/2025 | N/A | N/A | N/A | 02/06/2025 | 03/06/2025 | N/A | 2025-06-03 | 2025-06-03 | N/A | NA | 04/06/2025 | 04/06/2025 | N/A
LTC/FIRE/06/2025-Works | Maintenance of Appliance bay floor tile. | 4000 | 4000 | Micro | 01/06/2025 | 02/06/2025 | N/A | N/A | N/A | 02/06/2026 | 03/06/2026 | N/A | 2025-06-04 | 2025-06-04 | N/A | NA | 04/06/2025 | 31/03/2025 | N/A
LTC/FIRE/07/2025-Supply | Supply and Delivery of Stores material & drugs | 21530 | 21530 | Micro | 01/06/2025 | 02/06/2025 | N/A | N/A | N/A | 02/06/2025 | 03/06/2025 | N/A | 2025-06-05 | 2025-06-05 | N/A | N/A | 04/06/2025 | 04/06/2025 | N/A
LTC/FIRE/08/2025-Supply | Supply and Delivery of Small Tools and Plants | 164000 | 164000 | Tender | 01/06/2025 | 12/05/2025 | 2025-05-26 | 09/06/2025 | 23/06/2025 | 27/06/2025 | 04/07/2025 | 09/07/2025 | 09/07/2025 | 11/07/2025 | 25/07/2025 | 01/08/2025 | 2025-08-06 | 2025-09-05 | N/A
LTC/FIRE/09/2025 Supply | Supply and delivery of furniture | 5600 | 5600 | Micro | 01/06/2025 | 02/06/2025 | N/A | N/A | N/A | 02/06/2025 | 03/06/2025 | N/A | 05/06/2025 | 05/06/2025 | N/A | N/A | 2025-07-02 | 2025-07-07 | N/A
LTC/FIRE/10/2025 Supply | Supply and Delivery of Radio Communication | 43800 | 43800 | RFQ | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 08/09/2026 | 31/03/2026
LTC/FIRE/11/2025 Supply | Procurement of Fire Engine for LTC. | 10000000.00 | 10000000.00 | DPM | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 08/09/2025 | 31/03/2026
TOTAL |  | 10438660 | 10438660
7. DEPARTMENT OF SOCIAL & COMMUNITY DEVELOPMENT
Descipline | Project Description | Budget Amount BWP | Estimated Cost BWP | Method of procurement | Preparation of ITT (incl. TORs & market research | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implementation | End of Activity report
Supplies
LTC/S&CD/25/26 | Purchase of Food for Model day care centre & meal planning and food variations training | 111 850.00 | 111 850.00 | Tender | Buy from a running food commodities tender | NA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LTC/S&CD/25/26 | Provision of Office Furniture | 25 000.00 | 25 00.00 | RFQ | 01/06/2025 | 12/05/2025 | 2025-05-26 | 09/06/2025 | 23/06/2025 | 27/06/2025 | 04/07/2025 | 09/07/2025 | 09/07/2025 | 11/07/2025 | 25/07/2025 | 01/08/2025 | 2025-08-06 | 2025-09-05 | 2026-09-06
LTC/S&CD/25/26 | Supply and delivery of teaching Material | 69 900.00 | 69 900.00 | RFQ | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 04/09/2026
LTC/S&CD/25/26 | First aid kit | 1 800.00 | 1 800.00 | Micro | 01/06/2025 | 02/06/2025 | N/A | N/A | N/A | 02/06/2025 | 03/06/2025 | N/A | 2025-06-03 | 2025-06-03 | N/A | NA | 04/06/2025 | 04/06/2025 | N/A
LTC/S&CD/25/26 | Uniform & Protective clothing | 14 140.00 | 14 140.00 | Tender |  | N/A | N/A | N/A | N/A |  |  |  | N/A | #NAME? | N/A |  |  | 30/11/2025 | 31/12/2035
Services
LTC/S&CD/25/26 | Medical examinations | 880 | 880 | MICRO | Micro | 01/06/2025 | 02/06/2025 | N/A | N/A | N/A | 02/06/2025 | 03/06/2025 | N/A | 2025-06-03 | 2025-06-03 | N/A | NA | 04/06/2025 | 04/06/2025 | N/A
LTC/S&CD/25/26 | Organising of Mini-show | 20 400 | 20 400 | RFQ | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 04/09/2026
LTC/S&CD/25/26 | Day care centre workshop & commemoration of Home Economics day | 15 400 | 15 400 | RFQ | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 04/09/2026
LTC/S&CD/25/26 | Sewing machine Servicing | 8 800.00 | 8 800.00 | RFQ | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 04/09/2026
8. DEPARTMENT OF HUMAN & ADMINISTRATION
LTC/HR&ADMIN/01/2025 | Supply, Delivery and Installation of office mobile cabinets for Lobatse Town Council | 111 177.39 | 111 177.39 | DP | 10/07/2025 | 20/07/2025 | 22/07/2025 | 25/07/2025 | 07/08/2025 | 08/08/2025 | 15/08/2025 | 19/08/2025 | 20/08/2025 | 21/08/2025 | 05/09/2025 | 06/09/2025 | 07/08/2025 | 07/03/2026 | 31/03/2025
LTC/HR&ADMIN/02/2025 | Supply, Delivery and Installation of light duty racking fitted with galvanised steel shelves for Lobatse Town Council | 211 620.00 | 211 620.00 | Tender | 01/06/2025 | 12/05/2025 | 2025-05-26 | 09/06/2025 | 23/06/2025 | 27/06/2025 | 04/07/2025 | 09/07/2025 | 09/07/2025 | 11/07/2025 | 25/07/2025 | 01/08/2025 | 2025-08-06 | 2025-09-05 | N/A
LTC/HR&ADMIN/03/2025 | Supply and delivery of office table at RMU Lobatse Town Council | 7 000.00 | 7 000.00 | Micro procurement | 01/06/2025 | 02/06/2025 | N/A | N/A | N/A | 02/06/2025 | 03/06/2025 | N/A | 2025-06-03 | 2025-06-03 | N/A | NA | 04/06/2025 | 04/06/2025 | N/A
LTC/HR&ADMIN/04/2025 | Supply and delivery of office swivel chairs at RMU Lobatse Town Council | 10 000.00 | 10 000.00 | Micro Procurement | 01/06/2025 | 02/06/2025 | N/A | N/A | N/A | 02/06/2025 | 03/06/2025 | N/A | 2025-06-03 | 2025-06-03 | N/A | NA | 04/06/2025 | 04/06/2025 | N/A
9. DEPARTMENT OF CIVIL & MECHNICAL
A. TRANSPORT DIVISION
TM01-Supplies | Supply of vehicle spare parts | 500000 | 500000 | ODB | 2025-03-03 | 17/03/2025 | 01/04/2025 | 14/04/2025 | 25/04/2025 | 06/05/2025 | 06/05/2025 | 07/05/2025 | 08/05/2025 | 16/05/2025 | 02/06/2025 | 2025-06-18 | 2025-06-18 | 2026-03-30 | 2026-04-05
TM02-Supplies | Supply & delivery of wet cell batteries | 75200 | 75200 | RFQ | 2025-03-03 | 07/03/2025 | 17/03/2025 | 17/03/2025 | 21/03/2025 | 28/03/2025 | 28/03/2025 | 31/03/2025 | 04/04/2025 | 07/04/2025 | 21/04/2025 | 2025-05-05 | 2025-05-05 | 2026-03-30 | 2026-04-05
TM03-Supplies | Fuel, Oil, lubriicants | 1799930 | 1799930 | Selective | 2025-03-03 | 17/03/2025 | 01/04/2025 | 14/04/2025 | 25/04/2025 | 06/05/2025 | 06/05/2025 | 07/05/2025 | 08/05/2025 | 16/05/2025 | 02/06/2025 | 2025-06-18 | 2025-06-18 | 2026-03-30 | 2026-04-05
TM04-Service | Air refrigerant refil | 8700 | 8700 | Micro | 2025-10-06 | 2025-10-07 | 2025-10-10 | 2025-10-10 | 2025-10-17 | 2025-10-20 | 2025-10-20 | N/A | N/A | 2025-10-20 | N/A | N/A | 27/10/2025 | 03/11/2025 | 2025-11-10
TM05-Service | Maintenance of primary school pots & airconditioner | 285500 | 285500 | Selective | 2025-03-03 | 17/03/2025 | 01/04/2025 | 14/04/2025 | 25/04/2025 | 06/05/2025 | 06/05/2025 | 07/05/2025 | 08/05/2025 | 16/05/2025 | 02/06/2025 | 2025-06-18 | 2025-06-18 | 2026-03-30 | 2026-04-05
TM06-Supplies | First Aid Kit Refill | 400 | 400 | Micro | 2025-10-06 | 2025-10-07 | 2025-10-10 | 2025-10-10 | 2025-10-17 | 2025-10-20 | 2025-10-20 | N/A | N/A | 2025-10-20 | N/A | N/A | 27/10/2025 | 03/11/2025 | 2025-11-10
TM07-Supplies | Small Tools & Plants | 15500 | 15500 | Micro | 2025-10-06 | 2025-10-07 | 2025-10-10 | 2025-10-10 | 2025-10-17 | 2025-10-20 | 2025-10-20 | N/A | N/A | 2025-10-20 | N/A | N/A | 27/10/2025 | 03/11/2025 | 2025-11-10
TM08-Service | Plant Maintenance | 200000 | 200000 | Selective | 2025-04-01 | 04/04/2025 | 07/04/2025 | 14/04/2025 | 18/04/2025 | 25/04/2025 | 25/04/2025 | 28/04/2025 | 28/04/2025 | 29/04/2025 | 16/05/2025 | 26/05/2025 | 26/05/2025 | 30/03/2025 | 2026-04-05
TM009-Service | Purchase of Office Furniture & Equipment | 138000 | 138000 | Selective | 2025-04-01 | 04/04/2025 | 07/04/2025 | 14/04/2025 | 18/04/2025 | 25/04/2025 | 25/04/2025 | 28/04/2025 | 28/04/2025 | 29/04/2025 | 16/05/2025 | N/A | 26/05/2025 | 28/08/2025 | 2025-09-05
TM11-Supplies | Supply & fitting of Tyres Tubes & Flaps | 179800 | 179800 | ODB | 2025-03-03 | 17/03/2025 | 01/04/2025 | 14/04/2025 | 25/04/2025 | 06/05/2025 | 06/05/2025 | 07/05/2025 | 08/05/2025 | 16/05/2025 | 02/06/2025 | 2025-06-18 | 2025-06-18 | 2026-03-30 | 2026-04-05
3203030
B. ELECTRICAL DIVISION
ELECT 01-Supplies | Maintenance of Streetlights | 334594 | 334594 | ODB | 2025-03-03 | 17/03/2025 | 01/04/2025 | 14/04/2025 | 25/04/2025 | 06/05/2025 | 06/05/2025 | 07/05/2025 | 08/05/2025 | 16/05/2025 | 02/06/2025 | 2025-06-18 | 2025-06-18 | 2026-03-30 | 2026-04-05
ELEC02-Supplies | Maintenance of Grounds and Buildings | 138565 | 138565 | ODB | 2025-03-03 | 17/03/2025 | 01/04/2025 | 14/04/2025 | 25/04/2025 | 06/05/2025 | 06/05/2025 | 07/05/2025 | 08/05/2025 | 16/05/2025 | 02/06/2025 | 2025-06-18 | 2025-06-18 | 2026-03-30 | 2026-04-05
ELEC03-Supplies | Small Tools and Plants | 15900 | 15900 | RFQ | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-29 | 2025-05-06 | 2025-05-20 | 2025-05-30 | 2025-06-10 | 2025-06-13 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2026-03-31
ELECT 04-Supplies | Plant Hire | 35750 | 35750 | RFQ | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-29 | 2025-05-06 | 2025-05-20 | 2025-05-30 | 2025-06-10 | 2025-06-13 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2026-03-31
ELECT 05-Supplies | Maintenance of Radio communication Equipment | 5000 | 5000 | Micro | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-29 | 2025-05-06 | 2025-05-20 | 2025-05-30 | 2025-06-10 | 2025-06-13 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2026-03-31
ELECT06-Supplies | Radio Communication Licencing | 5750 | 5750 | Micro | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-29 | 2025-05-06 | 2025-05-20 | 2025-05-30 | 2025-06-10 | 2025-06-13 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2026-03-31
535559
C. ROADS
Discipline | Project Description | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implemention | End of Activity report
ROADS 001-Works | Reinstatement of Road markings and replacement of road signs, desilting of culverts and vegetation control. (Road Fund Levy) | 0 | 0 | Open Domestic | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
ROADS 002-Works | Road paving, Edge Protection, Patching, Kerb-lining & construction of drainage systems. (CCP 25) | 0 | 0 | Open Domestic | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
ROADS 003-Supplies | PROCUREMENT OF ROADS MAINTENANCE MATERIAL | 151900 | 151900 | Restricted Domestic Bidding | 2025-03-03 | 17/03/2025 | 01/04/2025 | 14/04/2025 | 25/04/2025 | 06/05/2025 | 06/05/2025 | 07/05/2025 | 08/05/2025 | 16/05/2025 | 02/06/2025 | 2025-06-18 | 2025-06-18 | 2026-03-30 | 2026-04-05
151900
10. DEPARTMENT OF ARCHITECTURE & BUILDINGS SERVICES
Discipline | Project Description | Budget Amount (BWP) | Estimated Cost (BWP) | Method of Procurement | Preparation of ITT (Incl.TORS & market research) | Submission of ITT to POU for Vetting | Date of intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implemention | End of Activity report
SUPPLIES
AB 01 | Supply and delivery of buiding material and tools 08-203-BE-01 | Tender (Restricted to Hardwares within Locality) | 500000 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 02 | Small tools and Plants 08-301-BE-07 | Qoutation | 362280 | RFQ | 20/06/2025 | - | - | 27/06/2025 | 12/07/2025 | 16/07/2025 | 29/07/2025 | - | - | 29/07/2025 | 8/08/2025 | 08/08/2025 | 09/08/2025 | 10/10/2025
AB 03 | Backlog eradication: Construction of staff houses at plot 5523, Motswedi 1X4 LA2 flats | Tender | 3991531.9 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 04 | Backlog eradication: Construction of LA3 Nurses staff House | Tender | 1000000 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 05 | Expansion of Type 2 Customary Court Offices | Tender | 4, 822, 650.00 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 06 | Supply and delivery of stores material and drugs 08-301-BE-06 | Qoutation | 105210 | RFQ | 2025-05-05 | 2025-05-12 | 2025-05-26 | 2025-06-06 | 2025-06-06 | 2025-06-13 | 2025-06-27 | 2025-06-30 | 2025-07-15 | 2026-07-27 | 2026-07-27
AB 07 | Maintenance of 1No staff House 4055E (Package A) | Qoutation | 200000 | RFQ |  | 2025-05-05 | 2025-05-12 | 2025-05-26 | 2025-06-06 | 2025-06-06 | 2025-06-13 | 2025-06-27 | 2025-06-30 | 2025-07-01 | 2026-07-27 | 2026-07-27
AB 08 | Maintenance of 1No staff House 2587 (Package B) | Qoutation | 200000 | RFQ |  | 2025-05-05 | 2025-05-12 | 2026-05-26 | 2025-06-06 | 2025-06-06 | 2025-06-13 | 2025-06-27 | 2025-06-30 | 2025-07-01 | 2026-07-27 | 2026-02-27
AB 09 | Construction of Ablution block at Tsopeng Cemetry | Tender (Restricted to Local Contractors) | 276920 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 10 | Maintenance of toilets at Maitlamo Primary School | Qoutation | 100000 | RFQ |  | 2025-05-05 | 2025-05-12 | 2025-05-26 | 2025-06-06 | 2025-06-06 | 2025-06-13 | 2025-06-27 | 2025-06-30 | 2025-09-01 | 2026-02-27 | 2026-02-27
AB 11 | Maintenance of Maitlamo Primary School (Installation of white boards and Associated Works) | Tender (Restricted to Local Contractors) | 271810.42 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 12 | Installation of 2No. water Tanks & booster Pump at Civic Centre | Qoutation | 100000 | RFQ |  |  | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-16 | 2025-05-20 | 2025-06-03 | 2025-06-07 | 2025-07-05 | 2026-01-04 | 2026-01-05
AB 13 | Maintenance of house 1088 B at Jacaranda (Labour only) | Qoutation | 100000 | RFQ |  |  | 2025-05-20: 2025-05-06
AB 14 | Maintenance of 4No.Teachers Flats at Bothakga Primary School | Tender (Restricted to Local Contractors) | 560000 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 15 | Upgrading of 3 Bedroom house No:1088 to Execuctive Suit | Qoutation | 400000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
AB 16 | Maintenance of Transport Toilets and Office Block Roof | Qoutation | 100000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
AB 17 | Maintenance of 6No.Teachers Flats at Bothakga Primary School | Tender (Restricted to Local Contractors) | 775000 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 18 | Replacement of worn out fences to 5No. Staff houses | Qoutation | 150000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
AB 19 | Provision of floor tiles in 7No. Staff houses | Qoutation | 150800 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
AB 20 | Maintenance of 6No staff houses | Qoutation | 600000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
AB 21 | Erection of working timber cubicles in the drawing office | Qoutation | 100000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
AB 22 | Construction of timber counter with alluminium frame glass complete with automated door lock | Tender (Restricted to Local Contractors) | 300000 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 23 | Erection of 1800mm rear boundary wall with razor wire at civic center | Qoutation | 400000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
AB 24 | Construction of the reception area at the main entrance to the civic centre buildings | Tender (Restricted to Local Contractors) | 200000 | RDB | 06/06/2025 | 10/06/2025 | 2025-06-17 | 20/06/2025 | 04/07/2025 | 05/07/2025 | 10/07/2025 | 11/07/2025 | 2025-07-15 | 2025-07-16 | 01/08/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 31/03/2025
AB 25 | Provision of LTC logo and signage at Civic Centre main entrance gates | Qoutation | 50000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
AB 26 | Improvement of the signage and repair of the old block entrance doors at civic centre | Qoutation | 40000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
AB 27 | Design of Records centre,with CCTV cameras and specialised door | Tender (Restricted to Local Contractors) | 200000 | RDB | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-30 | 2026-06-29 | 2026-06-29
11233552.32
PARKS DIVISION
AB 28 | Maintenance of Civic Centre grounds | Qoutation | 300000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-15 | 2026-07-14 | 2026-07-14
AB 29 | Maintenance of Fire Brigade | Qoutation | 100000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-15 | 2026-07-14 | 2026-07-14
AB 30 | Maintenance of Town Park grounds (Survey, Drilling and Borehole equiping) | Tender | 400000 | RDB | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-15 | 2026-07-14 | 2026-07-14
AB 31 | Maintenance of Cemeteries grounds (Tsopeng) Fencing and casting and installation of numbered crosses | Qoutation | 100000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-15 | 2026-07-14 | 2026-07-14
AB 32 | Maintenance of Model day care Children playgrounds | Qoutation | 60000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-15 | 2026-07-14 | 2026-07-14
AB 33 | Redevelopment of Parks net house at Parks Nursery | Qoutation | 200000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-15 | 2026-07-14 | 2026-07-14
AB 34 | Maintenance of traffic Circles | Qoutation | 100000 | RFQ | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-01 | 2026-01-15 | 2026-07-14 | 2026-07-14
1260000
TOTAL LTC BUDGET-(COUNCIL) |  |  | P50 895 602,21
TOTAL LTC BUDGET( CLINICS) (HEALTH CARE-5) |  |  | P22 940 224,00
GRAND TOTAL LTC BUDGET (COUNCIL & CLINICS) |  |  | P73 835 826,21
DISPOSAL PLAN-LTC | 2025-07-01
(TWICE IN A FINANCIAL YEAR) | 2026-01-01
Lobatse Town Council
Address: QMPP+JHV,Lobatse,Botswana<br>Tel:+2675330241
Note on R1: Mpaphi Ikula:
Note on R32: Mpaphi Ikula:
Note on R53: Mpaphi Ikula:
Note on R60: Mpaphi Ikula:
Note on R65: Mpaphi Ikula:
Note on R78: Mpaphi Ikula:
Note on R104: Mpaphi Ikula:
Note on R199: Mpaphi Ikula:
Note on R205: Mpaphi Ikula: