## Sheet1
OKAVANGO DISTRICT COUNCIL
PPRA PROCUREMENT PLAN 2025-2026
Service | PROJECT DESCRIPTION | BUDGET AMOUNT | COST ESTIMATE (BWP) | PROCUREMENT METHOD | PREPARATION OF ITT (incl. TORs & market research) | SUBMISSION OF ITT TO POU FOR VETTING | DATE OF INTENDED PUBLICATION OF TENDER (where applicable) | ISSUING OF INVITATION TO TENDER | CLOSING DATE FOR TENDERS | EVALUATION OF TENDER BY EVALUATION COMMITTEE | VERIFICATION OF EVALUATION REPORT BY PU | SUBMISSION OF EVALUATION REPORT TO POU | PRE-ADJUDICATION BY POU | AWARD DECISION BY AO | COOLING OFF AND DEBRIEFING | CONTRACT SIGNING | COMMENCMENT OF PROJECT IMPLEMENTATION | COMPLETION OF PROJECT IMPLEMENTATION | END OF ACTIVITY REPORT
SERVICE | Hire of transport for delivery of construction materials to Jao flats | 614500 | 614500 | Restricted Domestic Bidding | 2025-04-04 | 2025-04-11 | 2025-04-22 | 2025-04-18 | 2025-04-30 | 2025-05-07 | 2025-05-12 | 2025-06-02 | 2025-06-04 | 2025-06-06 | 2025-06-20 | 2025-06-30 | 2025-07-07 | 2025-07-07
| Provision Tribal Administration Facilities of Human Security Services To Okavango District Council | 21057000 | 21057000 | Restricted Domestic Bidding | 2025-04-01 | 2025-04-08 | 2025-04-14 | 2025-05-05 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-30 | 2025-07-02 | 2025-07-04 | 2025-07-18 | 2025-07-30 | 2025-07-06 | 2026-07-06
| A tender for procurement of wireless conference systems at RAC Chambers | 500000 | 500000 | Restricted Domestic Bidding | 2025-05-09 | 2025-04-07 | 30/04/02025 | 2025-05-09 | 2025-05-23 | 2025-06-13 | 2025-06-17 | 2025-06-20 | 2025-06-24 | 2025-06-30 | 2025-07-11 | 2025-07-18 | 28/07/02025 | 2025-10-31
| A Service Contract for maintenance of Printers and Photocopiers for Okavango District Primary School, | 135000 | 135000 | Quotation Proposal Procurement | 2025-05-09 | 2025-02-10 | 2025-04-30 | 12/05/2025 | 2025-06-06 | 2025-03-19 | 24/03/20205 | 2025-04-17 | 2025-04-23 | 1905-07-17 | 2025-07-16 | 2025-07-25 | 2025-08-04 | 2026-08-04
| Provision of accomodation and meal for orphan retreat. | 337500 | 337500 | Direct Procurement | 2025-08-15 | 21/082025 | 2025-08-11 | 2025-09-29 | 2025-10-14 | 2025-10-31 | 2025-11-04 | 2025-10-07 | 2025-11-11 | 2025-12-14 | 2025-11-21 | 2025-11-25 | 2025-12-05 | 2025-12-12
| Provision of Food basket & Toiletry(CHBC) | 1520770 | 1520770 | Restricted Domestic Bidding | 2025-02-28 | 2025-03-07 | 2025-03-20 | 2025-04-14 | 2025-05-02 | 2025-05-12 | 2025-05-28 | 2025-06-03 | 2025-06-11 | 2025-06-13 | 2025-06-30 | 2025-06-04 | 2025-06-09 | 2026-06-09
| Provision of service contract for mortuary and coffins services. | 412500 | 412500 | Restricted Domestic Bidding | 2025-03-28 | 2025-04-04 | 2025-03-12 | 2025-04-17 | 2025-05-06 | 2025-05-23 | 2025-05-27 | 2025-05-28 | 2025-06-03 | 2025-06-05 | 2025-06-20 | 2025-06-26 | 2025-07-02 | 2025-07-02
| Consultancy services for the procurement of Startegic Environmental Assesment (SEA) study for five (5) Okavango District villages | 2000000 | 2000000 | Open Domestic Bidding | 2025-04-01 | 2025-04-07 | 2025-04-24 | 2025-05-05 | 2025-05-30 | 2025-06-13 | 2025-06-17 | 2025-06-19 | 2025-06-23 | 2025-06-27 | 2025-07-14 | 2025-07-18 | 2025-07-25 | 2025-07-25
| Procurement of Cleaning services at RAC(Old&New),Transport,Bus Rank and Procurement Unit. | 2064000 | 2064000 | Open Domestic Bidding | 2025-04-01 | 2025-04-07 | 2025-04-24 | 2025-05-05 | 2025-05-30 | 2025-06-13 | 2025-06-17 | 2025-06-19 | 2025-06-23 | 2025-06-27 | 2025-07-14 | 2025-07-18 | 2025-07-25 | 2025-07-25
| TOTAL AMOUNT (BWP) | 28641270 | 28641270
WORKS | Maintanance of staff houses | 400000 | 400000 | Open Domestic Bidding | 2025-07-11 | 2025-07-14 | 2025-08-07 | 2025-08-13 | 2025-08-29 | 2025-09-12 | 2025-09-16 | 2025-09-19 | 2025-09-23 | 2025-09-29 | 2025-10-15 | 2025-10-22 | 2025-10-31 | 2025-12-31
| Maintance of Jao Flats satellite Primary School,facilities at Jao Flats. | 150000 | 150000 | Quotation Proposal Procurement | 2025-09-05 | 2025-09-12 | 2025-09-25 | 2025-10-17 | 2025-10-31 | 2025-11-03 | 2025-11-14 | 2025-11-19 | 2025-11-21 | 2025-11-26 | 2025-12-10 | 2025-12-19 | 2025-12-31 | 2026-01-09
| Construction completion of RADP houses | 152000 | 152000 | Quotation Proposal Procurement | 2025-05-19 | 2025-05-23 | 2025-06-05 | 2025-06-13 | 2025-06-30 | 2025-07-11 | 2025-07-14 | 2025-07-18 | 2025-07-25 | 2025-07-29 | 2025-08-12 | 2025-08-15 | 2025-08-25 | 2025-12-31
| Maintenance of Toilet Blocks at Ngarange, Gunotsoga, Sekondomboro, Seronga | 200000 | 200000 | Quotation Proposal Procurement | 2025-07-15 | 2025-07-18 | 2025-07-31 | 2025-08-05 | 2025-08-20 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2015-09-16 | 2025-09-19 | 2025-10-03 | 2025-12-08 | 2025-10-15 | 31/11/2025
| Maintenance of Toilet Blocks at Kathiana, Mohembo, Samochima, Shakawe | 200000 | 200000 | Quotation Proposal Procurement | 2025-07-15 | 2025-07-18 | 2025-07-31 | 2025-08-05 | 2025-08-20 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2015-09-16 | 2025-09-19 | 2025-10-03 | 2025-12-08 | 2025-10-15 | 31/11/2025
| Construction of Executive Office in RAC, Gumare | 3000000 | 3000000 | Open Domestic Bidding | 2025-04-11 | 2025-04-17 | 2025-05-08 | 2025-05-20 | 2025-05-28 | 2025-06-13 | 2025-06-15 | 2025-06-20 | 2025-06-23 | 2025-06-26 | 2025-07-14 | 2025-07-16 | 2025-08-07 | 2025-08-07
| Construction of Executive LA3 House , Gumare | 2000000 | 2000000 | Restricted Domestic Bidding | 2025-04-14 | 2025-04-17 | 2025-08-01 | 2025-08-05 | 2020-08-19 | 2025-08-29 | 2025-09-02 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2025-09-26 | 2025-10-03 | 2025-10-08 | 2026-01-08
| Maintenance of Xakao RADP Hostel | 2000000 | 2000000 | Restricted Domestic Bidding | 2025-04-15 | 2025-04-17 | 2025-08-01 | 2025-08-05 | 2020-08-19 | 2025-08-29 | 2025-09-02 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2025-09-26 | 2025-10-03 | 2025-10-08 | 2026-01-08
| Construction of Type 1 Tribal Office at Shakawe | 4500000 | 4500000 | Restricted Domestic Bidding | 2025-04-17 | 2025-04-17 | 2025-05-08 | 2025-05-20 | 2025-05-28 | 2025-06-13 | 2025-06-15 | 2025-06-20 | 2025-06-23 | 2025-06-26 | 2025-07-14 | 2025-07-16 | 2025-08-07 | 2025-08-07
| Termite treatment and replacement of worn out roof trusses of Mohembo staff houses roof structures | 102000 | 102000 | Quotation Proposal Procurement | 2025-07-15 | 2025-07-18 | 2025-07-31 | 2025-08-05 | 2025-08-20 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2015-09-16 | 2025-09-19 | 2025-10-03 | 2025-12-08 | 2025-10-15 | 31/11/2025
| Construction of LA2 House in Gumare | 1000000 | 1000000 | Restricted Domestic Bidding | 2025-04-25 | 2025-04-30 | 2025-05-15 | 2025-05-22 | 2025-06-06 | 2025-06-30 | 2025-07-03 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-08-15 | 2025-08-20 | 2025-08-26 | 2025-11-26
| Maintenance of buildings and Roads and other sevices through out the district through CCP funds | 30000000 | 30000000 | Open Domestic Bidding
| Maintenance of fuel point in Gumare and Shakawe fuel | 220000 | 220000 | Open Domestic Bidding | 2025-04-04 | 2025-04-07 | 2025-04-22 | 2025-05-08 | 2025-05-23 | 2025-06-06 | 2025-06-10 | 2025-06-13 | 2025-06-17 | 2025-06-20 | 2025-07-04 | 2025-07-10 | 2025-07-17 | 2025-08-17
| Road signs installation and road marking of Gumare Internal roads | 1500000 | 1500000 | Restricted Domestic Bidding | 2025-05-26 | 2025-05-30 | 2025-06-12 | 2025-06-17 | 2025-06-30 | 2025-07-11 | 2025-07-15 | 2025-07-17 | 2025-07-23 | 2025-07-25 | 2025-08-08 | 2025-08-14 | 2025-08-21 | 2025-09-19
| Installation of Kerbstones in Gumare 6km | 2900000 | 2900000 | Open Domestic Bidding | 2025-05-26 | 2025-05-30 | 2025-06-12 | 2025-06-17 | 2025-06-30 | 2025-07-11 | 2025-07-15 | 2025-07-17 | 2025-07-23 | 2025-07-25 | 2025-08-08 | 2025-08-14 | 2025-08-21 | 2025-09-19
| Works contract for provision of resealing of Gumare internal roads 10km | 5600000 | 5600000 | Open Domestic Bidding | 2025-04-25 | 2025-04-30 | 2025-05-15 | 2025-05-22 | 2025-06-06 | 2025-06-30 | 2025-07-03 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-08-15 | 2025-08-20 | 2025-08-26 | 2025-11-26
| A works contract for maintenance of Etsha 6 solar streetlights | 288000 | 288000 | Quotation Proposal Procurement | 2025-04-29 | 2025-04-28 | 2025-05-15 | 2025-05-22 | 2025-06-06 | 2025-06-28 | 2025-07-03 | 2025-07-07 | 2025-07-10 | 2025-07-16 | 2025-07-31 | 2025-08-07 | 2025-08-25 | 2025-10-25
| A works contract for maintenance of Gumare solar streetlights | 360000 | 360000 | Direct Procurement | 2025-04-29 | 2025-04-28 | 2025-05-15 | 2025-05-22 | 2025-06-06 | 2025-06-28 | 2025-07-03 | 2025-07-07 | 2025-07-10 | 2025-07-16 | 2025-07-31 | 2025-08-07 | 2025-08-25 | 2025-10-25
| A works contract for maintenance of Seronga solar streetlights | 360000 | 360000 | Direct Procurement | 2025-04-29 | 2025-04-28 | 2025-05-15 | 2025-05-22 | 2025-06-06 | 2025-06-28 | 2025-07-03 | 2025-07-07 | 2025-07-10 | 2025-07-16 | 2025-07-31 | 2025-08-07 | 2025-08-25 | 2025-10-25
| A works contract for conversion of On-grid streetlights to solar streetlights in Gumare | 1620000 | 1620000 | Direct Procurement | 2025-04-29 | 2025-04-28 | 2025-05-15 | 2025-05-22 | 2025-06-06 | 2025-06-28 | 2025-07-03 | 2025-07-07 | 2025-07-10 | 2025-07-16 | 2025-07-31 | 2025-08-07 | 2025-08-25 | 2025-10-25
| TOTAL | 56552000 | 56552000
SUPPLIES | A Supplies contract for Supply and Delivery of Sorghum meal to Okavango District Council | 1137763.2 | 1137763.2 | Restricted Domestic Bidding | 2025-05-05 | 2025-05-08 | 2025-05-22 | 2025-05-27 | 2025-06-30 | 2025-07-11 | 2025-07-14 | 2025-07-18 | 2025-07-25 | 2025-07-29 | 2025-08-12 | 2025-08-15 | 2025-08-25 | 2025-12-31
| A Supplies contract for Supply and Delivery of UHT Fresh Milk to Okavango District Council | 6998146.6667 | 6998146.6667 | Open Domestic Bidding | 2025-05-05 | 2025-05-08 | 2025-05-22 | 2025-05-27 | 2025-06-30 | 2025-07-11 | 2025-07-14 | 2025-07-18 | 2025-07-25 | 2025-07-29 | 2025-08-12 | 2025-08-15 | 2025-08-25 | 2025-12-31
| A Supplies contract for Supply and Delivery of Fruit Jam and Peanut Butter to Okavango District Council | 7785551.04 | 7785551.04 | Open Domestic Bidding | 2025-04-28 | 2025-05-05 | 2025-05-22 | 2025-08-05 | 2025-08-20 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2015-09-16 | 2025-09-19 | 2025-10-03 | 2025-12-08 | 2025-10-15 | 31/11/2025
| A Supplies contract for Supply and Delivery of Sunflower Cooking Oil to Okavango District Council | 2573512 | 2573512 | Open Domestic Bidding | 2025-04-28 | 2025-04-30 | 2025-05-07 | 2025-05-16 | 2025-05-28 | 2025-06-13 | 2025-06-15 | 2025-06-20 | 2025-06-23 | 2025-06-26 | 2025-07-14 | 2025-07-16 | 2025-08-07 | 2025-08-07
| A Supplies contract for Supply and Delivery of LPG Cooking Gas for Okavango District Council | 943500 | 943500 | Open Domestic Bidding | 2025-05-12 | 2025-04-17 | 2025-08-01 | 2025-08-05 | 2020-08-19 | 2025-08-29 | 2025-09-02 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2025-09-26 | 2025-10-03 | 2025-10-08 | 2026-01-08
| A Supplies contract for Supply and Delivery of Uniform and Protective Clothing for Okavango District Council | 300000 | 300000 | Open Domestic Bidding | 2025-05-05 | 2025-05-08 | 2025-05-22 | 2025-05-27 | 2025-06-30 | 2025-07-11 | 2025-07-14 | 2025-07-18 | 2025-07-25 | 2025-07-29 | 2025-08-12 | 2025-08-15 | 2025-08-25 | 2025-12-31
| A supplies contract for Supply and Delivery of Electrical maitenance material for Okavango District Council | 335000 | 335000 | Restricted Domestic Bidding | 2025-04-17 | 2025-08-01 | 2025-08-05 | 2020-08-19 | 2025-08-29 | 2025-09-02 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2025-09-26 | 2025-10-03 | 2025-10-08 | 2026-01-08 | 2025-12-31
| A supplies contract for Supply and Delivery of Roads camping equipment for Okavango District Council | 140140 | 140140 | Quotation Proposal | 2025-04-25 | 2025-04-30 | 2025-05-15 | 2025-05-22 | 2025-06-06 | 2025-06-30 | 2025-07-03 | 2025-07-18 | 2025-07-25 | 2025-07-30 | 2025-08-15 | 2025-08-20 | 2025-08-26 | 2025-09-26
| A supplies contract for Supply and Delivery of Tyres and tubes to Okavango District Council | 669530 | 669530 | Restricted Domestic Bidding | 2025-05-12 | 2025-07-18 | 2025-07-31 | 2025-08-05 | 2025-08-20 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2015-09-16 | 2025-09-19 | 2025-10-03 | 2025-12-08 | 2025-10-15 | 31/11/2025
| A supplies contract for Supply and Delivery of Oils and lubricants to Okavango District Council | 366000 | 366000 | Open Domestic Bidding | 2025-04-14 | 2025-04-17 | 2025-05-08 | 2025-05-20 | 2025-05-28 | 2025-06-13 | 2025-06-15 | 2025-06-20 | 2025-06-23 | 2025-06-26 | 2025-07-14 | 2025-07-16 | 2025-08-07 | 2025-08-07
| A Supplies contract for supply and delivery of motor vehicle spare parts to Okavango District Council | 4349370 | 4349370 | Open Domestic Bidding | 2025-04-14 | 2025-04-17 | 2025-08-01 | 2025-08-05 | 2020-08-19 | 2025-08-29 | 2025-09-02 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2025-09-26 | 2025-10-03 | 2025-10-08 | 2026-01-08
| A supplies contract for supply and delivery of motor vehicle and related equipment to Okavango District Council | 5300000 | 5300000 | Open Domestic Bidding | 2025-04-15 | 2025-04-17 | 2025-08-01 | 2025-08-05 | 2020-08-19 | 2025-08-29 | 2025-09-02 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2025-09-26 | 2025-10-03 | 2025-10-08 | 2026-01-08
| A supplies contract for supply and delivery of small tools for maintenance works for Okavango District Council | 342590 | 342590 | Restricted Domestic Bidding | 2025-04-04 | 2025-04-07 | 2025-04-22 | 2025-05-08 | 2025-05-23 | 2025-06-06 | 2025-06-10 | 2025-06-13 | 2025-06-17 | 2025-06-20 | 2025-07-04 | 2025-07-10 | 2025-07-17 | 2025-08-17
| A supplies contract for supply and delivery of Truck Bus to Okavango District Council | 2000000 | 2000000 | Restricted Domestic Bidding | 2025-04-28 | 2025-04-30 | 2025-05-07 | 2025-05-16 | 2025-05-28 | 2025-06-13 | 2025-06-15 | 2025-06-20 | 2025-06-23 | 2025-06-26 | 2025-07-14 | 2025-07-16 | 2025-08-07 | 2025-08-07
| Tender for supply & delivery of computers, laptops and accessories to Okavango District Council | 150000 | 150000 | Quotation Proposal | 2025-04-15 | 2025-04-17 | 2025-08-01 | 2025-08-05 | 2020-08-19 | 2025-08-29 | 2025-09-02 | 2025-09-05 | 2025-09-09 | 2025-09-12 | 2025-09-26 | 2025-10-03 | 2025-10-08 | 2025-12-08
| TOTAL | 33391102.9067 | 33391102.9067