## AUDIT
MABUTSANE DISTRICT COUNCIL 2025/2026 PROCUREMENT PLAN
Discipline | Project Description | Budget Amount(BWP) | Estimated cost (BWP) | Method of procument | Preparation of ITT (inc.Tors & Market research | Submission of ITT to POU for vetting | Date of intended publication of tender(where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-adjudication by POU | Award decision by AO | Cooling Off and debriefing | Contract signing | Commencement of project implementation | Completion of project implementation | End of activity
SUPPLIES
| Supply and Delivery of Printing,stationery and advertising | 131505 | 131505 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Supply and Delivery of Computers and Accessories | 827300 | 827300 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Supply of electrical maintenance materials | 300000 | 300000 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Supply of airconditioner maintenance materials | 150000 | 150000 | Restricted Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-24 | 2025-04-28 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-26 | 2025-05-28 | 2025-05-29 | 2025-12-31 | 2026-01-31
| Supply of SMALL TOOLS (jacks, reflective tape, fire extinguishers | 107200 | 107200 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Supply of vehicle maintenance and repair parts | 974500 | 974500 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Tyre services tender | 441900 | 441900 | Restricted Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-24 | 2025-04-28 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-26 | 2025-05-28 | 2025-05-29 | 2025-12-31 | 2026-01-31
| Supply of road signs | 309000 | 309000 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Supply and delivery of stationery, equipment and consumable materials to Primary Schools | 800000 | 800000 | Restricted Domestic | 2025-09-12 | 2025-09-16 | 2025-09-17 | 2025-09-17 | 2025-10-06 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-31 | 2025-11-03 | 2025-11-04 | 2026-11-04 | 2026-12-04
| Supply and delivery of Jam & Peanut Butter Spreads for primary schools | 551653 | 551653 | Restricted Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-24 | 2025-04-28 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-26 | 2025-05-28 | 2025-05-29 | 2025-12-31 | 2025-01-31
| Supply and delivery of 750 ml Sunflower Oil | 1060000 | 1060000 | Restricted Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-24 | 2025-04-28 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-26 | 2025-05-28 | 2025-05-29 | 2026-05-29 | 2026-06-30
| Supply and delivery of Beans for primary schools | 940524 | 940524 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Supply and Delivery of Refuse bags, dustbins & surgical gloves for Mabutsane District Council | 163567 | 163567 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Provision to cater for office furniture for new offices and offices outside RAC | 910610 | 910610 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Procurement of irrigation systems and netshading at Kutuku | 250000 | 250000 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-07-31 | 2025-08-29
| Procurement of reservoir at Kutuku | 250000 | 250000 | Restricted Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-24 | 2025-04-28 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-26 | 2025-05-28 | 2025-05-29 | 2025-06-30 | 2025-07-31
| Supply of camping equipments | 55150 | 55150 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-09-30 | 2025-10-30
| Provision of Clothing for participants, Mr and Miss RADP | 80000 | 80000 | RFQ | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-08-01 | 2025-08-04 | 2025-08-05 | 2025-10-25 | 2025-11-30
| Supply and delivery of food and fresh produce to Kanaku day care centre | 90000 | 90000 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-12-31 | 2026-01-31
| Supply of batteries | 25500 | 25500 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-09-30 | 2025-10-30
| Supply of DOMESTIC REQUISITES (toilet paper and Mosquito repellent) | 32190 | 32190 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-09-30 | 2025-10-30
| supply of borehole maintenance materials | 60000 | 60000 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-09-30 | 2025-10-30
| Procurement of seedlings and fertilizers at Kutuku | 100000 | 100000 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-09-30 | 2025-10-30
| SUB TOTAL | 8610599 | 8610599
SERVICES
| Procurement of street light maintenance materials | 175000 | 175000 | Restricted Domestic | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-24 | 2025-04-28 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-26 | 2025-05-28 | 2025-05-29 | 2025-06-30 | 2025-07-31 | 2025-08-29
| Procurement of refreshments for the District Clean-up Campaings | 134600 | 134600 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Network Maintenance | 150000 | 150000 | Restricted Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-24 | 2025-04-28 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-26 | 2025-05-28 | 2025-05-29 | 2025-12-31 | 2026-01-31
| UPS Maintenance | 130000 | 130000 | Restricted Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-24 | 2025-04-28 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-26 | 2025-05-28 | 2025-05-29 | 2025-12-31 | 2026-01-31
| Maintanance of computers & photocopiers | 150000 | 150000 | Restricted Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-24 | 2025-04-28 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-26 | 2025-05-28 | 2025-05-29 | 2025-12-31 | 2026-01-31
| Psychosocial support for S&CD staff retreat | 375000 | 375000 | Open Domestic | 2025-06-11 | 2025-06-13 | 2025-06-16 | 2025-06-16 | 2025-07-16 | 2025-07-17 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-14 | 2025-08-15 | 2025-08-18 | 2025-08-22 | 2025-09-22
| Psychosocial retreat camp for orphans and vulnerable children | 400000 | 400000 | Open Domestic | 2025-07-31 | 2025-08-04 | 2025-08-05 | 2025-08-05 | 2025-09-02 | 2025-09-03 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-16 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-10 | 2025-11-10
| Stakeholders workshop for child protection | 150000 | 150000 | Open Domestic | 2025-06-04 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-07-08 | 2025-07-09 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-23 | 2025-08-06 | 2025-08-08 | 2025-08-11 | 2025-08-15 | 2025-09-15
| Provision of private clothing to OVCs & CHBC | 594000 | 594000 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Provision of bedding to OVCs & CHBC | 277000 | 277000 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-12-31 | 2026-01-31
| Therapy for abused children | 300000 | 300000 | Direct Appointment | 2025-06-04 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-16 | 2025-06-17 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | N/A | 2025-06-30 | 2025-07-02 | 2026-07-02 | 2026-08-03
| Boy children retreat | 300000 | 300000 | Direct Appointment | 2025-06-04 | 2025-07-08 | 2025-06-12 | 2025-06-26 | 2025-07-05 | 2025-07-12 | 2025-07-15 | 2025-07-16 | 2025-07-18 | 2025-07-23 | N/A | 2025-07-25 | 2025-07-28 | 2025-08-01 | 2025-09-01
| Procurement of electricity units/bills for street lights | 80000 | 80000 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-09-30 | 2025-10-30
| Maintenance of standby generator | 50000 | 50000 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-09-30 | 2025-10-30
| Cleanest village & Beautification commemoration | 59430 | 59430 | RFQ | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-11 | 2025-06-17 | 2025-06-18 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-30 | 2025-07-15 | 2025-07-17 | 2025-07-23 | 2025-07-24 | 2025-08-25
| Preparation of Khakhea Structure Plan | 100000 | 100000 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-06-30 | 2025-07-11 | 2025-07-31
| Caregivers workshop | 100000 | 100000 | RFQ | 2025-12-09 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-17 | 2025-12-18 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-05 | 2026-01-16 | 2026-01-19 | 2026-01-21 | 2026-01-30 | 2026-02-28
| Capacity building workshop for S & CD staff | 150000 | 150000 | RFQ | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-11 | 2025-06-17 | 2025-06-18 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-30 | 2025-07-15 | 2025-07-17 | 2025-07-23 | 2025-07-24 | 2025-08-25
| Private House Leasing | 1170000 | 1170000 | Expression of Interest (EOI) | 2025-05-02 | 2025-05-05 | 2025-05-06 | 2025-05-13 | 2025-08-13 | 2025-08-14 | 2025-08-22 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-09-10 | 2025-09-12 | 2025-09-15 | 2026-09-15 | 2026-09-29
| SUB TOTAL | 4845030 | 4845030
WORKS
| Supply and installation of air condidioners | 540000 | 540000 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-07-17 | 2025-08-15
| Spot Improvement in Morwamosu | 750000 | 750000 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-07-17 | 2025-08-15
| Upgrading of 4No. staff houses to Executive Houses 08-203-BE-01 | 600000 | 600000 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-07-17 | 2025-08-15
| Major maintenance of 20No. Staff houses | 900000 | 900000 | Open Domestic | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-05-15 | 2025-05-19 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-06-12 | 2025-06-16 | 2025-06-17 | 2025-07-17 | 2025-08-15
| Maintenance of General payment and HR office | 100000 | 100000 | RFQ | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-15 | 2025-04-22 | 2025-04-23 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-06-30 | 2025-07-31 | 2025-08-29
| Procurement for maintanance of Waste Disposal Sites in Mabutsane District Council | 70680 | 70680 | RFQ | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-24 | 2025-04-29 | 2025-04-30 | 2025-05-09 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-28 | 2025-05-30 | 2025-06-02 | 2025-07-02 | 2025-07-31
| SUB TOTAL | 2960680 | 2960680
| GRAND TOTAL | 16416309 | 16416309