## Sheet1
Discipline | Project description | Budget Amount BWP | Estimated cost BWP | Procurement Method | Month | Preparation of ITT(Incl…TOR's& market reaserch) | Submission of ITT to POU for vetting | Date of intended publication of tender (where applicable) | Issuing of invitation to tender | Closing date for tenders | Evaluation of tender by Evaluation Committee | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision by AO | Cooling Off and Debriefing | Contract Signing | Commencement of project implementation | Completion of project implementation | End of Activity report
Estates
Services | Rent subsidy lease contract | 72000 | 71500 | Micro | Dec 2025 | N/A | N/A | N/A | 27.11.2025 | 02.12.2025 | 03.12.2025 | 08.12.2025 | N/A | N/A | 10.12.2025 | N/A | 15.12.2025 | 01.01.2026 | 31.12.2029 | 31.12.2029
Services | Rent Private accomodation to the Land Board | 322300 | 321500 | Open domestic bidding | March 2026 | 06.01.2026 | 12.01.2026 | 30.01.2026 | 30.01.2026 | 13.02.2026 | 17.02.2026 | 24.02.2026 | 27.02.2026 | 02.03.2026 | 10.03.2026 | 24.03.2026 | 26.03.2026 | 01.04.2026 | 30.03.2029 | 30.03.2029
Procurement
Supplies | Procurement of Protective clothing | 92150 | 91000 | QPP | June 2025 | 23.04.2025 | N/A | N/A | 30.04.2025 | 09.05.2025 | 16.05.2025 | 19.05.2025 | 22.05.2025 | 30.05.2025 | 02.06.2025 | 03.06.2025 | 17.06.2025 | 17.06.2025 | 30.06.2025 | 01.07.2025
Supplies | Small tools and plants | 1050 | 1000 | Micro | Sept 2025 | 16.09.2025 | N/A | N/A | 15.09.2025 | 16.09.2025 | 17.09.2025 | 18.09.2025 | N/A | N/A | 19.09.2025 | N/A | N/A | 22.09.2025 | 24.09.2025 | 25.09.2025
Supplies | Stationer and toners | 164270 | 161000 | QPP | June 2025 | 23.04.2025 | N/A | N/A | 30.04.2025 | 09.05.2025 | 16.05.2025 | 19.05.2025 | 22.05.2025 | 30.05.2025 | 02.06.2025 | 03.06.2025 | 17.06.2025 | 17.06.2025 | 30.06.2025 | 01.07.2025
RMU
Service | Franking Machine Airtime | P37,500.00 | 36500 | Micro | June 2025 | 09.06.2025 | N/A | N/A | 10.06.2025 | 12.06.2025 | 12.06.2025 | 13.06.2025 | N/A | N/A | 16.06.2025 | N/A | N/A | 16.06.2025 | 19.06.2025 | 20.06.2025
Supplies | Franking Machine Ribbon | P24,190.00 | 23190 | Micro | June 2025 | 09.06.2025 | N/A | N/A | 10.06.2025 | 12.06.2025 | 12.06.2025 | 13.06.2025 | N/A | N/A | 16.06.2025 | N/A | N/A | 16.06.2025 | 19.06.2025 | 20.06.2025
Service | Franking Machine Service | P17,000.00 | 16000 | Micro | June 2025 | 09.06.2025 | N/A | N/A | 10.06.2025 | 12.06.2025 | 12.06.2025 | 13.06.2025 | N/A | N/A | 16.06.2025 | N/A | N/A | 16.06.2025 | 19.06.2025 | 20.06.2025
Service | Postal Rental | P3,540.00 | 3400 | Micro | 2025-12-01 | 26.11.2025 | N/A | N/A | 27.11.2025 | 01.12.2025 | 02.12.2025 | 03.12.2025 | N/A | N/A | 04.12.2025 | N/A | N/A | 04.12.2025 | 08.12.2025 | 09.12.2025
Service | Courier Service | P18,000.00 | 17000 | Micro | 2025-05-01 | May | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 16.05.2025 | 16.05.2025 | 30.03.2026 | 31.03.2026
AUTO
Services | 450,000 km Service for B295ANS 450,000 KM | 6000 | 5500 | Micro | June 2025 | 08.06.2025 | N/A | N/A | 06.06.2025 | 09.06.2025 | 10.06.2025 | 10.06.2025 | N/A | N/A | 11.06.2025 | N/A | N/A | 11.06.2025 | 13.06.2025 | 13.06.2025
Services | 21000KM Service for B213BIC | 6000 | 5500 | Micro | June 2025 | Week 2 | N/A | N/A | 06.06.2025 | 09.06.2025 | 10.06.2025 | 10.06.2025 | N/A | N/A | 11.06.2025 | N/A | N/A | 11.06.2025 | 13.06.2025 | 13.06.2025
Services | 18000KM Service for B217BIC | 6000 | 5500 | Micro | April 2025 | 04.04.2025 | N/A | N/A | 08.04.2025 | 09.04.2025 | 10.04.2025 | 11.04.2025 | N/A | N/A | 14.04.2025 | N/A | N/A | 14.04.2025 | 25.04.2025 | 25.04.2025
Services | 220000KM Service for B219BIC | 6000 | 5500 | Micro | May 2025 | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | 160000KM Service for B779 BIF | 6000 | 5500 | Micro | May 2025 | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | 140000KM Service for B443 BIE | 5000 | 5500 | Micro | July 2025 | 08.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 14.07.2025 | 15.07.2025 | N/A | N/A | 15.07.2025 | N/A | N/A | 15.07.2025 | 18.07.2025 | 18.07.2025
Services | 165000KM Service for B484 AZK | 6000 | 5500 | Micro | May 2025 | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | 230000KM Service for B863 AZK | 6000 | 6000 | Micro | May 2025 | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | 90000KM Service for B959 BIE | 6000 | 5500 | Micro | April 2025 | 04.04.2025 | N/A | N/A | 08.04.2025 | 09.04.2025 | 10.04.2025 | 11.04.2025 | N/A | N/A | 14.04.2025 | N/A | N/A | 14.04.2025 | 25.04.2025 | 25.04.2025
Services | 375000KM Service for B831 ANT | 23000 | 20000 | Micro | Sept 2025 | 03.09.2025 | N/A | N/A | 04.09.2025 | 08.09.2025 | 08.09.2025 | 09.09.2025 | N/A | N/A | 10.09.2025 | N/A | N/A | 10.09.2025 | 12.09.2025 | 12.09.2025
Services | 270000KM Service for B447 BBJ | 6000 | 5500 | Micro | July 2025 | 06.07.2025 | N/A | N/A | 08.07.2025 | 09.07.2025 | 11.07.2025 | 14.07.2025 | N/A | N/A | 15.07.2025 | N/A | N/A | N/A | 18.07.2025 | 18.07.2025
Services | 270000KM Service for B404 BBJ | 6000 | 5500 | Micro | June 2025 | 05.06.2025 | N/A | N/A | 08.06.2025 | 09.06.2025 | 10.06.2025 | 10.06.2025 | N/A | N/A | 11.06.2025 | N/A | N/A | 11.06.2025 | 13.06.2025 | 13.06.2025
Services | 210000KM Service for B290 ANS | 6000 | 5500 | Micro | July 2025 | 08.07.2025 | N/A | N/A | N/A | 09.07.2025 | 11.07.2025 | 14.07.2025 | N/A | N/A | 15.07.2025 | N/A | N/A | 15.07.2025 | 18.07.2025 | 18.07.2025
Services | 220000KM Service for B497 AOL | 6000 | 5500 | Micro | August 2025 | 06.08.2025 | N/A | N/A | 07.08.2025 | 11.08.2025 | 11.08.2025 | 12.08.2025 | N/A | N/A | 13.08.2025 | N/A | N/A | 13.08.2025 | 15.08.2025 | 15.08.2025
Services | 305000KMservice for B908AOI | 6000 | 5500 | Micro | Sept 2025 | 03.09.2025 | N/A | N/A | 04.09.2025 | 08.09.2025 | 08.09.2025 | 09.09.2025 | N/A | N/A | 10.09.2025 | N/A | N/A | 10.09.2025 | 12.09.2025 | 12.09.2025
Services | 255000KM Serice for B617AWX | 6000 | 5500 | Micro | May 2025 | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | 460000KM Service for B295 ANS | 6000 | 5500 | Micro | Sept 2025 | 03.09.2025 | N/A | N/A | 04.09.2025 | 08.09.2025 | 08.09.2025 | 09.09.2025 | N/A | N/A | 10.09.2025 | N/A | N/A | 10.09.2025 | 12.09.2025 | 12.09.2025
Services | 220000KM Service for B213 BIC | 6000 | 5500 | Micro | Oct 2025 | 09.10.2025 | N/A | N/A | 10.10.2025 | 13.10.2025 | 13.10.2025 | 14.10.2025 | N/A | N/A | 15.10.2025 | N/A | N/A | 15.10.2025 | 17.10.2025 | 17.10.2025
Services | 190000 KM Service for B217 BIC | 6000 | 5500 | Micro | Nov 2025 | 07.11.2025 | N/A | N/A | 10.11.2025 | 11.11.2025 | 11.11.2025 | 12.11.2025 | N/A | N/A | 12.11.2025 | N/A | N/A | 12.11.2025 | 14.11.2025 | 14.11.2025
Services | 23000KM Service for B219 BIC | 6000 | 5500 | Micro | Sept 2025 | 03.09.2025 | N/A | N/A | 04.09.2025 | 08.09.2025 | 08.09.2025 | 09.09.2025 | N/A | N/A | 10.09.2025 | N/A | N/A | 10.09.2025 | 12.09.2025 | 12.09.2025
Services | 170000KM Service for B779 BIF | 6000 | 5500 | Micro | Sept 2025 | 03.09.2025 | N/A | N/A | 04.09.2025 | 08.09.2025 | 08.09.2025 | 09.09.2025 | N/A | N/A | 10.09.2025 | N/A | N/A | 10.09.2025 | 12.09.2025 | 12.09.2025
Services | 150000KM Service for B443 BIE | 6000 | 5500 | Micro | Nov 2025 | 07.11.2025 | N/A | N/A | 10.11.2025 | 11.11.2025 | 11.11.2025 | 12.11.2025 | N/A | N/A | 12.11.2025 | N/A | N/A | 12.11.2025 | 14.11.2025 | 14.11.2025
Services | 180000KM Service for B484 AZK | 6000 | 5500 | Micro | Dec 2025 | 09.12.2025 | N/A | N/A | 09.12.2025 | 10.12.2025 | 10.12.2025 | 10.12.2025 | N/A | N/A | 10.12.2025 | N/A | N/A | 10.12.2025 | 12.12.2025 | 12.12.2025
Services | 240000KM Service for B863 AZK | 6000 | 5500 | Micro | Nov 2025 | 07.11.2025 | N/A | N/A | 10.11.2025 | 11.11.2025 | 11.11.2025 | 12.11.2025 | N/A | N/A | 12.11.2025 | N/A | N/A | 12.11.2025 | 14.11.2025 | 14.11.2025
Services | 100000KM Service for B959 BIE | 6000 | 5500 | Micro | Dec 2025 | 09.12.2025 | N/A | N/A | 09.12.2025 | 10.12.2025 | 10.12.2025 | 10.12.2025 | N/A | N/A | 10.12.2025 | N/A | N/A | 10.12.2025 | 12.12.2025 | 12.12.2025
Services | 285000KM Service for B447 BBJ | 6000 | 5500 | Micro | Nov 2025 | 07.11.2025 | N/A | N/A | 10.11.2025 | 11.11.2025 | 11.11.2025 | 12.11.2025 | N/A | N/A | 12.11.2025 | N/A | N/A | 12.11.2025 | 14.11.2025 | 14.11.2025
Services | 285000KM Service for B404 BBJ | 6000 | 5500 | Micro | Oct 2025 | 09.10.2025 | N/A | N/A | 10.10.2025 | 13.10.2025 | 13.10.2025 | 14.10.2025 | N/A | N/A | 15.10.2025 | N/A | N/A | 15.10.2025 | 17.10.2025 | 17.10.2025
Services | 420000KM Service for B290 ANS | 6000 | 5500 | Micro | Nov 2025 | 07.11.2025 | N/A | N/A | 10.11.2025 | 11.11.2025 | 11.11.2025 | 12.11.2025 | N/A | N/A | 12.11.2025 | N/A | N/A | 12.11.2025 | 14.11.2025 | 14.11.2025
Services | 230000KM Service for B497 AOL | 6000 | 5500 | Micro | Dec 25 | 09.12.2025 | N/A | N/A | 09.12.2025 | 10.12.2025 | 10.12.2025 | 10.12.2025 | N/A | N/A | 10.12.2025 | N/A | N/A | 10.12.2025 | 12.12.2025 | 12.12.2025
Services | 320000KM Service for B908 AOI | 6000 | 5500 | Micro | Dec 25 | 09.12.2025 | N/A | N/A | 09.12.2025 | 10.12.2025 | 10.12.2025 | 10.12.2025 | N/A | N/A | 10.12.2025 | N/A | N/A | 10.12.2025 | 12.12.2025 | 12.12.2025
Services | 270000KM Sevbice for B617 AWX | 6000 | 5500 | Micro | Dec 25 | 09.12.2025 | N/A | N/A | 09.12.2025 | 10.12.2025 | 10.12.2025 | 10.12.2025 | N/A | N/A | 10.12.2025 | N/A | N/A | 10.12.2025 | 12.12.2025 | 12.12.2025
Repair | B295 ANS , B290 ANS, Repair of door lock | 6000 | 5500 | Micro | 2025-04-01 | 04.04.2025 | N/A | N/A | 08.04.2025 | 09.04.2025 | 10.04.2025 | 11.04.2025 | N/A | N/A | 14.04.2025 | N/A | N/A | 14.04.2025 | 25.04.2025 | 25.04.2025
Repair | Replace Windscreen for B779 BIF , B4447 BBJ, B295 ANS | 7500 | 7000 | Micro | 2025-04-01 | 04.04.2025 | N/A | N/A | 08.04.2025 | 09.04.2025 | 10.04.2025 | 11.04.2025 | N/A | N/A | 14.04.2025 | N/A | N/A | 14.04.2025 | 25.04.2025 | 25.04.2025
Supplies | Batteries for booster | 500 | 500 | Micro | 2025-04-01 | 04.04.2025 | N/A | N/A | 08.04.2025 | 09.04.2025 | 10.04.2025 | 11.04.2025 | N/A | N/A | 14.04.2025 | N/A | N/A | 14.04.2025 | 25.04.2025 | 25.04.2025
Services | Atttend airconditioner for B908 AOI & B863 AZK | 4000 | 3800 | Micro | 2025-04-01 | 04.04.2025 | N/A | N/A | 08.04.2025 | 09.04.2025 | 10.04.2025 | 11.04.2025 | N/A | N/A | 14.04.2025 | N/A | N/A | 14.04.2025 | 25.04.2025 | 25.04.2025
Supplies | Tyres for B497 AOL & B863 AZK, B779 BIE, B290 ANS | 24700 | 24000 | Micro | 2025-04-01 | 04.04.2025 | N/A | N/A | 08.04.2025 | 09.04.2025 | 10.04.2025 | 11.04.2025 | N/A | N/A | 14.04.2025 | N/A | N/A | 14.04.2025 | 25.04.2025 | 25.04.2025
INFORMATION SYSTEM
Supplies | configuration of offsite backup | 150000 | 148000 | Micro | 30 Sept 2025 | 04.09.2025 | N/A | N/A | 05.09.2025 | 12.09.2025 | 12.09.2025 | 15.09.2025 | N/A | N/A | 15.09.2025 | N/A | N/A | 15.09.2025 | 19.09.2025 | 19.09.2025
Supplies | procurement of laptops | 80000 | 79000 | Micro | 2025-06-30 | 04.09.2025 | N/A | N/A | 05.09.2025 | 12.09.2025 | 12.09.2025 | 15.09.2025 | N/A | N/A | 15.09.2025 | N/A | N/A | 15.09.2025 | 19.09.2025 | 19.09.2025
Services | preventative maintenance of servers | 30000 | 29000 | Micro | 30 Sept 2025 | 04.09.2025 | N/A | N/A | 05.09.2025 | 12.09.2025 | 12.09.2025 | 15.09.2025 | N/A | N/A | 15.09.2025 | N/A | N/A | 15.09.2025 | 19.09.2025 | 19.09.2025
Services | preventative maintenance of servers | 30000 | 29000 | Micro | 31 March 2026 | 04.09.2025 | N/A | N/A | 05.09.2025 | 12.09.2025 | 12.09.2025 | 15.09.2025 | N/A | N/A | 15.09.2025 | N/A | N/A | 15.09.2025 | 19.09.2025 | 19.09.2025
Services | preventative maintenance of UPS | 20000 | 20000 | Micro | 30 Sept 2025 | 04.09.2025 | N/A | N/A | 05.09.2025 | 12.09.2025 | 12.09.2025 | 15.09.2025 | N/A | N/A | 15.09.2025 | N/A | N/A | 15.09.2025 | 19.09.2025 | 19.09.2025
HR
Supplies | First Aid kit refill | 800 | 800 | Micro | April | 04.04.2025 | N/A | N/A | 08.04.2025 | 09.04.2025 | 10.04.2025 | 11.04.2025 | N/A | N/A | 14.04.2025 | N/A | N/A | 14.04.2025 | 25.04.2025 | 25.04.2025
Buildings
Services | Service and repair of power back-up generator | 30 000,00 | 29000 | Micro | May 2025 | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | Service of fire equipments | 30 000,00 | 28000 | Micro | 2025-07-01 | 08.07.2025 | N/A | N/A | N/A | 09.07.2025 | 11.07.2025 | 14.07.2025 | N/A | N/A | 15.07.2025 | N/A | N/A | 15.07.2025 | 18.07.2025 | 18.07.2025
Services | Service of airconditioners | 40 000,00 | 39000 | Micro | 2025-06-01 | 09.06.2025 | N/A | N/A | 10.06.2025 | 12.06.2025 | 12.06.2025 | 13.06.2025 | N/A | N/A | 16.06.2025 | N/A | N/A | 16.06.2025 | 19.06.2025 | 20.06.2025
Services | Draining of septic tanks | 28 000,00 | 27000 | Micro | 2025-08-01 | 06.08.2025 | N/A | N/A | 07.08.2025 | 11.08.2025 | 11.08.2025 | 12.08.2025 | N/A | N/A | 13.08.2025 | N/A | N/A | 13.08.2025 | 15.08.2025 | 15.08.2025
Services | Minor maintanance of TLB Premises | 210 000,00 | 205000 | QPP | 2025-05-01 | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Works | Major maintenance of office | 50 000,00 | 49000 | Micro | 2025-10-01 | 09.10.2025 | N/A | N/A | 10.10.2025 | 13.10.2025 | 13.10.2025 | 14.10.2025 | N/A | N/A | 15.10.2025 | N/A | N/A | 15.10.2025 | 17.10.2025 | 17.10.2025
Supplies | Purchase of 4 burner gas stoves | 10 000,00 | 9500 | Micro | 2025-05-01 | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
SURVEYS
Supplies | Round bar 6m @12 mm | 30000 | 28500 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | 300 x Standard pegs (2.4m) | 37500 | 36000 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | Danger tape 50 m | 5000 | 4900 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | White wash | 1500 | 1450 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | Round bar 6m @ 20 mm | 3000 | 2900 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | CADASTRAL GPS external batteries | 7500 | 7000 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | Panga knives handles | 1000 | 1000 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | Panga knives | 2250 | 2000 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | 100* AO plotting film paper | 30000 | 29000 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | 100* AO plotting film paper | 45000 | 44000 | Micro | Jun | 16.06.2025 | N/A | N/A | 16.06.2025 | 18.06.2025 | 18.06.2025 | 19.06.2025 | N/A | N/A | 20.06.2025 | N/A | N/A | 20.06.2025 | 20.06.2025 | 20.06..2025
Supplies | 100 x AO Plotting bond paper | 6000 | 5900 | Micro | Jun | 23.06.2025 | N/A | N/A | 23.06.2025 | 25.06.2025 | 25.06.2025 | 26.06.2025 | N/A | N/A | 27.06.2025 | N/A | N/A | 27.06.2025 | 30.06.2025 | 30.07.2025
Supplies | Tape measure 100 ml | 400 | 390 | Micro | Jun | 23.06.2025 | N/A | N/A | 23.06.2025 | 25.06.2025 | 25.06.2025 | 26.06.2025 | N/A | N/A | 27.06.2025 | N/A | N/A | 27.06.2025 | 30.06.2025 | 30.07.2025
Supplies | Trig plates/ adopter | 2000 | 1800 | Micro | Jun | 23.06.2025 | N/A | N/A | 23.06.2025 | 25.06.2025 | 25.06.2025 | 26.06.2025 | N/A | N/A | 27.06.2025 | N/A | N/A | 27.06.2025 | 30.06.2025 | 30.07.2025
Supplies | Round bar 6m @12 mm | 30000 | 28000 | Micro | Jul | 03.07.2025 | N/A | N/A | 04.07.2025 | 08.07.2025 | 08.07.2025 | 09.07.2025 | N/A | N/A | 09.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 11.07.2025
Supplies | White wash | 1500 | 1300 | Micro | Jul | 03.07.2025 | N/A | N/A | 04.07.2025 | 08.07.2025 | 08.07.2025 | 09.07.2025 | N/A | N/A | 09.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 11.07.2025
Supplies | 100* AO plotting film paper | 45000 | 44000 | Micro | Jul | 03.07.2025 | N/A | N/A | 04.07.2025 | 08.07.2025 | 08.07.2025 | 09.07.2025 | N/A | N/A | 09.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 11.07.2025
Supplies | 100 x AO Plotting bond paper | 6000 | 5800 | Micro | Jul | 03.07.2025 | N/A | N/A | 04.07.2025 | 08.07.2025 | 08.07.2025 | 09.07.2025 | N/A | N/A | 09.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 11.07.2025
Services | Maintenance of software - microstation, ArcGIS, Autocad | 360000 | 350000 | ODB | Aug | 01.08.2025 | N/A | N/A | 01.08.2025 | 05.08.2025 | 05.08.2025 | 06.08.2025 | N/A | N/A | 06.08.2025 | N/A | N/A | 06.08.2025 | 08.08.2025 | 08.08..2025
Services | Infomate licences | 60000 | 58000 | Micro | Aug | 01.08.2025 | N/A | N/A | 01.08.2025 | 05.08.2025 | 05.08.2025 | 06.08.2025 | N/A | N/A | 06.08.2025 | N/A | N/A | 06.08.2025 | 08.08.2025 | 08.08..2025
Supplies | 100 x AO Plotting bond paper | 6000 | 5800 | Micro | Aug | 01.08.2025 | N/A | N/A | 01.08.2025 | 05.08.2025 | 05.08.2025 | 06.08.2025 | N/A | N/A | 06.08.2025 | N/A | N/A | 06.08.2025 | 08.08.2025 | 08.08..2025
Supplies | 100* AO plotting film paper | 45000 | 44000 | Micro | Aug | 08.08.2025 | N/A | N/A | 08.08.2025 | 12.08.2025 | 12.08.2025 | 13.08.2025 | N/A | N/A | 13.08.2025 | N/A | N/A | 13.08.2025 | 15.08.2025 | 15.08.2025
Services | CADASTRAL GPS service Leica, GS 16/18 and Trimble R4 & R8s | 35000 | 35000 | Micro | Sep | 05.09.2025 | N/A | N/A | 05.09.2025 | 09.09.2025 | 09.09.2025 | 10.09.2025 | N/A | N/A | 10.09.2025 | N/A | N/A | 10.09.2025 | 12.09.2025 | 12.09.2025
Supplies | CADASTRAL GPS internal batteries | 30000 | 28000 | Micro | Oct | 10.10.2025 | N/A | N/A | 10.10.2025 | 14.10.2025 | 14.10.2025 | 15.10.2025 | N/A | N/A | 15.10.2025 | N/A | N/A | 15.10.2025 | 17.10.2025 | 17.10.2025
Supplies | 100 x AO Plotting bond paper | 3000 | 2800 | Micro | Nov | 14.11.2025 | N/A | N/A | 14.11.2025 | 18.11.2025 | 18.11.2025 | 19.11.2025 | N/A | N/A | 19.11.2025 | N/A | N/A | 19.11.2025 | 21.11.2025 | 21.11.2025
Supplies | 100* AO plotting film paper | 45000 | 44000 | Micro | Nov | 31.10.2025 | N/A | N/A | 31.10.2025 | 04.11.2025 | 04.11.2025 | 05.11.2025 | N/A | N/A | 05.11.2025 | N/A | N/A | 05.11.2025 | 07.11.2025 | 07.11.2025
Services | CADASTRAL GPS service Leica, GS 16/18 and Trimble R4 & R8s | 35000 | 34000 | Micro | Dec | 28.11.2025 | N/A | N/A | 28.11.2025 | 02.12.2025 | 02.12.2025 | 03.12.2025 | N/A | N/A | 03.12.2025 | N/A | N/A | 03.12.2025 | 05.12.2025 | 05.12.2025
Services | AO plotter repair/ service | 25000 | 24000 | Micro | Dec | 28.11.2025 | N/A | N/A | 28.11.2025 | 02.12.2025 | 02.12.2025 | 03.12.2025 | N/A | N/A | 03.12.2025 | N/A | N/A | 03.12.2025 | 05.12.2025 | 05.12.2025
Supplies | 100 x AO Plotting bond paper | 3000 | 2800 | Micro | Jan | 02.01.2026 | N/A | N/A | 02.01.2026 | 06.01.2026 | 06.01.2026 | 07.01.2026 | N/A | N/A | 07.01.2026 | N/A | N/A | 07.01.2026 | 09.01.2026 | 09.01.2026
Supplies | 100* AO plotting film paper | 45000 | 44000 | Micro | Jan | 02.01.2026 | N/A | N/A | 02.01.2026 | 06.01.2026 | 06.01.2026 | 07.01.2026 | N/A | N/A | 07.01.2026 | N/A | N/A | 07.01.2026 | 09.01.2026 | 09.01.2026
Supplies | CADASTRAL GPS internal & external batteries | 30000 | 28000 | Micro | Feb | 20.02.2026 | N/A | N/A | 20.02.2026 | 24.02.2026 | 24.02.2026 | 25.02.2026 | N/A | N/A | 25.02.2026 | N/A | N/A | 25.02.2026 | 27.02.2026 | 27.02.2026
Supplies | 100 x AO Plotting bond paper | 6000 | 5800 | Micro | Feb | 18.02.2026 | N/A | N/A | 18.02.2026 | 18.02.2026 | 18.02.2026 | 18.02.2026 | N/A | N/A | 18.02.2026 | N/A | N/A | 18.02.2026 | 20.02.2026 | 20.02.2026
Supplies | 100* AO plotting film paper | 45000 | 44000 | Micro | Feb | 18.02.2026 | N/A | N/A | 18.02.2026 | 18.02.2026 | 18.02.2026 | 18.02.2026 | N/A | N/A | 18.02.2026 | N/A | N/A | 18.02.2026 | 20.02.2026 | 20.02.2026
Services | CADASTRAL GPS service Leica, GS 16/18 and Trimble R4 & R8s | 35000 | 34000 | Micro | Mar | 26.02.2026 | N/A | N/A | 26.02.2026 | 03.03.2026 | 03.03.2026 | 04.03.2026 | N/A | N/A | 04.03.2026 | N/A | N/A | 04.03.2026 | 06.03.2026 | 06.03.2026
GENERAL ADMINISTRATION
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | April | 21.04.2025 | N/A | N/A | 22.04.2025 | 23.04.2025 | 23.04.2025 | 23.04.2025 | N/A | N/A | 23.04.2025 | N/A | N/A | 23.04.2025 | 24.04.2025 | 24.04.2025
Services | Catering (Board meetings) | 2000 | 2000 | Micro | April | 21.04.2025 | N/A | N/A | 22.04.2025 | 23.04.2025 | 23.04.2025 | 23.04.2025 | N/A | N/A | 23.04.2025 | N/A | N/A | 23.04.2025 | 24.04.2025 | 24.04.2025
Services | Procurement of Civic entertainment | 7750 | 7750 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | Procurement of Domestic requisites | 29655 | 29655 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | Catering (Board meetings) | 2000 | 2000 | Micro | June | 16.06.2025 | N/A | N/A | 16.06.2025 | 18.06.2025 | 18.06.2025 | 19.06.2025 | N/A | N/A | 20.06.2025 | N/A | N/A | 20.06.2025 | 20.06.2025 | 20.06..2025
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | June | 16.06.2025 | N/A | N/A | 16.06.2025 | 18.06.2025 | 18.06.2025 | 19.06.2025 | N/A | N/A | 20.06.2025 | N/A | N/A | 20.06.2025 | 20.06.2025 | 20.06..2025
Supplies | Procurement of Civic entertainment | 7750 | 7750 | Micro | July | 03.07.2025 | N/A | N/A | 04.07.2025 | 08.07.2025 | 08.07.2025 | 09.07.2025 | N/A | N/A | 09.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 11.07.2025
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | July | 03.07.2025 | N/A | N/A | 04.07.2025 | 08.07.2025 | 08.07.2025 | 09.07.2025 | N/A | N/A | 09.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 11.07.2025
Supplies | Auction sale | 2500 | 2500 | Micro | July | 03.07.2025 | N/A | N/A | 04.07.2025 | 08.07.2025 | 08.07.2025 | 09.07.2025 | N/A | N/A | 09.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 11.07.2025
Services | Catering (Board meetings) | 2000 | 2000 | Micro | July | 03.07.2025 | N/A | N/A | 04.07.2025 | 08.07.2025 | 08.07.2025 | 09.07.2025 | N/A | N/A | 09.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 11.07.2025
Supplies | Small tools & plants | 920 | 920 | Micro | August | 08.08.2025 | N/A | N/A | 08.08.2025 | 12.08.2025 | 12.08.2025 | 13.08.2025 | N/A | N/A | 13.08.2025 | N/A | N/A | 13.08.2025 | 15.08.2025 | 15.08.2025
Supplies | Mtce of grounds & buildings | 0 | 0 | Micro | August | 08.08.2025 | N/A | N/A | 08.08.2025 | 12.08.2025 | 12.08.2025 | 13.08.2025 | N/A | N/A | 13.08.2025 | N/A | N/A | 13.08.2025 | 15.08.2025 | 15.08.2025
Services | Catering (Board meetings) | 2000 | 2000 | Micro | August | 08.08.2025 | N/A | N/A | 08.08.2025 | 12.08.2025 | 12.08.2025 | 13.08.2025 | N/A | N/A | 13.08.2025 | N/A | N/A | 13.08.2025 | 15.08.2025 | 15.08.2025
Services | Catering (Meeting, Committees & Management) | 10000 | 1660 | Micro | August | 08.08.2025 | N/A | N/A | 08.08.2025 | 12.08.2025 | 12.08.2025 | 13.08.2025 | N/A | N/A | 13.08.2025 | N/A | N/A | 13.08.2025 | 15.08.2025 | 15.08.2025
Services | Catering (Board meetings) | 2000 | 2000 | Micro | September | 04.09.2025 | N/A | N/A | 05.09.2025 | 12.09.2025 | 12.09.2025 | 15.09.2025 | N/A | N/A | 15.09.2025 | N/A | N/A | 15.09.2025 | 19.09.2025 | 19.09.2025
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | September | 04.09.2025 | N/A | N/A | 05.09.2025 | 12.09.2025 | 12.09.2025 | 15.09.2025 | N/A | N/A | 15.09.2025 | N/A | N/A | 15.09.2025 | 19.09.2025 | 19.09.2025
Supplies | Procurement of Civic entertainment | 7750 | 7750 | Micro | October | 09.10.2025 | N/A | N/A | 10.10.2025 | 13.10.2025 | 13.10.2025 | 14.10.2025 | N/A | N/A | 15.10.2025 | N/A | N/A | 15.10.2025 | 17.10.2025 | 17.10.2025
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | October | 09.10.2025 | N/A | N/A | 10.10.2025 | 13.10.2025 | 13.10.2025 | 14.10.2025 | N/A | N/A | 15.10.2025 | N/A | N/A | 15.10.2025 | 17.10.2025 | 17.10.2025
Services | Catering (Board meetings) | 2000 | 2000 | Micro | October | 09.10.2025 | N/A | N/A | 10.10.2025 | 13.10.2025 | 13.10.2025 | 14.10.2025 | N/A | N/A | 15.10.2025 | N/A | N/A | 15.10.2025 | 17.10.2025 | 17.10.2025
Supplies | Procurement of Domestic requisites | 29655 | 29655 | Micro | November | 31.10.2025 | N/A | N/A | 31.10.2025 | 04.11.2025 | 04.11.2025 | 05.11.2025 | N/A | N/A | 05.11.2025 | N/A | N/A | 05.11.2025 | 07.11.2025 | 07.11.2025
Service | Catering (Board meetings) | 2000 | 2000 | Micro | November | 31.10.2025 | N/A | N/A | 31.10.2025 | 04.11.2025 | 04.11.2025 | 05.11.2025 | N/A | N/A | 05.11.2025 | N/A | N/A | 05.11.2025 | 07.11.2025 | 07.11.2025
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | November | 31.10.2025 | N/A | N/A | 31.10.2025 | 04.11.2025 | 04.11.2025 | 05.11.2025 | N/A | N/A | 05.11.2025 | N/A | N/A | 05.11.2025 | 07.11.2025 | 07.11.2025
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | December | 28.11.2025 | N/A | N/A | 28.11.2025 | 02.12.2025 | 02.12.2025 | 03.12.2025 | N/A | N/A | 03.12.2025 | N/A | N/A | 03.12.2025 | 05.12.2025 | 05.12.2025
Service | Catering (Board meetings) | 8000 | 2000 | Micro | December | 28.11.2025 | N/A | N/A | 28.11.2025 | 02.12.2025 | 02.12.2025 | 03.12.2025 | N/A | N/A | 03.12.2025 | N/A | N/A | 03.12.2025 | 05.12.2025 | 05.12.2025
| Procurement of Civic entertainment | 7750 | 7750 | Micro | January | 02.01.2026 | N/A | N/A | 02.01.2026 | 06.01.2026 | 06.01.2026 | 07.01.2026 | N/A | N/A | 07.01.2026 | N/A | N/A | 07.01.2026 | 09.01.2026 | 09.01.2026
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | January | 02.01.2026 | N/A | N/A | 02.01.2026 | 06.01.2026 | 06.01.2026 | 07.01.2026 | N/A | N/A | 07.01.2026 | N/A | N/A | 07.01.2026 | 09.01.2026 | 09.01.2026
Services | Catering (Board meetings) | 6000 | 2000 | Micro | January | 02.01.2026 | N/A | N/A | 02.01.2026 | 06.01.2026 | 06.01.2026 | 07.01.2026 | N/A | N/A | 07.01.2026 | N/A | N/A | 07.01.2026 | 09.01.2026 | 09.01.2026
Supplies | Maintanance of buildings & grounds | 10000 | 10000 | Micro | February | 16.02.2026 | N/A | N/A | 16.02.2026 | 16.02.2026 | 16.02.2026 | 16.02.2026 | N/A | N/A | 16.02.2026 | N/A | N/A | 16.02.2026 | 18.02.2026 | 18.02.2026
Supplies | Small tools & plants | 920 | 920 | Micro | February | 16.02.2026 | N/A | N/A | 16.02.2026 | 16.02.2026 | 16.02.2026 | 16.02.2026 | N/A | N/A | 16.02.2026 | N/A | N/A | 16.02.2026 | 18.02.2026 | 18.02.2026
Services | Catering (Board meetings) | 4000 | 2000 | Micro | February | 16.02.2026 | N/A | N/A | 16.02.2026 | 16.02.2026 | 16.02.2026 | 16.02.2026 | N/A | N/A | 16.02.2026 | N/A | N/A | 16.02.2026 | 18.02.2026 | 18.02.2026
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | February | 16.02.2026 | N/A | N/A | 16.02.2026 | 16.02.2026 | 16.02.2026 | 16.02.2026 | N/A | N/A | 16.02.2026 | N/A | N/A | 16.02.2026 | 18.02.2026 | 18.02.2026
Services | Catering (Meeting, Committees & Management) | 1660 | 1660 | Micro | March | 26.02.2026 | N/A | N/A | 26.02.2026 | 03.03.2026 | 03.03.2026 | 04.03.2026 | N/A | N/A | 04.03.2026 | N/A | N/A | 04.03.2026 | 06.03.2026 | 06.03.2026
Services | Catering (Board meetings) | 2000 | 2000 | Micro | March | 26.02.2026 | N/A | N/A | 26.02.2026 | 03.03.2026 | 03.03.2026 | 04.03.2026 | N/A | N/A | 04.03.2026 | N/A | N/A | 04.03.2026 | 06.03.2026 | 06.03.2026
| PUBLIC RELATIONS | [11 empty] | N/A | N/A
Supplies | PA System (out door) | 15000 | 15000 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | Rotating lantern banner | 3500 | 3500 | Micro | June | 16.06.2025 | N/A | N/A | 16.06.2025 | 18.06.2025 | 18.06.2025 | 19.06.2025 | N/A | N/A | 20.06.2025 | N/A | N/A | 20.06.2025 | 20.06.2025 | 20.06..2025
Supplies | Cluster banner | 1000 | 1000 | Micro | Feb | 16.02.2026 | N/A | N/A | 16.02.2026 | 16.02.2026 | 16.02.2026 | 16.02.2026 | N/A | N/A | 16.02.2026 | N/A | N/A | 16.02.2026 | 18.02.2026 | 18.02.2026
Supplies | Administration of Inheritance Act | 70 | 70 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Supplies | Promotional Material | 25000 | 25000 | Micro | July | 19.05.2025 | N/A | N/A | 19.02.2025 | 21.05.2025 | 21.05.2025 | 21.05.2025 | N/A | N/A | 21.05.2025 | N/A | N/A | 22.05.2025 | 23.05.2025 | 23.05.2025
Services | DSTV Subscription | 7200 | 7200 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | Press Conference | 6000 | 6000 | Micro | May | 08.05.2025 | N/A | N/A | 09.05.2025 | 11.05.2025 | 12.05.2025 | 13.05.2025 | N/A | N/A | 14.05.2025 | N/A | N/A | 14.05.2025 | 16.05.2025 | 16.05.2025
Services | Stakeholder Workshop | 6000 | 6000 | Micro | July | 03.07.2025 | N/A | N/A | 04.07.2025 | 08.07.2025 | 08.07.2025 | 09.07.2025 | N/A | N/A | 09.07.2025 | N/A | N/A | 09.07.2025 | 11.07.2025 | 11.07.2025
Services | Stakeholder Workshop | 6000 | 6000 | Micro | October | 28.10.2025 | N/A | N/A | 28.10.2025 | 29.10.2025 | 29.10.2025 | 30.10.2025 | N/A | N/A | 30.10.2025 | N/A | N/A | 30.10.2025 | 31.10.2025 | 31.10.2025
2503940
CONTIGENCY PLAN
Services | Microsoft Dynamics GP Routine maintanance | 56000 | 55000 | Micro | 2025-06-01 | N/A
Services | Maintenance of Computers/laptops | 70000 | 68000 | Micro | 2025-12-01 | N/A
Services | Maintenance of printers & scanners | 70000 | 68000 | Micro | 2025-06-01 | N/A
Services | Maintenance of plotter | 25000 | 24000 | Micro | 2025-12-01 | N/A
Services | Major and minor repairs to be done as an when the arise | 40000 | 38000 | Micro | N/A | N/A | As an when the need arise
Tati Land Board
4724,Masunga,Botswana<br>Tel:+2672489267