## Sheet1
BOTSWANA HOUSING CORPORATION
PROCUREMENT PLAN FOR 2025/2026
Discipline | Project Description | Budget Amount | Cost Estimate (BWP) | Method of Procurement | Tender Document Vetting-completion | ITT to POU | Issuing of ITT | Tender Closing | Bid Evaluation Submission | Verification of Tender Evaluation Report | Pre-Adjudication by POU | Award Decision by AO | Cooling Off period-END | Contract Placement | Project Commencement
SERVICES | ManageEngine Endpoint Central | 400000 | 400000 | Direct Appointment | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Darktrace Mail Security | 450000 | 450000 | Direct Appointment | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Backup Revamp | 450000 | 450000 | Open Domestic | 2025-07-01 | 2025-07-03 | 2025-07-10 | 2025-08-11 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30
| DR Improvement | 150000 | 150000 | Open Domestic | 2025-07-01 | 2025-07-03 | 2025-07-10 | 2025-08-11 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30
| Alfresco Upgrade | 500000 | 500000 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Review of Organisational Structure | 1500000 | 1500000 | Direct Appointment | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| ERP Upgrade Phase 2-Payroll, HR Functionility,Dashboard | 1000000 | 1000000 | Direct Appointment | 2025-07-01 | 2025-07-03 | 2025-07-10 | 2025-08-11 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30
| Provision of Home Internet to BHC Staff | 4500000 | 4500000 | Direct Appointment | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-05 | 2026-01-20 | 2026-01-27 | 2026-02-03
| Provision of Cleaning Services for BHC Offices | 1500000 | 1500000 | Open Domestic | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-06 | 2026-01-21 | 2026-01-28 | 2026-02-03
| Provision of Document Off Site Storage | 511200 | 511200 | Open Domestic | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-07 | 2026-01-22 | 2026-01-29 | 2026-02-03
| Provision of Mobile Communication Services | 2916000 | 2916000 | Restricted Domestic | 2025-07-01 | 2025-07-03 | 2025-07-10 | 2025-08-11 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30
| Provision of Oracle EBS Support | 2000000 | 2000000 | Direct Appointment | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| PROVISION OF MICROSOFT 365 LICENSES | 3000000 | 3000000 | Direct Appointment | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-07 | 2026-01-22 | 2026-01-29 | 2026-02-03
| Provision of online Fax | 140000 | 140000 | Direct Appointment | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| PROVISION OF MIMECAST CLOUD SECURITY | 1600000 | 1600000 | Restricted Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Provision of Call Centre Services | 3000000 | 3000000 | Open Domestic | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-07 | 2026-01-22 | 2026-01-29 | 2026-02-03
| Provision of Alarm Monitoring Servivces | 400000 | 400000 | Open Domestic | 2026-01-05 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-25 | 2026-04-01 | 2026-04-08
| Provision of Skip Collection - South | 1600000 | 1600000 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Mobile App Development | 500000 | 500000 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Data Repository/Warehouse Implementation | 500000 | 500000 | Open Domestic | 2025-07-01 | 2025-07-03 | 2025-07-10 | 2025-08-11 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30
SUPPLIES | Supply of Office Furniture - North | 148900 | 148900 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Supply of Office Furniture - South | 329500 | 329500 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Supply of Office Equipment - North | 126500 | 126500 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Supply of Office Equipment - South | 133300 | 133300 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Computer Hardware | 2178000 | 2178000 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Supply of Sowa Generator | 700000 | 700000 | Open Domestic | 2025-07-01 | 2025-07-03 | 2025-07-10 | 2025-08-11 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30
| Supply of Maun Generator | 700000 | 700000 | Open Domestic | 2025-07-01 | 2025-07-03 | 2025-07-10 | 2025-08-11 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30
WORKS | Provision of Maintenance at High Density Areas | 5000000 | 5000000 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Provision of Third Party Maintenance | 6000000 | 6000000 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Letlhakane HD 72 | 63360000 | 63360000 | Open Domestic | 2025-07-01 | 2025-07-03 | 2025-07-10 | 2025-08-11 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30 | Q2
| Government Camp (52486) HD 72 | 39957949 | 39957949 | Open Domestic | 2025-07-01 | 2025-07-03 | 2025-07-10 | 2025-08-11 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30
| Maun 55 | 29800000 | 29800000 | Direct Appointment | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Tati 30 - | 17700000 | 17700000 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04 | Q1
| Block 7 48(C) | 23693426 | 23693426 | Direct Appointment | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Block 7 48(D) | 23982326 | 23982326 | Direct Appointment | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Block 7 78(com) | 54203547 | 54203547 | Direct Appointment | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Maruapula Plot 21968-40 | 36600000 | 36600000 | Open Domestic | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-05 | 2026-01-20 | 2026-01-27 | 2026-02-03 | Q3
| Gaborone - Lot 50594 New Canada -12 HD | 7800000 | 7800000 | Restricted Domestic | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-06 | 2026-01-21 | 2026-01-28 | 2026-02-03
| Sese 55 - 25/26 | 22550000 | 22550000 | Open Domestic | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-07 | 2026-01-22 | 2026-01-29 | 2026-02-03
| Mabutsane 20 | 11000000 | 11000000 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Gaborone (lot 60038 Block 7 ) TH 5 | 3625000 | 3625000 | Restricted Domestic | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-05 | 2026-01-20 | 2026-01-27 | 2026-02-03
| Gaborone (lot 5432) - TH 3 | 2175000 | 2175000 | Restricted Domestic | 2025-10-01 | 2025-10-04 | 2025-10-10 | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-06 | 2026-01-21 | 2026-01-28 | 2026-02-03
| Pilane 200 infrastructure | 63000000 | 63000000 | Restricted Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Peolwane (Block 7) infrastructure | 21200000 | 21200000 | Open Domestic | 2025-04-01 | 2025-04-03 | 2025-04-10 | 2025-05-09 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-21 | 2025-07-28 | 2025-08-04
| Gaborone - lot 2414 | 4140000 | 4140000 | Restricted Domestic | 2026-01-05 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-25 | 2026-04-01 | 2026-04-08
| Gaborone - lot 2494 | 5520000 | 5520000 | Restricted Domestic | 2026-01-05 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-25 | 2026-04-01 | 2026-04-08
| Gaborone - lot 2641 | 4140000 | 4140000 | Restricted Domestic | 2026-01-05 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-25 | 2026-04-01 | 2026-04-08
| Gaborone - lot 2645 | 4140000 | 4140000 | Restricted Domestic | 2026-01-05 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-25 | 2026-04-01 | 2026-04-08