## Sheet1
PROJECT NAME | BUDGET AMOUNT | ACTIVITY NAME | PROCUREMENT METHOD | DISCIPLINE | ESTIMATED COST | INVITATION DATE | TENDER CLOSE DATE | EVALUATION COMPLETE | SUBMISSION FOR ADJUDICATION | AWARD DECISION | PROJECT COMMENCEMENT DATE | PROJECT COMPLETION | END OF ACTIVITY REPORT
INFORMATION TECHNOLOGY DIVISION
Fortigate Firewall - Hardware | 200000 | Purchase of Group cyber security and control | Request for Quotation (RFQ) | Supplies | 200000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 18.07.2025 | 18.07.25 | 19.07.25
Biometrix Access Control Harware | 400000 | Intergrate Oracle Time and Labor for access control management | Open Tender | Supplies | 400000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 09.01.2026 | 13.01.2026
Oracle Management Cloud (OMC) including EAM (replace Maximo) | 3000000 | Cloud-Based backup and recovery solutions that serves as Off-Premise DR Site. | Open Tender | Service | 3000000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 10.01.2026 | 13.01.2026
MIS (Slaughter floor, Deboning and Warehousing) | 2000000 | System replacement - food chain | Selective Tender | Service | 2000000 | 31.10.2025 | 11.11.2025 | 21.11.2025 | 05.12.2025 | 19.12.2025 | 22.12.2025 | 22.06.2025 | 26.06.2025
ACL Robotics Enterpriise Audit Software | 640000 | Internal Audit Software | Open Tender | Service | 640000 | 31.07.2025 | 15.08.2025 | 22.08.2025 | 25.08.2025 | 08.09.2025 | 09.09.2025 | 26.09.2025 | 30.09.2025
15x Wifi AP Cisco or Sophos & x1 controller | 125000 | Upgrade WI-FI security and connectivity across the plant | Request for Quotation (RFQ) | Supplies | 125000 | 02.12.2025 | 05.12.2025 | 08.12.2025 | 09.12.2025 | 10.12.2025 | 13.10.2025 | 17.10.2025 | 20.10.2025
Cisco Network switches | 150000 | Replace obsolete Deboning and Slaughter floor for switches | Request for Quotation (RFQ) | Supplies | 150000 | 02.12.2025 | 05.12.2025 | 08.12.2025 | 09.12.2025 | 10.12.2025 | 13.10.2025 | 17.10.2025 | 20.10.2025
Replacement of IT equipment | 250000 | Purchase of Laptops and Desktops for Departments | Request for Quotation (RFQ) | Supplies | 250000 | 11.08.2025 | 14.08.2025 | 15.08.2025 | 15.08.2025 | 19.08.2025 | 20.08.2025 | 29.08.2025 | 01.09.2025
HUMAN RESOURCES DIVISION
Multi Purpose Hall/Wellness Centre | 500000 | Renovation & development of a resting place & gym, tv room, meeting space and games room. | Open Domestic Bidding | Small Works | 300 000,00 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 27.03.2026 | 31.03.2026
Office Furniture upgrade for all employees | 1500000 | All furtniture is old and there is need for replacement. | Open Domestic Bidding | Supplies | 1500000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 27.03.2026 | 31.03.2026
Guest houses | 500000 | Revamp the guest houses (Lobatse) to commerciality including licensing. | Open Domestic Bidding | Small Works | 500000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 27.03.2026 | 31.03.2026
EXECUTIVE OFFICE
Board room upgrade | 300000 | Purchase Board room chairs. | Request for quotation | Supplies | 300000 | 03.06.2025 | 06.06.2025 | 14.06.2025 | 17.06.2025 | 18.06.2025 | 19.06.2025 | 04.07.2025 | 07.07.2025
SECURITY DIVISION
Purchase and upgrade of CCTV cameras & Repair of the Plant Electric fence | 300000 | Installation of security surveilance at Slaugther, Labour Canteen, Lairages, Offal Freezers, engineering workshops and perimeter fence. | request for quotation | Supplies | 300000 | 03.06.2025 | 06.06.2025 | 14.06.2025 | 17.06.2025 | 18.06.2025 | 19.06.2025 | 23.07.2025 | 25.07.2025
PR & MARKETING DIVISION
Show furniture | 120000 | Furniture to be used during shows and events | Request for Proposal | Supplies | 120000 | 07.10.2025 | 10.10.2025 | 17.10.2025 | 20.10.2025 | 21.10.2025 | 28.10.2025 | 29.10.2025 | 31.10.2025
Refridgerated Truck (5-7 Ton) | 1500000 | Purchase of refidgerated transportation truck for BMC products to Reatil Outlets (Gabs, Ftown) | Open tender bidding | Supplies | 1500000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 29.08.2025 | 01.09.2025
Closed Forklifts | 1200000 | Purchase Forklift for warehouse operations. | Open tender bidding | Supplies | 1200000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 29.08.2025 | 01.09.2025
Lobatse Butchery Meat Processing Equipment | 100000 | Butchery processing equipment. | Request for Quotation | Supplies | 100000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 23.07.2025 | 25.07.2025
Lobatse Factory Shop Upgrade | 250000 | Installation of coldroom & window & till to reduce congestion in the factory shop. | Request for Quotation | small works | 250000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 23.07.2025 | 25.07.2025
Racking System For Holding Stores | 2000000 | Racking storage facility for cold temperatues. | Open tender bidding | Supplies | 2000000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 30.01.2026 | 02.02.2026
CIVIL WORKS DIVISION
Main Entrace Road Upgrade | 400000 | Re-surface road with 30MPa concrete slab. | Open tender bidding | Small Works | 400000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 05.01.2026 | 27.03.2026 | 31.03.2026
Water Saving at Ablutions | 260000 | Water saving sanitary ware and fittings (taps, cisterns, urinals and shower heads). | Request for Quotation (RFQ) | Supplies | 260000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 12.12.2025 | 15.12.2025
Borehole no 1 water usage for toilet flushing | 150000 | Procurement of materials to complete water reticulation for toilet flushing at ablusions. | Request for Quotation (RFQ) | Supplies | 150000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 12.12.2025 | 15.12.2025
ENGINEERING DIVISION
Laser alignment equipment | 120000 | Alignment of Equipment for ammonia compressors. | Request for Quotation (RFQ) | Supplies | 120000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 31.07.2025 | 01.08.2025
Central Engineering Software Station | 120000 | Industrial laptop and interface devices for use across all plants for troubleshooting and software storage. | Request and Quotation (RFQ) | Service | 120000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 31.07.2025 | 01.08.2025
Vacuum Packing Machine for Production - Deboning | 4500000 | Refurnish the Vacuum Packer Machine for chilled products. | Selective Tender | Supplies | 4500000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 02.07.2025
Replacement of Conveyors for Holding Stores | 2500000 | Replacement of carton conveyors at the holding store. | Selective Tender | Supplies | 2500000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 02.07.2025
POWER STATION DIVISION
Upgrade of Boiler Control Panels | 1800000 | Replacement Boilers No. 2 & No. 3 Controls. | Selective Tender | Service | 1800000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 02.07.2025
Heat Exchanger Refurbishment | 350000 | Replacement of Steam Control Valve (Flow Serve) & Heat Exchanger Plates & Gaskets. | Request for Quotation (RFQ) | Service | 350000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Induced Draft Fans (ID Fan) | 150000 | Boiler Fans Replacement (Boilers No. 2 & No. 3) | Request for Quotation (RFQ) | Service | 150000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Forced Draft fans for boilers | 100000 | Boiler Fans Replacement. (FD Fan). | Request for Quotation (RFQ) | Service | 100000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Replacement Air Compressor | 3500000 | Replacement of Clean Air Compressor- Cooper | Selective Tender | Service | 3500000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 02.07.2025
Fire fighting system | 450000 | Firefighting Resuscitation - Hydrants | Request for Quotation (RFQ) | Service | 450000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Stoker Mats for Boiler 2 & 3 | 1600000 | Replacements of Stokers for the 10T boilers. | Selective Tender | Service | 1600000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 02.07.2025
REFRIDGERATOR DIVISION
Chillers Controls Upgrade | 3500000 | Chiller PLC & SCADA Upgrade. | Selective Tender | Service | 3500000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 02.07.2025
Plate Freezers | 1200000 | Plate Freezer Upgrade & valve banks separation | Selective Tender | Service | 1200000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 02.07.2025
Upgrade of Compressors & Condenser | 1200000 | Compressor Replacement for Maun/Cannery plant. | Open public bidding | Service | 1200000 | 31.07.2025 | 15.08.2025 | 22.08.2025 | 25.08.2025 | 08.09.2025 | 09.09.2025 | 24.10.2025 | 27.10.2025
Re-cladding & Insulation | 350000 | Replacement of cladding and insulation of pipes for Ammonia Line. | Request for Quotation (RFQ) | Service | 350000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Unisub Modules | 450000 | Purchase of compressor loading automatic controls. - Ammonia Compressors | Request for Quotation (RFQ) | Service | 450000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Bulk Ammonia Facility | 180000 | Installation of 2 ammounia bulk tanks (960 kg each) one at Main Plant and one at Maun Warehouse/Cannery refrigeration plants. | Request for Quotation (RFQ) | Supplies | 180000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Data Loggers | 150000 | Replacement of dataloggers for verification of temperature trends as well as back-up for SCADA system. | Request for Quotation (RFQ) | Supplies | 150000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
LOADING BAY DIVISION
FLT Batteries+ Battery | 500000 | Replacement of flat fock lift truck batteries. | Request for Quotation (RFQ) | Supplies | 500000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
FLT Battery Chargers | 114000 | Replacement of three (3)extra chargers for FLT's. | Request for Quotation (RFQ) | Supplies | 114000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
FLT Tires | 120000 | Replacement for ten (10) sets of tires for FLT's. | Request for Quotation (RFQ) | Supplies | 120000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Incinerator Upgrade | 150000 | Installation of emmission monitors and air polution control. | Request for Quotation (RFQ) | Service | 150000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
ELECTRICAL DIVISION
Soft Starters | 500000 | Purchase of Power Modulators. | Open tender bidding | Supplies | 500000 | 31.07.2025 | 15.08.2025 | 22.08.2025 | 25.08.2025 | 08.09.2025 | 09.09.2025 | 24.10.2025 | 27.10.2025
Incomer High Voltage Meter | 120000 | Installation of incomer high voltage meter. | Request for Quotation (RFQ) | Service | 120000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Site Power Rehabilitation | 100000 | Rehabilitation of site power recticulation. | Request for Quotation (RFQ) | Service | 100000 | 07.10.2025 | 10.10.2025 | 17.10.2025 | 20.10.2025 | 21.10.2025 | 22.10.2025 | 21.11.2025 | 24.11.2025
Upgrade high voltage cabling | 600000 | Cabling Upgrade - XLPE (Cross-Linked Polyethylene). | Selective Tender | Service | 600000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 30.06.2025
Transformer protection | 400000 | Installation of transformer Power Protection. | Open tender bidding | Service | 400000 | 31.07.2025 | 15.08.2025 | 22.08.2025 | 25.08.2025 | 08.09.2025 | 09.09.2025 | 24.10.2025 | 27.10.2025
Fire Suppression system | 750000 | Purchase & installation of Fire Protection system. | Open tender bidding | Service | 750000 | 31.07.2025 | 15.08.2025 | 22.08.2025 | 25.08.2025 | 08.09.2025 | 09.09.2025 | 24.10.2025 | 27.10.2025
High voltage breaker refurbishment | 800000 | Switching Refurbishment for 13 high voltage breakers (Hawker & Sydley). | Selective Tender | Service | 800000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 30.06.2025
Power factor correction | 1200000 | Resuscitation of power factor correction | Selective Tender | Service | 1200000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 27.06.2025 | 30.06.2025
CANNERY DIVISION
Petfood Mincer | 350000 | Purchase of petfood mincer. | Request for Quotation (RFQ) | Supplies | 350000 | 11.08.2025 | 14.08.2025 | 15.08.2025 | 15.08.2025 | 19.08.2025 | 20.08.2025 | 12.09.2025 | 16.09.2025
Meat Lifter | 300000 | Purchase of petfood meat lifter equipment. | Request for Quotation (RFQ) | Supplies | 300000 | 03.06.2025 | 06.06.2025 | 14.06.2025 | 17.06.2025 | 18.06.2025 | 19.06.2025 | 18.07.2025 | 23.07.2025
White meat bins | 300000 | Pucrhase of two hundred (200) white meat binns. | Request for Quotation (RFQ) | Supplies | 300000 | 03.06.2025 | 06.06.2025 | 14.06.2025 | 17.06.2025 | 18.06.2025 | 19.06.2025 | 18.07.2025 | 23.07.2025
Spin chiller | 300000 | Purchase of spin chiller. | Request for Quotation (RFQ) | Supplies | 300000 | 03.06.2025 | 06.06.2025 | 14.06.2025 | 17.06.2025 | 18.06.2025 | 19.06.2025 | 18.07.2025 | 23.07.2025
Iso panels | 284000 | Partitioning of laundry and spin chiller area. | Request for Quotation (RFQ) | Service | 284000 | 08.12.2025 | 12.12.2025 | 15.12.2025 | 17.12.2025 | 19.12.2025 | 20.06.2025 | 25.06.2025 | 26.06.2025
Steam Regulators | 200000 | Purchase three (3) steam regulators. | Request for Quotation (RFQ) | Supplies | 200000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 23.07.2025 | 25.07.2025
Weighing scale at main plant | 150000 | Purchase of one (1) weighing scale. | Request for Quotation (RFQ) | Supplies | 150000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 23.07.2025 | 25.07.2025
Retort refurbishment | 141000 | Refurbishment of relief valves, Steam Traps for retorts. | Request for Quotation (RFQ) | Service | 141000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 23.07.2025 | 25.07.2025
Ingredients agitator | 100000 | Development of ingridient mix for both corned beef & petfood. | Request for Quotation (RFQ) | Service | 100000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 23.07.2025 | 25.07.2025
Stand-by genset for cannery | 1500000 | Purchase Standby genset and swith-over for cannery. | Open tender bidding | Supplies | 1500000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 30.01.2026 | 02.02.2026
BY-PRODUCTS DIVISION
Fork lift (3 -tonne) Electrical | 500000 | Purchase of three tonne electrical forklift. | Selective Tender | Supplies | 500000 | 31.10.2025 | 11.11.2025 | 21.11.2025 | 05.12.2025 | 19.12.2025 | 22.12.2025 | 27.03.2026 | 30.03.2026
Reprocessing Plant | 250000 | Purchase of Independent reprossesing unit (Beam, Dozing Equip, Hoist,Scale) | Request for Quotation (RFQ) | Supplies | 250000 | 25.11.2025 | 28.11.2025 | 01.12.2025 | 03.12.2025 | 05.12.2025 | 08.12.2025 | 11.12.2025 | 15.12.2025
HYGIENE DIVISION
Laundry Washer | 1200000 | To replace one (1) commission washer | Open tender bidding | Supplies | 1200000 | 31.07.2025 | 15.08.2025 | 22.08.2025 | 25.08.2025 | 08.09.2025 | 09.09.2025 | 26.09.2025 | 29.09.2025
Laundry Dryer | 1200000 | To replace (1) commission driers | Open tender bidding | Supplies | 1200000 | 31.07.2025 | 15.08.2025 | 22.08.2025 | 25.08.2025 | 08.09.2025 | 09.09.2025 | 26.09.2025 | 29.09.2025
Drain Jetter/Unclogger | 400000 | High pressure clearing of blockages due to clogs and spills. | Request for Quotation (RFQ) | Service | 300000 | 25.11.2025 | 28.11.2025 | 01.12.2025 | 03.12.2025 | 05.12.2025 | 08.12.2025 | 12.12.2025 | 15.12.2025
SLAUGHTER HALL DIVISION
De-Hider Knives | 125000 | Purchase of five (5) DE-Hider (Airknives) Knives. | Request for Quotation (RFQ) | Supplies | 125000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 31.07.2025 | 01.08.2025
Stainless steel hides pallets | 300000 | Purchase of ten (10) stainless steel hides pallets. | Request for Quotation (RFQ) | Supplies | 300000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 31.07.2025 | 01.08.2025
Hydraulic Head Splitter | 400000 | Replacement of hydraulic Head Splitter. | Request for Quotation (RFQ) | Supplies | 300000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 31.07.2025 | 01.08.2025
Carcass Splitting Saw | 140000 | Purchase of two (2) smaller carcass splitting saw. | Request for Quotation (RFQ) | Supplies | 140000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 31.07.2025 | 01.08.2025
DEBONING DIVISION
Skinning/Denuiding machine | 200000 | Purchase of three (3) skinning machines / denuiding. | Request for Quotation (RFQ) | Supplies | 200000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 15.08.2025 | 18.08.2025
Bone Trimming Machines | 160000 | Replacement of four (4) bone trimming machines | Request for Quotation (RFQ) | Supplies | 160000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 15.08.2025 | 18.08.2025
Shrink wrapping Machine | 1200000 | To replace the old shrink wrapping machine. | Selective Tender | Supplies | 1200000 | 2025-05-01 | 16.05.2025 | 23.05.2025 | 26.05.2025 | 27.05.2025 | 28.05.2025 | 29.08.2025 | 01.09.2025
COMPLIANCE DIVISION
Full automatic seam monitor | 500000 | Double seam monitoring during production | Open tender bidding | Supplies | 500000 | 31.07.2025 | 15.08.2025 | 22.08.2025 | 25.08.2025 | 08.09.2025 | 09.09.2025 | 28.11.2025 | 01.12.2025
LABORATORY DIVISION
Idexx Quantity -Tray Seal Plus | 120000 | Replacement of IDEXXQuantity-tray seal plus. | Request for Quotation (RFQ) | Supplies | 120000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Incubator | 110000 | Replacement of 30 degrees celcius incubator. | Request for Quotation (RFQ) | Supplies | 110000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Purchase Laboratory Fridges | 280000 | Replacement of two (2) Fridges for controlled environment in laboratory operations. | Request for Quotation (RFQ) | Supplies | 280000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
Fat Extraction Unit (SOXTEC) | 800000 | Replacement of fat analysis & extraction unit. | Selective Tender | Supplies | 800000 | 31.07.2025 | 15.08.2025 | 22.08.2025 | 25.08.2025 | 08.09.2025 | 09.09.2025 | 28.11.2025 | 01.12.2025
Digestion Block | 210000 | Replacement of digestion block. | Request for Quotation (RFQ) | Supplies | 210000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 16.07.2025 | 29.08.2025 | 01.09.2025
SAFETY & HEALTH ENVIRONMENT (SHE) DIVISION
Upgrade Fire detection system & additional fire safety units for Lobatse (Fresh Meat, Cannery Effluent) and Francistown Plants. | 650000 | Purchase of fire detection equipment. | Open tender bidding | Supplies | 650000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 30.01.2026 | 02.02.2026
LIVESTOCK PROCUREMENT DIVISION
Orapa Feedlot Facility Development | 500000 | Materials & fitting for feedlot facility in Orapa | Open tender bidding | Service | 500000 | 31.10.2025 | 14.11.2025 | 21.11.2025 | 24.11.2025 | 08.12.2025 | 09.12.2025 | 27.03.2025 | 30.03.2025
Live scale | 150000 | Puchase of live animal scale | Request for Quotation (RFQ) | Supplies | 150000 | 31.06.2025 | 07.07.2025 | 11.07.2025 | 13.07.2025 | 15.07.2025 | 09.12.2025 | 30.01.2026 | 02.02.2026
Botswana Meat Commission
Private Bag 4,Lobatse,Botswana<br>Tel:+2675340000
Note on A31: topo kgakge:
Note on A48: Kelebogile nhlabano: to confirm