## Works (hidden)
PROCUREMENT PLAN
1 | General | Fill gray cells only!
Country/Organisation:
Project/Programme Description
Project/Programme SAP Identification #
Loan #:
Executing Agency:
Approval Date of Procurement Plan:
Date of General Procurement Notice:
Advance Contracting
Period Covered by these Proc. Plans:
| Prior Review Threshold: | Procurement decisions subject to Prior Review by the Bank as
stated in Annex B5 of the Appraisal Report
2. WORKS
2 | Works (see Note 1)
Prior review
| Procurement Method | Threshold |  |  |  | Comments
(UA$equiv.)
3 | Procurement Packages with Methods and Time Schedule | Basic Data | [11 empty] | Bid Documents |  | Pre-Qualification |  | Pre-Qualification |  | Bidding Period |  | Bid Evaluation |  | Draft Contract |  | Contract Award |  |  | Contract Implementation
| Description* | Lot Number | SPN/IFP Received | SPN/IFP No-Objection Date | SPN/IFP Publication Date (UNDB) | Estimated Amount in Currcy (000) | Lumpsum or Unit Rate | Procurement Method | Pre-Qualification (Y/N) | Dom/Reg. Preference (Y/N) | Prior or Post Review | Bid Closing Date | Plan/ Revised/ Actual | Bid Documents Received | No- Objection Date | PQ Doc Issued | Closing Date | Evaluation Report Received | No- Objection Date | Bid Invitation Date | Bid Closing-Opening | Bid Evaluation Report Received | No- Objection Date | Draft Contract Received | No- Objection Date | Contract Amount in UA(000) | Date Contract Award | Date Contract Signature | Start Date | End Date
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
| Total Cost | [7 empty] | 0 |  |  |  | Plan | [12 empty] | #REF!
[9 empty] | 0 |  |  |  | Revised
[9 empty] | 0 |  |  |  | Actual | [12 empty] | 0
Note 1. (Supplementary information concerning Procurement of Works, such as Pre-qualification or any other Special Procurement Arrangement)
Page 1/X

## Consultants
PROCUREMENT PLAN
1 | General
| Country/Organisation: | BOTSWANA GOVERNMENT
| Project/Programme Description | BOTSWANA RENEWABLE ENERGY SUPPORT PROJECT
| Project/Programme SAP Identification # | P-BW-FA0-002
| Grant #: | 5590155000101
| Executing Agency: | BOTSWANA REGULATORY AUTHORITY (BERA)
| Approval Date of Procurement Plan: | 22 February 2024
| Date of General Procurement Notice: | 21 February 2022
| Advance Contracting | N/A
| Period Covered by these Proc. Plans: | 19 July 2023 to 31 December 2024
| Procurement Plan Updated date: | 16 February 2024
| Prior Review Threshold: | Procurement decisions subject to Prior Review by the Bank as
stated in the Appraisal Report
2 | Consultants
Prior review
| Selectiont Method |  |  | Threshold | Comments
(USD)
| 1. QCBS and LCS |  | Above | 100000 | All contracts will be prior reviewed
| 2. QCBS and LCS |  | Below | 100000 | Three first contracts
| 3. Individual Consultants |  | Above | 50000 | All contracts will be prior reviewed
| 4. Individual Consultants |  | Below | 50000 | First Three contracts
| 5. Single Source Selection and Direct Contracting |  | - | - | All contracts
3 | Procurement Packages with Methods and Time Schedule | Basic Data | [7 empty] | Request for Expression of Interest |  | Terms of Reference |  | Short List |  | Request for Proposal |  | Proposal Period |  | Bid Evaluation Technical (T) & Financial (F) |  |  |  |  | Draft Contract |  |  | Contract Award |  |  |  | Contract Implementation
| Description* | Date EOI Received | Date No-Objection | Selection Method | Lumpsum or Time-Based | Estimated Amount in USD | Prior/Post Review | Bid Closing Date | Plan/ Revised/ Actual | Date Published | Closing Date | Date Received | Date No-Objection | Date Received | Date No-Objection | Date Received | Date No-Objection | Issuance Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Evaluation Report (T & F) | No-objection Evaluation Report (T & F) | Draft Contract Received | Draft Contract Amount in USD | Date No-Objection | Final Contract Received | Contract Amount in USD | Contract Award Date | Contract Signature | Start Date | End Date
1 | Consultancy service for Operationalization of policy and regulatory framework for IRP implementation / Development of regulatory instruments and technical studies to support IPP facilitation roll out: Grid Code, Electricity Cost of Service Studies; and Licensing Frameworks | 2022-01-24 | 2022-01-26 | QCBS | Lumpsum | 985000 | Prior | 6-May-22 | Plan | 2022-01-21 | 2022-02-14 | 2022-01-21 | 2022-01-23 | 24-Feb-22 | 2022-02-28 | 10-03-22 | 13-03-22 | 2022-03-15 | 6-May-22 | 13-May-22 | 16-May-22 | 2022-05-20 |  |  | 2022-05-22 | 985000 | 27-May-22 | 27-May-22 | 985000 | 27-May-22 | 01-June-22 | 01-June-22 | 2022-12-18
1 |  | 2022-02-18 | 2022-02-20 | QCBS | Lumpsum | 985000 | Prior | 2022-05-14 | Revised | 2022-02-23 | 2022-03-09 | 2022-02-28 | 2022-03-07 | 2022-03-24 | 2022-04-08 | 2022-03-24 | 2022-04-08 | 2022-04-10 | 2022-05-19 | 2022-06-09 | 2022-06-16 | 2022-06-21 |  |  | 2022-07-06 | 985000 | 2022-07-13 | 2022-07-16 | 985000 | 2022-07-16 | 2022-07-21 | 2022-07-21 | 2024-05-31
|  | 2022-02-15 | 2022-02-24 | QCBS | Lumpsum | 403000 | Post Review | 2022-03-14 | Revised | 2022-02-25 | 2022-03-14 | 2022-02-15 | 2022-02-24 | 2022-04-27 | 2022-07-29 | 2022-04-27 | 2022-07-29 | 2022-07-29 | 2022-09-19 | 2022-10-12 | 2022-10-21 | 2022-11-08 | 2022-12-15 | 2022-12-29 | 2022-12-14 | 403000 | 2022-12-29 | 2023-04-21 | 403000 | 2023-03-22 | 2023-03-28 | 2023-04-14
|  | N/A | N/A | QCBS | Lumpsum | 130000 | Post Review | N/A | Revised | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 533800 | 2024-02-14 | 2024-02-19 | 533800 | N/A | 2024-02-19 | 2024-02-29 | 2024-12-15
2 | Consultancy Service for Procurement & Financial Audit of the entire Project | 2022-11-10 | 2022-11-12 | LCS | Lumpsum | 15000 | Prior | 2023-01-19 | Plan | 2022-11-15 | 2022-11-29 | 2022-11-15 | 2022-11-22 | 2022-12-14 | N/A | 2022-12-14 | N/A | 2022-12-16 | 2023-01-24 | 2023-02-14 | N/A | 2023-02-19 |  |  | 2023-03-06 | 15000 | 2023-03-13 | 2023-03-16 | 15000 | 2023-03-16 | 2023-03-21 | 2023-03-21 | 2023-06-19
|  | 2024-01-18 | 2024-01-20 | LCS | Lumpsum | 15000 | Prior | 2024-03-28 | Revised | 2024-01-23 | 2024-02-06 | 2024-01-23 | 2024-01-30 | 2024-02-21 | N/A | 2024-02-21 | N/A | 2024-02-23 | 2024-04-02 | 2024-04-23 | N/A | 2024-04-28 |  |  | 2024-05-13 | 15000 | 2024-05-20 | 2024-05-23 | 15000 | 2024-05-23 | 2024-05-28 | 2024-05-28 | 2024-08-26
Actual
3 | Consultancy Service for Electricity Sector Industry Reform Strategy | 2024-02-09 | 2024-02-16 | QCBS | Lumpsum | 452000 | Prior | 2024-05-22 | Plan | 2024-02-15 | 2024-03-08 | 2024-02-15 | 2024-02-23 | 2024-03-29 | 2024-04-15 | 2024-03-29 | 2024-04-15 | 2024-04-18 | 2024-05-31 | 2024-06-21 | 2024-07-01 | 2024-07-09 | 2024-08-16 | 2024-08-30 | 2024-08-15 |  | 2024-09-09 | 2024-09-13 |  | 2024-09-17 | 2024-09-23 | 2024-09-30 | 2025-06-30
Note 1. Details will be provided during implementation.
1000000
Formulas:
Basic Data = [Request for Expression of Interest]-5
Date No-Objection = +[Basic Data]+2
Date No-Objection = [Terms of Reference]+7
Bid Closing Date = [Proposal Period]+34
Closing Date = +[Request for Expression of Interest]+14
Short List = [Closing Date]+15
Request for Proposal = [Short List]
Proposal Period = +[Date No-Objection]+2
Proposal Period = +[Request for Proposal]+2
Submission/ Opening Date = [Bid Closing Date]+5
Submission Evaluation Report (T) = [Submission/ Opening Date]+21
No-objection Evaluation Report (T) = +[Submission Evaluation Report (T)]+7
No-objection Evaluation Report (T) = [Submission Evaluation Report (T)]+10
Opening Financial Proposals = +[No-objection Evaluation Report (T)]+5
Opening Financial Proposals = +[Submission Evaluation Report (T)]+5
Draft Contract = [Opening Financial Proposals]+15
Draft Contract = [Submission Evaluation Report (T & F)]-1
Contract Award = [Date No-Objection]+3
Contract Award Date = [Contract Award]
Contract Award Date = [Contract Award]+4
Contract Signature = [Contract Award Date]+5
Contract Signature = [Contract Award]
Contract Implementation = [Contract Signature]
Contract Implementation = [Contract Signature]+10
Request for Expression of Interest = [Terms of Reference]
End Date = [Contract Implementation]+90

## Consultants Web Template
PROCUREMENT PLAN
1 | General | Fill gray cells only!
| Country/Organisation: | BOTSWANA GOVERNMENT
| Project/Programme Description | BOTSWANA RENEWABLE ENERGY SUPPORT PROJECT
| Project/Programme SAP Identification # | P-BW-FA0-002
| Grant #: | 5590155000101
| Executing Agency: | BOTSWANA REGULATORY AUTHORITY (BERA)
| Approval Date of Procurement Plan: | 22 February 2024
| Date of General Procurement Notice: | 21 February 2022
| Advance Contracting | N/A
| Period Covered by these Proc. Plans: | 19 July 2023 to 31 December 2024
| Prior Review Threshold: | Procurement decisions subject to Prior Review by the Bank as
stated in Annex B5 of the Appraisal Report
3. CONSULTANTS
2 | Consultants (see Note 1)
| Selectiont Method | Prior Review Threshold in UA |  |  | Comments
| 1. QCBS and LCS | 100000 |  |  | All contracts will be prior reviewed
| 2. QCBS and LCS | 100000 |  |  | Three first contracts
| 3. Individual Consultants | 50000 |  |  | All contracts will be prior reviewed
| 4. Individual Consultants | 50000 |  |  | First Three contracts
| 5. Single Source Selection and Direct Contracting | -
3 | Procurement Packages with Methods and Time Schedule | Basic Data
| Description* | Date EOI Received | Date No-Objection | Selection Method | Lumpsum or Time-Based | Estimated Amount in Currcy (000) | Prior/Post Review | Bid Closing Date | Plan/ Revised/ Actual
| Consultancy service for Operationalization of policy and regulatory framework for IRP implementation / Development of regulatory instruments and technical studies to support IPP facilitation roll out: Grid Code, Electricity Cost of Service Studies; and Licensing Frameworks | 2022-01-24 | 2022-01-26 | QCBS | Lumpsum | 985000 | Prior | 6-May-22 | Plan
|  | 2022-02-18 | 2022-02-20 | QCBS | Lumpsum | 985000 | Prior | 2022-05-14 | Revised
Actual
| Consultancy Service for Procurement & Financial Audit of the entire Project | 2022-11-10 | 2022-11-12 | LCS | Lumpsum | 15000 | Prior | 2023-01-19 | Plan
|  | 2024-01-18 | 2024-01-20 | LCS | Lumpsum | 15000 | Prior | 2024-03-28 | Revised
Actual
| Consultancy Service for Electricity Sector Industry Reform Strategy | 2024-02-09 | 2024-02-16 | QCBS | Lumpsum | 452000 | Prior | 2024-05-22 | Plan
Revised
Actual
| Total Cost |  |  |  |  | 1000000 |  |  | Plan
[6 empty] | 1000000 |  |  | Revised
[6 empty] | 0 |  |  | Actual
Note 1. (Supplementary information concerning Procurement of Consultants, or any other Special Procurement Arrangement)
Page 1/X
Formulas:
Date No-Objection = [Prior Review Threshold in UA]+2