## Good & Works
Detailed Procurement Plan - Procurement of Goods & Works
Country / Executing Agency |  |  | Namibia -Ministry of Works and Transport (MoWT)
Name of Project/Program |  |  | Transport Infrastructure Improvement Project -II (TIIP-II)
Loan No. |  |  | 2000200006203
X6:AC46
Basic Data | [12 empty] | Bidding Document |  | Bidding Period |  | Bid Evaluation *++ |  | Contract Finalization
Procurement System* | Package No. | Package Descritption | Lot No.+ | Lot Description+ | Issue No. Invitation for Bids | Lump Sum or Bill of Quantities | Estimated Cost UA | Estimated Cost ZAR (Million) | Procurement Method | Pre-or-Post Qualification | Oversight Audit Prior-or-Post Review*** | Plan Revised Actual*+ | Date Submitted | Date No Objection | Date Bid Invitation (SPN) | Date Bid Closing/ Opening | Date Bid Evaluation Report Submitted | Date No-Objection | Date Contract Award | Contract Amount (NAD)*+++ | Date Contract Signature | Date Contract Completion
BPM | PG1 | Supply of 48kg/m Rails and Turnouts (Section 1: Kranzberg - Otjiwarongo) | Lot 1 | 25000ton | MWT/DRIM/ TIIP2024/ OCBI-01/2024 | BOQ | 49521922.975 | 1300000 | OCBI | Post | Prior | Plan | 2024-01-12 | 2024-01-26 | 2024-02-02 | 2024-04-26 | 2024-05-24 | 2024-06-07 | 2024-06-21 |  | 2024-06-28 | 2026-11-06
[12 empty] | Revised | 2024-01-31 | 2024-02-02 | 2024-02-09 | 2024-05-03 | 2024-05-31 | 2024-06-14 | 2024-06-28 |  | 2024-07-05 | 2026-11-13
[12 empty] | Actual | 2024-02-02 | 2024-02-06 | 2024-02-09 | 2024-05-03
BPM | PG1 | Supply of 48kg/m Rails and Turnouts (Section 2 and Section 3: Otjiwarongo - Tsumeb & Otavi - Grootfontein) | Lot 2 | 35000ton |  | BOQ | 69330692.165 | 1820000 | OCBI | Post | Prior | Plan | 2025-05-25 | 2025-06-08 | 2025-06-15 | 2025-09-07 | 2025-10-05 | 2025-10-19 | 2025-11-02 |  | 2025-11-16 | 2028-04-02
Revised
Actual
BPM | PW1 | Earthworks Section1 | Lot 1 | Km 0 - Km 50 |  | BOQ | 11809073.94 | 310000 | OCBN | Post | Prior | Plan | 2024-01-16 | 2024-01-23 | 2024-01-30 | 2024-04-23 | 2024-05-14 | 2024-05-28 | 2024-07-02 |  | 2024-07-16 | 2026-07-16
[12 empty] | Revised | 2024-03-08 | 2024-03-15 | 2024-03-22 | 2024-06-14 | 2024-07-05 | 2024-07-19 | 2024-08-23 |  | 2024-09-06 | 2026-09-06
Actual
BPM | PW2 | Earthworks Section 2 | Lot 2 | Km 50 - Km 100 |  | BOQ | 11809073.94 | 310000 | OCBN | Post | Prior | Plan | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-12-10 | 2025-02-04 | 2025-02-18 | 2025-03-18 |  | 2025-04-01 | 2027-04-01
Revised
Actual
BPM | PW1 | Earthworks Section3 | Lot 3 | Km 100 - Km 150 |  | BOQ | 14094701.15 | 370000 | OCBN | Post | Prior | Plan | 2024-01-16 | 2024-01-23 | 2024-01-30 | 2024-04-23 | 2024-05-14 | 2024-05-28 | 2024-07-02 |  | 2024-07-16 | 2026-07-16
[12 empty] | Revised | 2024-03-08 | 2024-03-15 | 2024-03-22 | 2024-06-14 | 2024-07-05 | 2024-07-19 | 2024-08-23 |  | 2024-09-06 | 2026-09-06
Actual
BPM | PW2 | Earthworks Section4 | Lot 4 | Km 150 - Km 200 |  | BOQ | 12570949.68 | 330000 | OCBN | Post | Prior | Plan | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-12-10 | 2025-02-04 | 2025-02-18 | 2025-03-18 |  | 2025-04-01 | 2027-04-01
Revised
Actual
BPM | PW3 | Permanent Work Section 1 | Lot 1 | Km 0 - Km 100 |  | BOQ | 20189707.06 | 530000 | OCBI | Post | Prior | Plan | 2025-05-25 | 2025-06-01 | 2025-09-14 | 2025-12-07 | 2026-01-04 | 2026-01-18 | 2026-02-15 |  | 2026-03-01 | 2028-02-29
Revised
Actual
BPM | PW3 | Permanent Work Section 2 | Lot 2 | Km 100 - Km 200 |  | BOQ | 22094396.4 | 580000 | OCBI | Post | Prior | Plan | 2025-07-25 | 2025-08-01 | 2025-11-14 | 2026-02-06 | 2026-03-06 | 2026-03-20 | 2026-04-17 |  | 2026-05-01 | 2028-04-30
Revised
Actual
BPM | PW4 | Bridges | Lot 1 | 1 - 6 |  | BOQ | 3047502.95 | 80000 | OCBN | Post | Prior | Plan | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-05-16 | 2025-06-13 | 2025-06-27 | 2025-07-25 |  | 2025-08-08 | 2027-02-06
Revised
Actual
BPM | PW4 | Bridges | Lot 2 | 7 - 12 |  | BOQ | 1904689.35 | 50000 | OCBN | Post | Prior | Plan | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-07-16 | 2025-08-13 | 2025-08-27 | 2025-09-24 |  | 2025-10-08 | 2027-04-08
Revised
Actual
BPM | PW4 | Bridges | Lot 3 | 13 - 16 |  | BOQ | 2857034.02 | 75000 | OCBN | Post | Prior | Plan | 2025-09-13 | 2025-09-20 | 2025-09-27 | 2025-11-15 | 2025-12-13 | 2025-12-27 | 2026-01-24 |  | 2026-02-07 | 2027-08-08
Revised
Actual
BPM | PW5 | Infrastructure Upgrades - TransNamib Windhoek Locomotive Workshop and Gamam Training Centre | n/a |  |  | BOQ | 1333.283 | 35000 | OCBN | Post | Prior | Plan | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-05-09 | 2025-06-13 | 2025-06-27 | 2025-07-25 |  | 2025-08-08 | 2026-04-25
Revised
Actual
BPM | PC 10 | Train Signalisation Upgrade | n/a |  |  | BOQ | 11428136.07 | 300000 | OCBN | Post | Prior | Plan | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-04-02 | 2026-05-07 | 2026-05-21 | 2026-06-18 |  | 2026-07-02 | 2027-03-19
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Total Cost | [6 empty] | 230659212.983 | 6090000 |  |  |  | Plan
Revised
Actual
* | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
+ | If applicable
** | Total cost of the package or lot or procurement transaction in UA from the PAR
*** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
*+ | Retain procurement "Plan" agreed at negotiations and approved by the Boards throughout the project duration
"Revised" includes all updates and revisions
Record the "Actual" date of completion of the activity
*++ | The template is to be adapted in case of two stage bidding by adding columns for the second stage bidding period and evaluation process
*+++ | Indicate currency of the contract
[7 empty] | 230659213.283 | 6090000
[7 empty] | 0.3 | 0
Formulas:
Bidding Document = [Date No Objection]-14
Date No Objection = [Bidding Period]-7
Date No Objection = [Bidding Document]+14
Bidding Period = [Date Bid Closing/ Opening]-(12*7)
Bidding Period = [Date No Objection]+7
Date Bid Closing/ Opening = [Bid Evaluation *++]-28
Date Bid Closing/ Opening = [Bidding Period]+(12*7)
Date No-Objection = [Bid Evaluation *++]+14
Contract Finalization = [Date No-Objection]+14
Date Contract Signature = [Contract Finalization]+7
Date Contract Completion = [Contract Finalization]+(124*7)
Date Contract Completion = [Date Contract Signature]+(124*7)
Bid Evaluation *++ = [Date Bid Closing/ Opening]+28

## Consulting Services
Detailed Procurement Plan - Procurement of Consulting Services
| Country / Executing Agency |  | Namibia- Ministry of Works and Transport (MoWT)
| Name of Project/Program |  | Transprot Infrastructure Inprovement Project - II (TIIP - II)
| Loan No. |  | 2000200006203
| Basic Data | [7 empty] | REOI |  | Terms of Reference |  | Short List |  |  | Request for Proposals (RFP) |  |  |  | Evaluation of Proposals | [5 empty] | Contract Finalization
| Procurement System* | Description | Selection Method | Lumpsum or Time-Based | Estimated Cost UA** | Estimated Cost ZAR (Million) | Oversight Audit Prior- or-Post Review*** | Plan Revised Actual*+ | Date Published | Date Closing | Date Submitted | Date No-Objection | Date Submitted | Date Approved | Plan Revised Actual | Date RFP Documents Submitted | Date No-Objection | Date RFPs Issued | Date Proposals Closing - Opening | Date Technical Report Submitted | Date No-Objection | Date Opening Financial Proposals | Date Combined Report Submitted | Date No-Objection | Plan Revised Actual | Date Contract Award | Contract Amount Currency*++ | Date Contract Signature | Date Contract Completion | months | 30.4167
2024.4 | BPM | Detail Design for Otavi - Grootfontein | QCBS | Lump Sum | 476.172 | 13.44 | Prior | Plan | 2024-06-11 | 2024-06-25 | 2024-05-21 | 2024-06-04 | 2024-07-09 | 2024-07-23 | Plan | 2024-08-06 | 2024-08-20 | 2024-08-27 | 2024-10-01 | 2024-10-29 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-10 | Plan | 2024-12-17 |  | 2024-12-24 | 2026-01-23 04:48
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 13
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2024.5 | BPM | Transaction advisory Services for PPP -Trans-Zambezi Railway Extension | QCBS | Lump Sum | 1142.814 | 32.25 | Prior | Plan | 2024-07-02 | 2024-07-16 | 2024-06-11 | 2024-06-25 | 2024-07-23 | 2024-08-06 | Plan | 2024-08-20 | 2024-09-03 | 2024-09-10 | 2024-10-15 | 2024-11-12 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-24 | Plan | 2024-12-31 |  | 2025-01-07 | 2025-10-07 14:24
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 9
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2025.7 | BPM | Project Financial Audits | LCS | Lump Sum | 30.475 | 0.86 | Prior | Plan | 2024-08-01 | 2024-08-15 | 2024-07-23 | 2024-07-30 | 2024-08-29 | 2024-09-12 | Plan | 2024-09-19 | 2024-10-03 | 2024-10-10 | 2024-11-21 | 2024-12-19 | 2025-01-02 | 2025-01-09 | 2025-01-16 | 2025-01-30 | Plan | 2025-02-06 |  | 2025-02-13 | 2028-02-12 09:36 | 36
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2025.4 | BPM | Technical Audits | CQS | Lump Sum | 190.469 | 5.38 | Prior | Plan | 2025-06-18 | 2025-07-02 | 2025-05-28 | 2025-06-11 | 2025-07-16 | 2025-07-30 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2025-08-13 |  | 2025-08-20 | 2028-08-18 09:36 | 36
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2024.8 | BPM | Environmental Audits | CQS | Lump Sum | 22.856 | 0.65 | Prior | Plan | 2024-09-30 | 2024-10-14 | 2024-09-09 | 2024-09-23 | 2024-10-28 | 2024-11-11 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2024-11-25 |  | 2024-12-02 | 2027-12-01 09:36 | 36
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2025.2 | BPM | Sensitisation on GBV, HIV/AIDS and wellsness services, monitoring the GRM and Gender Audit | CQS | Lump Sum | 285.703 | 8.06 | Prior | Plan | 2025-04-16 | 2025-04-30 | 2025-03-26 | 2025-04-09 | 2025-05-14 | 2025-05-28 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2025-06-11 |  | 2025-06-18 | 2028-06-16 09:36
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 36
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2026.1 | BPM | Training and/or retooling youth in railway operations (Targetting youth and woman) | QCBS | Lump Sum | 571.407 | 16.13 | Prior | Plan | 2026-05-14 | 2026-05-28 | 2026-04-23 | 2026-05-07 | 2026-06-11 | 2026-06-25 | Plan | 2026-07-09 | 2026-07-23 | 2026-07-30 | 2026-09-03 | 2026-10-01 | 2026-10-15 | 2026-10-22 | 2026-10-29 | 2026-11-12 | Plan | 2026-11-19 |  | 2026-11-26 | 2027-11-25 19:12 | 12
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2025.1 | BPM | Development of Namibia Railway Qualifications Framework | CQS | Lump Sum | 19.047 | 0.54 | Post | Plan | 2025-03-14 | 2025-03-28 | 2025-02-21 | 2025-03-07 | 2025-04-11 | 2025-04-25 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2025-05-09 |  | 2025-05-16 | 2026-03-16
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 10
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2025.6 | BPM | Skills and Capacity Development for TransNamib | QCBS | Lump Sum | 476.172 | 13.44 | Prior | Plan | 2025-10-01 | 2025-10-15 | 2025-09-10 | 2025-09-24 | 2025-10-29 | 2025-11-12 | Plan | 2025-11-26 | 2025-12-10 | 2025-12-17 | 2026-01-21 | 2026-02-18 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-04-01 | Plan | 2026-04-08 |  | 2026-04-15 | 2027-04-14 19:12
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 12
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2024.3 | BPM | TA - Cross Cutting support to MoWT | IC | Lump Sum | 228.563 | 6.45 | Prior | Plan | 2024-06-04 | 2024-06-18 | 2024-05-14 | 2024-05-28 | 2024-07-02 | 2024-07-16 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2024-07-30 |  | 2024-08-06 | 2028-08-04 04:48
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 48
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2024.1 | BPM | TA - Project Management support to MoWT | IC | Lump Sum | 228.563 | 6.45 | Prior | Plan | 2024-05-07 | 2024-05-21 | 2024-04-16 | 2024-04-30 | 2024-06-04 | 2024-06-18 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2024-07-02 |  | 2024-07-09 | 2028-07-07 04:48
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 48
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2024.2 | BPM | TA - Procurement Specialist | IC | Lump Sum | 152.375 | 4.3 | Prior | Plan | 2024-05-09 | 2024-05-23 | 2024-04-18 | 2024-05-02 | 2024-06-06 | 2024-06-20 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2024-07-04 |  | 2024-07-11 | 2028-07-09 04:48
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 48
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2024.6 | BPM | TA - Project Accountant | IC | Lump Sum | 190.469 | 5.38 | Prior | Plan | 2024-07-09 | 2024-07-23 | 2024-06-18 | 2024-07-02 | 2024-08-06 | 2024-08-20 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2024-09-03 |  | 2024-09-10 | 2028-09-08 04:48
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 48
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2027.1 | BPM | Feasibility and Detailed Design for Windhoek-Gobabis-Botswana Border Railway Line | QCBS | Lump Sum | 761.876 | 21.5 | Prior | Plan | 2027-03-14 | 2027-03-28 | 2027-02-21 | 2027-03-07 | 2027-04-11 | 2027-04-25 | Plan | 2027-05-09 | 2027-05-23 | 2027-05-30 | 2027-07-04 | 2027-08-01 | 2027-08-15 | 2027-08-22 | 2027-08-29 | 2027-09-12 | Plan | 2027-09-19 |  | 2027-09-26 | 2028-09-24 19:12
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 12
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2026.2 | BPM | Corridor Diagnostics and Transaction Advisory services for the Trans-Kalahari Corridor Railway Development | QCBS | Lump Sum | 571.407 | 16.13 | Prior | Plan | 2026-06-11 | 2026-06-25 | 2026-05-21 | 2026-06-04 | 2026-07-09 | 2026-07-23 | Plan | 2026-08-06 | 2026-08-20 | 2026-08-27 | 2026-10-01 | 2026-10-29 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-12-10 | Plan | 2026-12-17 |  | 2026-12-24 | 2027-06-24 09:36
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 6
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2025.3 | BPM | Detailed Design Study of Train Stations Upgrading | QCBS | Lump Sum | 571.407 | 16.13 | Prior | Plan | 2025-06-05 | 2025-06-19 | 2025-05-15 | 2025-05-29 | 2025-07-03 | 2025-07-17 | Plan | 2025-07-31 | 2025-08-14 | 2025-08-21 | 2025-09-25 | 2025-10-23 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-12-04 | Plan | 2025-12-11 |  | 2025-12-18 | 2026-09-17 14:24
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 9
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2025.5 | BPM | Update of the Logistics Masterplan | CQS | Lump Sum | 190.469 | 5.38 | Post | Plan | 2025-09-15 | 2025-09-29 | 2025-08-25 | 2025-09-08 | 2025-10-13 | 2025-10-27 | Plan | 2025-11-10 | 2025-11-24 | 2025-12-01 | 2026-01-05 | 2026-02-02 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-16 | Plan | 2026-03-23 |  | 2026-03-30 | 2026-09-28 09:36
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 6
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2026.3 | BPM | Climate Change Mitigation and Vulnerability Analysis | CQS | Lump Sum | 66.664 | 1.88 | Prior | Plan | 2026-07-02 | 2026-07-16 | 2026-06-11 | 2026-06-25 | 2026-07-30 | 2026-08-13 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2026-08-27 |  | 2026-09-03 | 2027-06-03 14:24
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 9
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
2026.5 | BPM | Transport and Trade Facilitation - Capacity strengthening for Corridor Management | CQS | Lump Sum | 114.281 | 3.23 | Post | Plan | 2026-10-29 | 2026-11-12 | 2026-10-08 | 2026-10-22 | 2026-11-26 | 2026-12-10 | Plan | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Plan | 2026-12-24 |  | 2026-12-31 | 2027-08-31 04:48
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised |  |  |  |  | 8
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
| BPM | [6 empty] | Plan | [6 empty] | Plan | [9 empty] | Plan
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
| Total Cost |  |  |  | 6291.189 | 177.58 |  | Plan | [6 empty] | Plan | [9 empty] | Plan
[8 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[8 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
| * | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
| ** | Total cost of the package or lot or procurement transaction in UA from the PAR
| *** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
| *+ | Retain procurement "Plan" agreed at negotiations and approved by the Boards throughout the project duration
"Revised" includes all updates and revisions
Record the "Actual" date of completion of the activity
| *++ | Indicate currency of the contract
[5 empty] | 2148.49 | 56.4
[5 empty] | 2148.489 | 60.64