## Good & Works
Detailed Procurement Plan - Procurement of Goods & Works
Country / Executing Agency |  |  | MINISTRY OF AGRICULTURE
Name of Project/Program |  |  | Project 2 of the Programme to Strengthen Food and Nutrition Insecurity in the Sahel (P2-P2RS)
Loan No.
Basic Data | [11 empty] | Bidding Document |  | Bidding Period |  | Bid Evaluation *++ |  | Contract Finalization
Procurement System* | Package No. | Package Descritption | Lot No.+ | Lot Description+ | Issue No. Invitation for Bids | Lump Sum or Bill of Quantities | Estimated Cost UA** | Procurement Method | Pre-or-Post Qualification | Oversight Audit Prior-or-Post Review*** | Plan Revised Actual*+ | Date Submitted | Date No Objection | Date Bid Invitation (SPN) | Date Bid Closing/ Opening | Date Bid Evaluation Report Submitted | Date No-Objection | Date Contract Award | Contract Amount (USD)*+++ | Date Contract Signature | Date Contract Completion
AfDB | P2-P2RS-G-01/24 | Procurement of Vehicles (One Station Wagon and Two Double Cabin Pickups and nineteen mlotor cycles) | 1 | Prourement of Vehicles (Two Double Cabin pickups and Nineteen Motor Cycles | 2024-01-03 | Lump Sum | 126000 | Direct Contracting | Prior | Prior | Plan | 2024-01-03 | 15/03/2024 | 15/03/2024 | 2024-01-04 | 2024-04-04 | 2024-11-04 | 14/04/2024 | 126000 | 25/04/2024 | 25/06/2024
Revised
Actual
AfDB | P2-P2RS-G-02/24 | ICT Equipments ( 2 Desktop, 2 Printers & 2 Inverters) | 1 | Procurement of ICT Equipments | 2024-08-03 | Lump Sum | 5000 | Shopping | Post | Post | Plan | 2024-01-03 | 2024-07-03 | 2024-08-03 | 15/03/2024 | 18/03/2024 | 18/03/2024 | 19/03/2024 | 5000 | 19/03/2024 | 26/03/2024
Revised
Actual
AfDB | P2-P2RS-G-03/24 | Procurement of Laptops ( For Operations Director, Accountant and Procurement, and M & E ) | 1 | Procurement of Laptops | 2024-08-03 | Lump Sum | 1000 | Shopping | Post | Post | Plan | 2024-01-03 | 2024-07-03 | 2024-08-03 | 15/03/2024 | 18/03/2024 | 18/03/2024 | 19/03/2024 | 1000 | 19/03/2024 | 26/03/2024
Revised
Actual
AfDB | P2-P2RS-G-04/24 | Office Equipment | 1 | Procurement of Office Equipment | 2024-08-03 | Lump Sum | 10000 | Shopping | Post | Post | Plan | 2024-01-03 | 2024-07-03 | 2024-08-03 | 15/03/2024 | 18/03/2024 | 18/03/2024 | 19/03/2024 | 10000 | 19/03/2024 | 26/03/2024
Revised
Actual
AfDB | P2-P2RS-G-05/24 | Audio Visual | 1 | Procurement of Visual Audio | 2024-08-03 | Lump Sum | 1500 | Shopping | Post | Post | Plan | 2024-01-03 | 2024-07-03 | 2024-08-03 | 15/03/2024 | 18/03/2024 | 18/03/2024 | 19/03/2024 | 1500 | 19/03/2024 | 26/03/2024
Revised
Actual
AfDB | P2-P2RS-G-06/24 | Heavy Duty Copier | 1 | Procurement of Photocopier | 2024-08-03 | Lump Sum | 1000 | Shopping | Post | Post | Plan | 2024-01-03 | 2024-07-03 | 2024-08-03 | 15/03/2024 | 18/03/2024 | 18/03/2024 | 19/03/2024 | 1000 | 19/03/2024 | 26/03/2024
Revised
Actual
AfDB | P2-P2RS-G-07/24 | Accounting Softawre and Maintenance | 1 | Accounting Sofware | 2024-08-03 | Lump Sum | 3000 | Shopping | Post | Post | Plan | 2024-01-03 | 2024-07-03 | 2024-08-03 | 15/03/2024 | 18/03/2024 | 18/03/2024 | 19/03/2024 | 3000 | 19/03/2024 | 19/03/2025
Revised
Actual
AfDB | P2-P2RS-G-08/24 | Fuel, vehicle, motor bike maitenance and repair | 1 | Procurement of Fuel, Motor bike maintenance and Repair | 2024-08-03 | Lump Sum | 5000 | Shopping | Post | Post | Plan | 2024-01-03 | 2024-07-03 | 2024-08-03 | 15/03/2024 | 18/03/2024 | 18/03/2024 | 19/03/2024 | 5000 | 19/03/2024 | 19/03/2025
Revised
Actual
AfDB | P2-P2RS-G-09/24 | Office Supplies and Computer Consumables | 1 | Office Supplies and consumables | 2024-08-03 | Lump Sum | 1500 | Shopping | Post | Post | Plan | 2024-01-03 | 2024-07-03 | 2024-08-03 | 15/03/2024 | 18/03/2024 | 18/03/2024 | 19/03/2024 | 1500 | 19/03/2024 | 26/03/2024
Revised
Actual
AfDB | P2-P2RS-G-10/24 | Purchase of Seedlings for 13ha of degraded forestry lands | 1 | Purchase of Seedlings | 15/04/2024 | Lump Sum | 3900 | Shopping | Post | Post | Plan | 2024-01-04 | 2024-08-04 | 15/04/2024 | 22/04/2024 | 22/04/2024 | 23/04/2024 | 25/04/2024 | 3900 | 25/04/2024 | 25/04/2024
Revised
Actual
AfDB | P2-P2RS-G-11/24 | Purchase of Production and Processing Equipments (Rice, Findi, Groundnut & Corn ) | 1 | Purchase of Equipment | 15/4/2024 | Lumpsum | 248000 | NCB | Prior | Prior | Plan | 2024-01-04 | 15/04/2024 | 15/04/2024 | 29/04/2024 | 2024-03-05 | 2024-10-05 | 13/05/2024 | 248000 | 24/05/2024 | 2024-07-05
Revised
Actual
AfDB | P2-P2RS-G-12/24 | Purchase of Inputs and Light Equipments for the Gardens | 1 | Purchase of Inputs | 15/4/2024 | Lumpsum | 498000 | NCB | Prior | Prior | Plan | 2024-01-04 | 15/04/2024 | 15/04/2024 | 29/04/2024 | 2024-03-05 | 2024-10-05 | 13/05/2024 | 498000 | 24/05/2024 | 2024-07-05
Revised
Actual
AfDB | P2-P2RS-G-13/24 | Acquisition and installation of additional Stations | 1 | Acquisition of Stations | 15/04/2024 | Lump Sum | 150000 | NCB | Post | Post | Plan | 2024-01-04 | 2024-08-04 | 15/04/2024 | 22/04/2024 | 22/04/2024 | 23/04/2024 | 25/04/2024 | 150000 | 25/04/2024 | 25/04/2024
Revised
Actual
AfDB | P2-P2RS-G-14/24 | Supply of Breeder and Foundation Seeds for findi | 1 | Supply of Seed | 15/04/2024 | Lumpsum | 498000 | NCB | Prior | Prior | Plan | 2024-01-04 | 2024-01-04 | 15/04/2024 | 15/04/2024 | 29/04/2024 | 2024-03-05 | 2024-10-05 | 498000 | 24/05/2024 | 24/05/2024
Revised
Actual
AfDB | P2-P2RS-G-15/24 | Supply of Production Kits ( seeds, fertilzer, pesticides /agrochemicals) to producers (women and young people in 17 Gardens (30 kits garderns0 | 1 | Supply of production kits | 16/9/2024 | Lumpsum | 204000 | NCB | Prior | Prior | Plan | 2024-02-09 | 16/09/2024 | 16/09/2024 | 30/09/2024 | 2024-04-10 | 2024-11-10 | 14/10/2024 | 204000 | 25/10/2024 | 25/11/2024
Revised
Actual
AfDB | P2-P2RS-G-16/24 | Purchase of small agro industrial equipments for producers of 17 horticultural gardens, diary products, poultry, fish etc (Items to be determine by sub projects) | 1 | Purchase of agro industrial equipments | 16/9/2024 | Lumpsum | 85000 | NCB | Prior | Prior | Plan | 2024-02-09 | 16/09/2024 | 16/09/2024 | 30/09/2024 | 2024-04-10 | 2024-11-10 | 14/10/2024 | 85000 | 25/10/2024 | 25/11/2024
Revised
Actual
AfDB | P2-P2RS-W-17/24 | Cockerel exchange program ( purchase of day old chicks) | 1 | Cockrel exchange program | 2024-08-05 | Lumpsum | 5000 | Shopping | Post | Post | Plan | 2024-01-05 | 2024-07-05 | 2024-08-05 | 15/05/2024 | 17/05/2024 | 17/05/2024 | 20/05/2024 | 5000 | 20/05/2024 | 20/06/2024
Revised
Actual
AfDB | P2-P2RS-W-18/24 | Cockerel exchange program ( purchase of starter and grower feeds) | 1 | Starter and grower feeds | 2024-08-05 | Lumpsum | 20800 | Shopping | Post | Post | Plan | 2024-01-05 | 2024-07-05 | 2024-08-05 | 15/05/2024 | 17/05/2024 | 17/05/2024 | 20/05/2024 | 20800 | 20/05/2024 | 20/06/2024
Revised
Actual
AfDB | P2-P2RS-W-19/24 | Roster Exchange Program (Purchase of feeding Equipments feeders and plastic feeders | 1 | Roster Exchange Program | 2024-08-05 | Lumpsum | 4500 | Shopping | Post | Post | Plan | 2024-01-05 | 2024-07-05 | 2024-08-05 | 15/05/2024 | 17/05/2024 | 17/05/2024 | 20/05/2024 | 4500 | 20/05/2024 | 20/06/2024
Revised
Actual
AfDB | P2-P2RS-W-20/24 | Cockerel Exchange Program ( Drugs for 10 weeks) | 1 | drugs for 10 weeks | 2024-08-05 | Lumpsum | 3125 | Shopping | Post | Post | Plan | 2024-01-05 | 2024-07-05 | 2024-08-05 | 15/05/2024 | 17/05/2024 | 17/05/2024 | 20/05/2024 | 3125 | 20/05/2024 | 20/06/2024
Revised
Actual
AfDB | P2-P2RS-W-21/24 | Construction of integrated service centers for training and business development support for small agribusinesses | 1 | Construction of integrated service centers | 15/11/2024 | BoQ | 140000 | NCB | Prior | Prior | Plan | 2024-01-11 | 15/11/2024 | 22/11/2024 | 23/12/2024 | 27/12/2024 | 2025-03-01 | 2025-06-01 | 140000 | 17/01/2025 | 17/06/2025
AfDB | P2-P2RS-W-22/24 | Low lands Rehabilitation and Construction of anti salt dike conservation bonds and de-silting canels | 1 | Low Lands Rehabilitation and anti salt dike | 15/11/2024 | BoQ | 600000 | NCB | Prior | Prior | Plan | 2024-01-11 | 15/11/2024 | 22/11/2024 | 23/12/2024 | 27/12/2024 | 2025-03-01 | 2025-06-01 | 600000 | 17/01/2025 | 17/06/2025
AfDB | P2-P2RS-W-23/24 | Upgrading P1-P2RS land development | 1 | upgrading of P1-P2RS Land Development | 15/11/2024 | BoQ | 90000 | NCB | Prior | Prior | Plan | 2024-01-11 | 15/11/2024 | 22/11/2024 | 23/12/2024 | 27/12/2024 | 2025-03-01 | 2025-06-01 | 900000 | 17/01/2025 | 17/06/2025
AfDB | P2-P2RS-W-24/24 | Construction of existing market gardens/nutritious gardens for women; 370m2 + toilets | 1 | Constrtruction of existing market gardens | 23/01/2025 | BoQ | 350000 | NCB | Prior | Prior | Plan | 2025-09-01 | 23/01/2025 | 23/01/2025 | 24/02/2025 | 28/02/2025 | 2025-07-03 | 2025-10-03 | 350000 | 21/03/2025 | 21/08/2025
AfDB | P2-P2RS-W-25/24 | Rehabilitation of Tidal development and hippo protection facilities | 1 | Rehabitation of Tidal development | 23/01/2025 | BoQ | 800000 | NCB | Prior | Prior | Plan | 2025-09-01 | 23/01/2025 | 23/01/2025 | 24/02/2025 | 28/02/2025 | 2025-07-03 | 2025-10-03 | 350000 | 21/03/2025 | 21/08/2025
AfDB | P2-P2RS-W-26/24 | Protection Dyke construction/ Protection bund | 1 | Protection Dyke and bund construction | 2025-07-02 | BoQ | 50000 | NCB | Post | Post | Plan | 31/01/2025 | 2025-07-02 | 2025-07-02 | 21/02/2025 | 27/02/2025 | 28/02/2025 | 2025-03-03 | 50000 | 2025-05-03 | 2025-05-06
AfDB | P2-P2RS-W-27/24 | Rehabilitation of and Building field access roads | 1 | Rehabilitation and building field access roads | 23/01/2025 | BoQ | 350000 | NCB | Prior | Prior | Plan | 2025-09-01 | 23/01/2025 | 23/01/2025 | 24/02/2025 | 28/02/2025 | 2025-07-03 | 2025-10-03 | 350000 | 21/03/2025 | 21/08/2025
AfDB | P2-P2RS-W-28/24 | Rehabilitation of Seed Stores | 1 | rehabilitation of seed stores | 23/01/2025 | BoQ | 100000 | NCB | Prior | Prior | Plan | 2025-09-01 | 23/01/2025 | 23/01/2025 | 24/02/2025 | 28/02/2025 | 2025-07-03 | 2025-10-03 | 100000 | 21/03/2025 | 21/08/2025
AfDB | P2-P2RS-W-29/24 | Development of Pastoral areas (land dev. Community, pastore plots, seed fencing etc | 1 | Development of Pastoral Areas | 2025-07-02 | BoQ | 40000 | NCB | Post | Post | Plan | 31/01/2025 | 2025-07-02 | 2025-07-02 | 21/02/2025 | 27/02/2025 | 28/02/2025 | 2025-03-03 | 40000 | 2025-05-03 | 2025-05-06
AfDB | P2-P2RS-W-30/24 | Construction/Rehabilitation of Livestock hydraulic infrasture | 1 | Construction /Rehabilitation of Livestock Hyraulic infrasture | 16/12/2024 | BoQ | 170000 | NCB | Prior | Prior | Plan | 2024-02-12 | 16/12/2024 | 16/12/2024 | 2025-06-01 | 2025-10-01 | 17/01/2025 | 20/01/2025 | 170000 | 31/01/2025 | 31/07/2025
AfDB | P2-P2RS-W-31/24 | Rehabilitation/Upgrading of existing market gardens/nutritious garden for women 370m2 + Toilets | 1 | Rehabitlitation/ Upgrading of Existing market gardens | 16/12/2024 | BoQ | 850000 | NCB | Prior | Prior | Plan | 2024-02-12 | 16/12/2024 | 16/12/2024 | 2025-06-01 | 2025-10-01 | 17/01/2025 | 20/01/2025 | 850000 | 31/01/2025 | 31/07/2025
AfDB | P2-P2RS-W-32/24 | Rehabilitation and Operationalisation of automatic stations of synoptic observation networks works | 1 | Rehabilitation and Operationalisationautomatic stations | 2025-07-02 | BoQ | 53000 | NCB | Post | Post | Plan | 31/01/2025 | 2025-07-02 | 2025-07-02 | 21/02/2025 | 27/02/2025 | 28/02/2025 | 2025-03-03 | 53000 | 2025-05-03 | 2025-05-06
AfDB | P2-P2RS-W-33/24 | Development of hydro-climatic products and information in a format | 1 | Development of hydro-climatic products | 2025-07-02 | BoQ | 10000 | Shopping | Post | Post | Plan | 31/01/2025 | 2025-07-02 | 2025-07-02 | 21/02/2025 | 27/02/2025 | 28/02/2025 | 2025-03-03 | 10000 | 2025-05-03 | 2025-05-06
Total Cost | [10 empty] | Plan
Revised
Actual
* | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
+ | If applicable
** | Total cost of the package or lot or procurement transaction in UA from the PAR
*** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
*+ | Retain procurement "Plan" agreed at negotiations and approved by the Boards throughout the project duration
"Revised" includes all updates and revisions
Record the "Actual" date of completion of the activity
*++ | The template is to be adapted in case of two stage bidding by adding columns for the second stage bidding period and evaluation process
*+++ | Indicate currency of the contract

## Consulting Services
Detailed Procurement Plan - Procurement of Consulting Services
Country / Executing Agency |  | GAMBIA - MINISTRY OF AGRICULTURE
Name of Project/Program |  | Project 2 of the Programme to Strengthen Food and Nutrition Insecurity in the Sahel (P2-P2RS)
Loan No.
Basic Data | [6 empty] | REOI |  | Terms of Reference |  | Short List |  |  | Request for Proposals (RFP) |  |  |  | Evaluation of Proposals | [5 empty] | Contract Finalization
Procurement System* | Description | Selection Method | Lumpsum or Time-Based | Estimated Cost UA** | Oversight Audit Prior- or-Post Review*** | Plan Revised Actual*+ | Date Published | Date Closing | Date Submitted | Date No-Objection | Date Submitted | Date Approved | Plan Revised Actual | Date RFP Documents Submitted | Date No-Objection | Date RFPs Issued | Date Proposals Closing - Opening | Date Technical Report Submitted | Date No-Objection | Date Opening Financial Proposals | Date Combined Report Submitted | Date No-Objection | Plan Revised Actual | Date Contract Award | Contract Amount( USD) | Date Contract Signature | Date Contract Completion
AfDB | Design and Supervision of Infrastructure works | QCBS | Time Base | 430000 | Prior | Plan | 20/06/2024 | 27/06/2024 | 2024-10-06 | 17/06/2024 | 2024-03-07 | 2024-10-07 | Plan | 20/06/2024 | 27/06/2024 | 2024-12-07 | 26/07/2024 | 2024-02-08 | 2024-09-08 | 2024-12-08 | 14/08/2024 | 21/08/2024 | Plan | 23/08/2024 | 430000 | 2024-05-09 | 30/12/2030
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
AfDB | Monitoring-evaluation system and baseline study | CQS | Time Base | 20000 | Prior | Plan | 2024-06-05 | 20/05/2024 | 25/04/2024 | 2024-02-05 | 23/05/2023 | 30/05/2024 | Plan | 2024-06-05 | 20/05/2024 | 2024-03-06 | 17/06/2024 | 20/06/2024 | 27/06/2024 | 2024-01-07 | 2024-03-07 | 2024-10-07 | Plan | 2024-12-07 | 20000 | 25/07/2024 | 25/08/2024
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
AfDB | Annual Audit of the Financial Accounts | LCS | Time Base | 25000 | Prior | Plan | 2025-03-02 | 17/02/2025 | 23/01/2025 | 30/01/2025 | 20/02/2025 | 27/02/2025 | Plan | 2025-03-02 | 17/02/2025 | 2025-03-03 | 17/03/2025 | 20/03/2025 | 27/03/2025 | 31/03/2025 | 2025-02-04 | 2025-09-04 | Plan | 2025-10-04 | 25000 | 24/04/2025 | 24/06/2025
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
AfDB | Strengthening data management tools | Individual Consultancy | Time Base | 5000 | Post | Plan | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | NIA | 2024-10-04 | 17/04/2024 | 19/04/2024 | 19/04/2024 | 19/04/2024 | 19/04/2024 | 19/04/2024 | Plan | 22/04/2024 | 5000 | 24/04/2024 | 24/05/2024
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
AfDB | Generation of Climate Data at the smallest possible geographical scales (down scaling) (example via satellitte data | Individual Consultancy | Time Base | 15000 | Post | Plan | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | NIA | 2024-10-04 | 17/04/2024 | 19/04/2024 | 19/04/2024 | 19/04/2024 | 19/04/2024 | 19/04/2024 | Plan | 22/04/2024 | 15000 | 24/04/2024 | 24/05/2024
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
[6 empty] | Plan | [6 empty] | Plan | [9 empty] | Plan
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
[6 empty] | Plan | [6 empty] | Plan
[6 empty] | Revised | [6 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual
Total Cost | [5 empty] | Plan | [6 empty] | Plan | [9 empty] | Plan
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
* | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
** | Total cost of the package or lot or procurement transaction in UA from the PAR
*** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
*+ | Retain procurement "Plan" agreed at negotiations and approved by the Boards throughout the project duration
"Revised" includes all updates and revisions
Record the "Actual" date of completion of the activity
*++ | Indicate currency of the contract