## Consulting Services
Detailed Procurement Plan - Procurement of Consulting Services
Country / Executing Agency |  | Botswana - Local Enterprise Authority
Name of Project/Program |  | Scaling Up And Accelerating Youth Entrepreneurship In Botswana (Project ID No. G-BW-100-ZZZ-001)
Loan No. |  | Grant No. ML-0064
Basic Data | [6 empty] | REOI |  | Terms of Reference |  | Short List |  |  | Request for Proposals (RFP) |  |  |  | Evaluation of Proposals |  |  |  |  | Contract Finalization
Procurement System* | Description | Selection Method | Lumpsum or Time-Based | Estimated Cost USD | Oversight Audit Prior- or-Post Review*** | Plan Revised Actual*+ | Date Published | Date Closing | Date Submitted | Date No-Objection | Date Submitted | Date Approved | Plan Revised Actual | Date RFP Documents Submitted | Date No-Objection | Date RFPs Issued | Date Proposals Closing - Opening | Date Technical Report Submitted | Date No-Objection | Date Opening Financial Proposals | Date Combined Report Submitted | Date No-Objection | Date Contract Award | Contract Amount US$ | Date Contract Signature | Date Contract Completion
Bank's Procurement Methods and Procedures | Consultancy to undertake a study to identify a pipeline of interventions to stimulate youth entrepreneurship, and development of high-impact and innovative interventions to build capacity and growth of youth-owned or led MSMEs and start-ups in Botswana in line with the Africa Growth Platform. | CQS | Lumpsum | 75000 | Prior Review | Plan | 29 May 2023 | 12 June 2023 | 22 May 2023 | 5 June 2023 | 19 June 2023 | 23 June 2023 | Plan | 12 June 2023 | 16 June 2023 | 26 June 2023 | 03 July 2023 | N/A | N/A | 04 July 2023 | 10 July 2023 | 17 July 2023 | 25 July 2023 | 75000 | 26 July 2023 | 15 Decemeber 2023
[6 empty] | Revised | [5 empty] | 19 July 2023 | Revised |  | 18 July 2023 | 19 July 2023 | 26 July 2023 |  |  | 27 July 2023 | 2 Aug 2023 | 9 Aug 2023 | 14 Aug 2023 |  | 15 Aug 2023 | 27 Jan 2024
[6 empty] | Revised | [5 empty] | 23 July 2023 | Revised | [12 empty] | April 2024
[6 empty] | Actual | 29 May 2023 | 12 June 2023 | 13 April 2023 | 23 May 2023 | 26 June 2023 | 23 July 2023 | Actual | 20 June 2023 | 23 July 2023 | 15 August 2023 | 29 Aug 2023 | 5 Sept 2023 | 7 Sept 2023 | 12 Sept 2023 | 16 Oct 2023 | 2 Nov 2023 | 7 Nov 2023 | 75000 | 14 Nov 2023
Bank's Procurement Methods and Procedures | Consultancy Services to Create a structured ecosystem platform to facilitate youth-led start-ups and MSME enterprise development (including business development, access to local and international markets, and finance). | CQS | Lumpsum | 35000 |  | Plan | 9 October 2023 | 23 October 2023 | 22 September 2023 | 6 October 2023 | 30 October 2023 | 6 December 2023 | Plan | 2023-11-10 | 2023-11-24 | 2023-12-08 | 2023-12-15 | N/A | N/A | 14 December 2023 | 2023-12-21 | 8 January 2024 | 2024-01-15 | 35000 | 2024-01-16 | 28 June 2024
[6 empty] | Revised | 11 Dec 2023 | 18 Dec 2023 | 30 Nov 2023 | 6 Dec 2023 | 21 Dec 2023 | 10 Jan 2024 | Revised | 2023-12-11 | 2023-12-20 | 2024-01-12 | 2024-01-19 |  |  | 25 Jan 2024 | 2024-01-29 | 31 Jan 2024 | 2 Feb 2024 | 35000 | 2024-02-09 | 28 Jun 2024
[6 empty] | Revised | [5 empty] | 13 March 2024 | Revised | 2024-03-08 | 13 March 2024 | 15 March 2024 | 2024-03-22 | 2024-03-27 | 2024-04-03 | 4 April 2024 | 2024-04-05 | 2024-04-12 | 2024-04-16 | 70000 | 2024-04-19 | 2024-08-30
[6 empty] | Actual | 2023-12-16 | 12 January 2024 | 30 November 2023 | 13 December 2023 | 6 February 2024 |  | Actual
Bank's Procurement Methods and Procedures | Consultancy Services to a Undertake mapping and feasibility study for the establishment of an SME-centered investment vehicle to support youth entrepreneurship based on a lifecycle approach in Botswana, and the developent of a framework for supporting business reforms to increase access to finance for youth-led Startups and MSMEs. | CQS | Lumpsum | 70000 |  | Plan | 6 November 2023 | 20 November 2023 | 22 September 2023 | 6 October 2023 | 30 October 2023 | 6 December 2023 | Plan | 2023-11-10 | 2023-11-24 | 2023-12-08 | 2023-12-15 | N/A | N/A | 14 December 2023 | 2023-12-21 | 8 January 2024 | 2024-01-15 | 70000 | 2024-01-16 | 28 June 2024
[6 empty] | Revised | 2023-12-04 | 2023-12-11 | 2023-11-26 | 2023-12-01 | 2023-12-14 | 2023-12-20 | Revised | 8 Dec 2023 | 15 Dec 2023 | 8 Jan 2024 | 15 Jan 2024 | 18 Jan 2024 | 23 Jan 2024 | 23 Jan 204 | 2024-01-26 | 2024-01-30 | 2024-02-02 | 70000 | 2024-02-09 | 2024-06-14
[6 empty] | Revised | [5 empty] | 13 March 2024 | Revised | 2024-03-08 | 13 March 2024 | 15 March 2024 | 2024-03-22 | 2024-03-27 | 2024-04-03 | 4 April 2024 | 2024-04-05 | 2024-04-12 | 2024-04-16 | 70000 | 2024-04-19 | 2024-08-30
[6 empty] | Actual | 2023-12-16 | 12 January 2024 | 26 November 2023 | 13 December 2023 | 6 February 2024 |  | Actual
Total Cost |  |  |  | 180000 |  | Plan | [6 empty] | Plan | [10 empty] | 180000
|  |  |  | 0 |  | Revised | [6 empty] | Revised | [10 empty] | 105000
|  |  |  | 180000 |  | Actual | [6 empty] | Actual | [10 empty] | 75000
* | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
** | Total cost of the package or lot or procurement transaction in UA from the PAR
*** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
*+ | Retain procurement "Plan" agreed at negotiations and approved by the Boards throughout the project duration
"Revised" includes all updates and revisions
Record the "Actual" date of completion of the activity
*++ | Indicate currency of the contract

## Other (Workshops and Meetings)
Detailed Procurement Plan - Procurement of Consulting Services
Country / Executing Agency |  | Botswana - Local Enterprise Authority
Name of Project/Program |  | Scaling Up And Accelerating Youth Entrepreneurship In Botswana (Project ID No. G-BW-100-ZZZ-001)
Loan No. |  | Grant No. ML-0064
Basic Data | [5 empty] | RFQ |  | Evaluation of Proposals
Procurement System* | Description | Selection Method | Lumpsum or Time-Based | Estimated Cost USD | Plan Revised Actual*+ | Date Published | Date Closing | Evaluation | Offers | Contract Amount US$ | Date Contract Signature | Date Contract Completion
BPS | Sourcing of Business Development Service Providers | RFQ | Lumpsum | 10000 | Plan | 18 March 2024 | 21 March 2024 | 25 March 2024 | 28 March 2024 | 10000 | 2 April 2024 | Jul 2024
Revised
Actual
BPS | Sourcing of Master Class venues and Youth summit with associated logistics (catering, Audio etc) | RFQ | Lumpsum | 65000 | Plan | 2 April 2024 | 5 April 2024 | 8 April 2024 | 11 April 2024 | 65000 | 15 April 2024 | Jul 2024
Revised
Actual
Total Cost |  |  |  | 75000 | Plan |  |  |  | Plan | 75000
[5 empty] | Revised |  |  |  | Revised
[5 empty] | Actual |  |  |  | Actual
* | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
** | Total cost of the package or lot or procurement transaction in UA from the PAR
*** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
*+ | Retain procurement "Plan" agreed at negotiations and approved by the Boards throughout the project duration
"Revised" includes all updates and revisions
Record the "Actual" date of completion of the activity
*++ | Indicate currency of the contract