## Goods & Works
Detailed Procurement Plan - Procurement of Goods
Country / Executing Agency |  |  |  | Intergovernmental Authority on Development (IGAD)
Name of Project/Program |  |  |  | ENTREPRENEURSHIP AND INNOVATION DEVELOPMENT FOR RESILIENCE BUILDING (EIRB ) PROJECT: SUDAN, SOUTH SUDAN AND DJIBOUTI
Project ID: |  |  |  | P -Z1 -IAO -033
Grant No.: |  |  |  | 5900155018152
Basic Data | [12 empty] | Bidding Document |  | Bidding Period |  | Bid Evaluation *++ |  | Contract Finalization
Procurement System* | Package No. | Package Descritption | Category | Lot No.+ | Lot Description+ | Issue No. Invitation for Bids | Lump Sum or Bill of Quantities | Estimated Cost UA ('000) | Procurement Method | Pre-or-Post Qualification | Oversight Audit Prior-or-Post Review*** | Plan Revised Actual*+ | Date Submitted | Date No Objection | Date Bid Invitation (SPN) | Date Bid Closing/ Opening | Date Bid Evaluation Report Submitted | Date No-Objection | Date Contract Award | Contract Amount (Currency)*+++ | Date Contract Signature | Date Contract Completion
BPM | W/EIRB/01/24 | Renovation works of the incubation centers/hubs to accommodate the procured equipment | Works | 1 | Renovation of works the incubation centers/hubs in Juba University to accommodate the procured equipment | RFQ/W/EIRB/01/24 | BoQ | 22363.6364 | RFQ | Post | Post | Plan | 2024-03-25 | 2024-03-30 | 2024-04-04 | 2024-04-25 | 2024-05-07 | 2024-05-12 | 2024-05-22 |  | 2024-06-03 | 2024-07-18
Revised
Actual
BPM | W/EIRB/02/24 | Renovation works of the incubation centers/hubs to accommodate the procured equipment | Works | 1 | Renovation of works the incubation centers/hubs to in University of Djibouti accommodate the procured equipment | RFQ/W/EIRB/02/24 | BoQ | 22363.6364 | RFQ | Post | Post | Plan | 2024-03-25 | 2024-03-30 | 2024-04-04 | 2024-04-25 | 2024-05-07 | 2024-05-12 | 2024-05-22 |  | 2024-06-03 | 2024-07-18
Revised
Actual
BPM | G/EIRB/01/24 | ICT equipment for incubation centres | Goods | Assorted | ICT equipment for incubation centres at University of Juba, South Sudan | RFQ/G/EIRB/01/24 | BoQ | 8303.0303 | RFQ | Post | Post | Plan | 2024-04-10 | 2024-04-15 | 2024-04-20 | 2024-05-11 | 2024-05-23 | 2024-05-28 | 2024-06-07 |  | 2024-06-19 | 2024-07-19
Revised
Actual
BPM | G/EIRB/02/24 | ICT equipment for incubation centres | Goods | Assorted | ICT equipment for incubation centres, at University of Djibouti | RFQ/G/EIRB/02/24 | BoQ | 8303.0303 | RFQ | Post | Post | Plan | 2024-04-10 | 2024-04-15 | 2024-04-20 | 2024-05-11 | 2024-05-23 | 2024-05-28 | 2024-06-07 |  | 2024-06-19 | 2024-07-19
Revised
Actual
Total Cost | [7 empty] | 61333.3333 |  |  |  | Plan
Revised
Actual
Formulas:
Date Contract Signature = [Contract Finalization]+12
Date Contract Completion = [Date Contract Signature]+45

## Consulting Services
Detailed Procurement Plan - Procurement of EIRB/CONsulting Services
Country / Executing Agency |  |  | Intergovernmental Authority on Development (IGAD)
Name of Project/Program |  |  | ENTREPRENEURSHIP AND INNOVATION DEVELOPMENT FOR RESILIENCE BUILDING (EIRB ) PROJECT: SUDAN, SOUTH SUDAN AND DJIBOUTI
Project ID NO:. |  |  | P -Z1 -IAO -033
Grant No: |  |  | 59001550155018096
Basic Data | [7 empty] | REOI |  | Terms of Reference |  | Short List |  |  | Request for Proposals (RFP) |  |  |  | Evaluation of Proposals | [5 empty] | EIRB/CONtract Finalization |  |  |  | Comments
Procurement System* | Package No. | Description | Selection Method | Lumpsum or Time-Based | Estimated Cost UA | Oversight Audit Prior- or-Post Review*** | Plan Revised Actual*+ | Date Published | Date Closing | Date Submitted | Date No-Objection | Date Submitted | Date Approved | Plan Revised Actual | Date RFP Documents Submitted | Date No-Objection | Date RFPs Issued | Date Proposals Closing - Opening | Date Technical Report Submitted | Date No-Objection | Date Opening Financial Proposals | Date Combined Report Submitted | Date No-Objection | Plan Revised Actual | Date EIRB/CONtract Award | EIRB/CONtract Amount (USD ) Currency*++ | Date EIRB/CONtract Signature | Date EIRB/CONtract Completion
BPM | EIRB/CON/03/24 | Hire EIRB/CONsultant(s) for University of Juba, South Sudan, to train 1,500 (500 per country) students, incubatees, researchers and policy makers | IC | Lumpsum | 12454.5455 | Prior | Plan | 2024-04-09 | 2024-04-24 | 2024-03-25 | 2024-04-04 | 2024-05-04 | 2024-05-19 | Plan | 2024-05-04 | 2024-05-11 | 2024-05-16 | 2024-06-06 | 2024-06-18 | 2024-06-28 | 2024-07-06 | 2024-07-11 | 2024-07-21 | Plan | 2024-08-02 |  | 2024-08-23 | 2024-10-12
[7 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[7 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPM | EIRB/CON/04/24 | Hire EIRB/CONsultants to support the five-day training and mentorship boot camps | LCS | Lumpsum | 45666.4242 | Prior | Plan | 2024-04-14 | 2024-04-29 | 2024-03-30 | 2024-04-09 | 2024-04-24 | 2024-05-09 | Plan | 2024-04-24 | 2024-05-09 | 2024-05-14 | 2024-06-19 | 2024-07-01 | 2024-07-16 | 2024-07-24 | 2024-07-29 | 2024-08-08 | Plan | 2024-08-20 |  | 2024-09-17 | 2024-11-21
[7 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[7 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPM | EIRB/CON/05/24 | Hire EIRB/CONsulants to support the mobilisation of private sector support including developing their database | LCS | Lumpsum | 45666.4242 | Prior | Plan | 2024-04-25 | 2024-05-10 | 2024-04-10 | 2024-04-20 | 2024-05-05 | 2024-05-20 | Plan | 2024-05-05 | 2024-05-20 | 2024-05-25 | 2024-06-30 | 2024-07-12 | 2024-07-27 | 2024-08-04 | 2024-08-09 | 2024-08-19 | Plan | 2024-08-31 |  | 2024-09-28 | 2024-12-02
[7 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[7 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPM | EIRB/CON/06/24 | Hire EIRB/CONsulants to support the mobilisation of private sector support including developing their database | IC | Lumpsum | 5303.0303 | Prior | Plan | 2024-04-09 | 2024-04-24 | 2024-03-25 | 2024-04-04 | 2024-05-04 | 2024-05-19 | Plan | 2024-05-04 | 2024-05-11 | 2024-05-16 | 2024-06-06 | 2024-06-18 | 2024-06-28 | 2024-07-06 | 2024-07-11 | 2024-07-21 | Plan | 2024-08-02 |  | 2024-08-23 | 2024-10-12
[7 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[7 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPM | EIRB/CON/07/24 | Hire EIRB/CONsulants to support the mobilisation of private sector support including developing their database | IC | Lumpsum | 5303.0303 | Prior | Plan | 2024-04-09 | 2024-04-24 | 2024-03-25 | 2024-04-04 | 2024-05-04 | 2024-05-19 | Plan | 2024-05-04 | 2024-05-11 | 2024-05-16 | 2024-06-06 | 2024-06-18 | 2024-06-28 | 2024-07-06 | 2024-07-11 | 2024-07-21 | Plan | 2024-08-02 |  | 2024-08-23 | 2024-10-12
[7 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[7 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPM | EIRB/CON/01/24 | Project Coordinator | IC | TB | 126000 | Prior | Plan | 2024-01-25 | 2024-02-09 | 2024-01-10 | 2024-01-20 | 2024-02-19 | 2024-03-05 | Plan | 2024-02-19 | 2024-02-26 | 2024-03-02 | 2024-03-23 | 2024-04-04 | 2024-04-14 | 2024-04-22 | 2024-04-27 | 2024-05-07 | Plan | 2024-05-19 |  | 2024-05-31 | 2025-05-31
[7 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[7 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPM | EIRB/CON/02/24 | Procurement Officer | IC | TB | 108000 | Prior | Plan | 2024-01-25 | 2024-02-09 | 2024-01-10 | 2024-01-20 | 2024-02-19 | 2024-03-05 | Plan | 2024-02-19 | 2024-02-26 | 2024-03-02 | 2024-03-23 | 2024-04-04 | 2024-04-14 | 2024-04-22 | 2024-04-27 | 2024-05-07 | Plan | 2024-05-19 |  | 2024-05-31 | 2025-05-31
[7 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[7 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPM | EIRB/CON/08/24 | Undertake procurement and financial management audit | LCS | Lumpsum | 8070.7148 | Prior | Plan | 2024-08-30 | 2024-09-14 | 2024-08-15 | 2024-08-25 | 2024-09-24 | 2024-10-09 | Plan | 2024-10-17 | 2024-11-01 | 2024-11-06 | 2024-12-12 | 2024-12-24 | 2025-01-03 | 2025-01-11 | 2025-01-16 | 2025-01-26 | Plan | 2025-02-13 |  | 2025-02-25 | 2025-05-26
[7 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[7 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Total Cost |  |  |  |  | 356464.1694
Formulas:
REOI = [Date No-Objection]+5
Date Closing = [REOI]+15
Date No-Objection = [Terms of Reference]+10
Short List = [Date Closing]+10
Short List = [Date No-Objection]+15
Date Approved = [Short List]+15
EIRB/CONtract Finalization = [Date No-Objection]+12
Date EIRB/CONtract Signature = [EIRB/CONtract Finalization]+21
Date EIRB/CONtract Completion = [Date EIRB/CONtract Signature]+50

## Sheet1
0.86
14.35
5.02
36.60
20.23 | 56.6
Note that there was only 20,000 UA in the latest cost tab shared during the launch of the project. Ref to the AM.