## Consulting Services_2024
Detailed Procurement Plan - Procurement of Consulting Services
Country / Executing Agency |  | Repubic of South Sudan/ Ministry of Finance and Planning
Name of Project/Program |  | Institutional Support Project for Strengthening Economic Governance in South Sudan
Grant No. |  | 2100155042068 and 5900155017651
Basic Data | [6 empty] | REOI |  | Terms of Reference |  | Short List |  |  | Request for Proposals (RFP) |  |  |  | Evaluation of Proposals | [5 empty] | Contract Finalization
Procurement System* | Description | Selection Method | Lumpsum or Time-Based | Estimated Cost UA(000) | Oversight Audit Prior or Post Review | Plan Revised Actual*+ | Date Published | Date Closing | Date Submitted | Date No-Objection | Date Submitted | Date Approved | Plan Revised Actual | Date RFP Documents Submitted | Date No-Objection | Date RFPs Issued | Date Proposals Closing - Opening | Date Technical Report Submitted | Date No-Objection | Date Opening Financial Proposals | Date Combined Report Submitted | Date No-Objection | Plan Revised Actual | Date Contract Award | Contract Amount in USD(000) | Date Contract Signature | Date Contract Completion
Bank | TA for Training on Public Debt Management and Reporting | SHL | LS | 45.113 | Prior | Plan | 2023-03-04 | 18/04/2023 | 20/03/2023 | 31/03/2023 | 25/04/2023 | 2023-05-05 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 23/06/2023 |  | 25/06/2023 | 30/09/2023
|  | SHL | LS | 45.113 | Prior | Revised | 15/07/2023 | 31/07/2023 | 2023-03-07 | 14/07/2023 | 2023-04-08 | 17/08/2023 | Revised | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Revised | 21/08/2023 |  | 25/08/2023 | 30/11/2023
|  | SHL | LS | 45.113 | Prior | Revised | 2024-05-02 | 29/02/2024 | 20/01/2024 | 30/01/2024 | 2024-07-03 | 21/03/2024 | Revised | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Revised | 25/03/2024 |  | 30/03/2024 | 30/06/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | Training on Negotiation Techniques | QCBS | LS | 37.594 | Prior | Plan | 2023-08-04 | 2023-02-05 | 23/03/2023 | 2023-03-04 | 2023-05-05 | 15/05/2023 | Plan | 2023-05-05 | 15/05/2023 | 16/05/2023 | 2023-12-06 | 19/06/2023 | 30/06/2023 | 2023-03-07 | 2023-06-07 | 20/07/2023 | Plan | 25/07/2023 |  | 30/07/2023 | 31/10/2023
|  | QCBS | LS | 37.594 | Prior | Revised | 15/07/2023 | 31/07/2023 | 2023-03-07 | 14/07/2023 | 2023-08-08 | 18/08/2023 | Revised | 2023-08-08 | 18/08/2023 | 21/08/2023 | 15/09/2023 | 21/09/2023 | 2023-05-10 | 2023-09-10 | 2023-12-10 | 23/10/2023 | Revised | 27/10/2023 |  | 31/10/2023 | 31/01/2024
|  | QCBS | LS | 37.594 | Prior | Revised | 15/02/2024 | 29/02/2024 | 25/01/2024 | 2024-09-02 | 2024-08-03 | 21/03/2024 | Revised | 24/03/2024 | 2024-10-04 | 2024-12-03 | 2024-10-04 | 20/04/2024 | 30/04/2024 | N/A | N/A | N/A | Revised | 2024-01-05 |  | 2024-03-05 | 30/07/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | Capacity Building in Domestic Debt and Capital Market | SHL | LS | 23.684 | Prior | Plan | 16/09/2023 | 2023-06-10 | 2023-05-09 | 15/09/2023 | 13/10/2023 | 23/10/2023 | Plan | 13/10/2023 | 23/10/2023 | 24/10/2023 | 14/11/2023 | 16/11/2023 | 23/11/2023 | 25/11/2023 | 27/11/2023 | 2023-05-12 | Plan | 2023-07-12 |  | 2023-10-12 | 28/02/2024
|  | SHL | LS | 23.684 | Prior | Revised |  |  | 2023-05-09 | 15/09/2023 | 13/10/2023 | 23/10/2023 | Revised | 13/10/2023 | 23/10/2023 | 24/10/2023 | 14/11/2023 | 16/11/2023 | 23/11/2023 | 25/11/2023 | 27/11/2023 | 2023-05-12 | Revised | 2023-07-12 |  | 2023-10-12 | 28/02/2024
|  | SHL | LS | 23.684 | Prior | Revised | 2024-07-04 | 21/04/2024 | 15/03/2024 | 30/03/2024 | 30/04/2024 | 15/05/2024 | Revised | 30/04/2024 | 15/05/2024 | 17/05/2024 | 2024-07-06 | 15/06/2024 | 30/06/2024 | N/A | N/A | N/A | Revised | 2024-01-07 |  | 2024-05-07 | 20/08/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to Develop an Arrears Management Strategy | QCBS | LS | 45.112 | Prior | Plan | 13/06/2023 | 26/06/2023 | 2023-01-06 | 2023-12-06 | 30/06/2023 | 2023-07-07 | Plan | 30/06/2023 | 2023-07-07 | 2023-08-07 | 2023-04-08 | 14/08/2023 | 25/08/2023 | 29/08/2023 | 31/08/2023 | 2023-11-09 | Plan | 15/09/2023 |  | 20/09/2023 | 31/12/2023
|  | QCBS | LS | 45.112 | Prior | Revised | 20/01/2024 | 2024-05-02 | 21/12/2023 | 15/01/2024 | 2024-10-02 | 25/02/2024 | Revised | 2024-10-02 | 25/02/2024 | 27/02/2024 | 19/03/2024 | 25/05/2024 | 2024-10-06 | N/A | N/A | N/A | Revised | 15/07/2024 |  | 16/07/2024 | 15/10/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
30
Bank | Tailored Training on Debt Management , DSA etc | TBD | LS | 37.593 | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD |  | TBD | 30/09/2023
|  | TBD | LS | 37.593 | TBD | Revised | TBD | TBD | TBD | TBD | TBD | TBD | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to support the Macro Planning Unit/Economic Advisor | SHL | LS | 108.271 | Prior | Plan | 18/03/2023 | 2023-03-04 | 2023-10-03 | 17/03/2023 | 2023-07-04 | 14/04/2023 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 26/05/2023 |  | 30/05/2023 | 31/05/2024
|  | SHL | LS | 108.271 | Prior | Revised | 2023-03-07 | 21/07/2023 | 19/06/2023 | 30/06/2023 | 28/07/2023 | 2023-10-08 | Revised | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Revised | 15/08/2023 |  | 18/08/2023 | 31/08/2024
|  | SHL | LS | 108.271 | Prior | Revised | 2024-05-02 | 20/02/2024 | 20/01/2024 | 30/01/2024 | 28/02/2024 | 14/03/2024 | Revised | 28/02/2024 | 14/03/2024 | 15/03/2024 | 30/03/3034 | 2024-07-04 | 20/04/2024 | N/A | N/A | N/A | Revised | 25/04/2024 |  | 28/04/2024 | 27/04/2026
|  | SHL | LS | 108.271 | Prior | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | Various Targeted Trainings to staff in Macro Planning Unit | TBD | LS | 23..684 | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD |  | TBD | 31/10/2023
|  | TBD | LS | 23..684 | TBD | Revised | 16/02/2024 | 29/02/2024 | 30/01/2024 | 15/02/2024 | 2024-05-03 | 20/03/2024 | Revised | 2024-05-03 | 20/03/2024 | 25/03/2024 | 15/04/2024 | 20/04/2024 | 30/04/2024 | N/A | N/A | N/A | Revised | 2024-01-05 |  | 2024-03-05 | 2024-03-07
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | Various targeted trainings to staff in Aid Management Unit | TBD | LS | 23.684 | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD |  | TBD | 31/12/2023
|  | TBD | LS | 23.684 | TBD | Revised | 16/02/2024 | 29/02/2024 | 30/01/2024 | 15/02/2024 | 2024-05-03 | 20/03/2024 | Revised | 2024-05-03 | 20/03/2024 | 25/03/2024 | 15/04/2024 | 20/04/2024 | 30/04/2024 | N/A | N/A | N/A | Revised | 2024-01-05 |  | 2024-03-05 | 2024-03-07
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to develop Aid Management Information System(AMIS) | SHL | LS | 45.113 | Prior | Plan | 15/04/2023 | 2023-03-05 | 2023-03-04 | 14/04/2023 | 2023-10-05 | 22/05/2023 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 26/06/2023 |  | 30/06/2023 | 31/12/2023
|  | SHL | LS | 45.113 | Prior | Revised | 2023-10-07 | 27/07/2023 | 26/06/2023 | 2023-07-07 | 2023-04-08 | 17/08/2023 | Revised | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Revised | 24/08/2023 |  | 31/08/2023 | 28/02/2024
|  | SHL | LS | 45.113 | Prior | Revised | 2024-05-02 | 20/02/2024 | 20/01/2024 | 30/01/2024 | 29/02/2024 | 15/03/2024 | Revised | 29/02/2024 | 15/03/2024 | 16/03/2024 | 30/03/2024 | 2024-10-04 | 25/04/2024 | N/A | N/A | N/A | Revised | 30/04/2024 |  | 2024-01-05 | 31/10/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | Various Targeted trainings for staff of BOSS | TBD | LS | 23.684 | Prior | Plan | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD |  | TBD | 31/12/2023
|  | TBD | LS | 23.684 | Prior | Revised | 20/02/2024 | 15/03/2024 | 30/01/2024 | 15/02/2024 | 25/03/2024 | 15/04/2024 | Revised | 25/03/2024 | 15/04/2024 | 16/04/2024 | 30/04/2024 | 2024-10-05 | 25/05/2024 | N/A | N/A | N/A | Revised | 28/05/2024 |  | 30/05/2024 | 30/08/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to operationalise Monetary Policy targeting regime and transition to price based | SHL | LS | 37.594 | Prior | Plan | 15/07/2023 | 2023-01-08 | 2023-03-07 | 13/07/2023 | 2023-08-08 | 21/08/2023 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 20/10/2023 |  | 25/10/2023 | 31/03/2024
|  | SHL | LS | 37.594 | Prior | Revised | 20/02/2024 | 2024-05-03 | 30/01/2024 | 15/02/2024 | 16/03/2024 | 30/03/2024 | Revised | 16/03/2024 | 30/03/2024 | 2024-01-04 | 25/04/2024 | 30/04/2024 | N/A | N/A | N/A | N/A | Revised | 2024-01-05 |  | 2024-02-05 | 31/08/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to review the current structure of the Banking sector and recommend restructuring of the sector | QCBS | LS | 82.707 | Prior | Plan | 15/04/2023 | 2023-04-05 | 2023-07-04 | 14/4/2023 | 2023-12-05 | 25/05/2023 | Plan | 2023-12-05 | 25/05/2023 | 26/05/2023 | 20/06/2023 | 28/06/2023 | 2023-10-07 | 14/07/2023 | 21/07/2023 | 2023-04-08 | Plan | 14/08/2023 |  | 21/08/2023 | 31/12/2023
|  | QCBS | LS | 82.707 | Prior | Revised | 21/07/2023 | 18/08/2023 | 2023-10-07 | 20/07/2023 | 25/08/2023 | 2023-08-09 | Revised | 25/08/2023 | 2023-08-09 | 2023-11-09 | 2023-10-10 | 16/10/2023 | 27/10/2023 | 31/10/2023 | 2023-06-11 | 16/11/2023 | Revised | 21/11/2023 |  | 30/11/2023 | 31/03/2024
|  | QCBS | LS | 82.707 | Prior | Revised | 2024-02-02 | 16/02/2024 | 20/01/2024 | 30/01/2024 | 23/02/2024 | 2024-08-03 | Revised | 23/02/2024 | 2024-08-03 | 2024-10-03 | 2024-10-04 | 15/04/2024 | 30/04/2024 | 2024-02-05 | 2024-07-05 | 21/05/2024 | Revised | 22/05/2024 |  | 25/05/2024 | 30/09/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to Develop Financial Sector Strategy | SHL | LS | 37.593 | Prior | Plan | 19/01/2024 | 2024-05-02 | 2024-10-01 | 18/01/2024 | 2024-09-02 | 23/02/2024 | Plan | 2024-09-02 | 23/02/2024 | 26/02/2024 | 22/03/2024 | 29/03/2024 | 2024-10-04 | 2024-12-04 | 18/04/2024 | 30/04/2024 | Plan | 2024-10-05 |  | 15/05/2024 | 30/09/2024
|  | SHL | LS | 37.593 | Prior | Revised | 2024-02-04 | 16/02/2024 | 20/01/2024 | 30/01/2024 | 21/2/2024 | 2024-03-03 | Revised | 21/2/2024 | 2024-03-03 | 2024-05-03 | 26/03/2024 | 2024-05-04 | 19/04/2024 | N/A | N/A | N/A | Revised | 20/04/2024 |  | 22/04/2024 | 30/07/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to provide Advisory service to the Central Bank Monetary Policy Unit | SHL | LS | 40.602 | Prior | Plan | 13/01/2024 | 31/01/2024 | 2024-04-01 | 2024-12-01 | 2024-07-02 | 15/02/2024 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 16/4/2024 |  | 22/4/2024 | 31/08/2024
|  | SHL | LS | 40.602 | Prior | Revised | 2024-02-04 | 16/02/2024 | 20/01/2024 | 30/01/2024 | 21/2/2024 | 2024-03-03 | Revised | 21/2/2024 | 2024-03-03 | 2024-05-03 | 26/03/2024 | 2024-05-04 | 19/04/2024 | N/A | N/A | N/A | Revised | 20/04/2024 |  | 22/04/2024 | 30/07/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to Develop ESW for Economic Diversification | SHL | LS | 30.075 | Prior | Plan | 2024-11-03 | 29/03/2024 | 29/02/2024 | 2024-08-03 | 2024-05-04 | 19/04/2024 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 18/06/2024 |  | 25/06/2024 | 30/09/2024
|  | SHL | LS | 30.075 | Prior | Actual | N/A | N/A | 30/03/2023 | 2023-02-04 | 17/03/2023 | 24/05/2024 | Actual | N/A | N/A | 31/05/2023 | 15/06/2023 | 2023-11-07 | 24/07/2023 | N/A | N/A | N/A | Actual | 2023-09-08 |  | 2023-12-09 | On-going
Bank | TA to develop a strategic roadmap for a PPP framework including an Act, regulations as well as PPP manual and conduct training | QCBS | LS | 75.188 | Prior | Plan | 14/03/2024 | 2024-02-04 | 2024-01-03 | 2024-12-03 | 2024-09-04 | 19/04/2024 | Plan | 2024-09-04 | 19/04/2024 | 20/04/2024 | 20/05/2024 | 27/05/2024 | 2024-07-06 | 2024-11-06 | 17/06/2024 | 28/06/2024 | Plan | 2024-10-07 |  | 14/07/2024 | 31/12/2024
|  | QCBS | LS | 75.188 | Prior | Revised | 2024-07-02 | 21/02/2024 | 20/01/2024 | 2024-05-02 | 28/02/2024 | 14/03/2024 | Revised | N/A | N/A | 15/03/2024 | 14/04/2024 | 20/04/2024 | 2024-10-05 | N/A | N/A | N/A | Revised | 20/05/2024 |  | 25/05/2024 | 30/11/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | Various Trainings to MOFP on PPPs development | TBD | LS | 22.556 | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD |  | TBD | 31/08/2023
|  | TBD | LS | 22.556 | TBD | Revised | 2024-07-03 | 21/03/2024 | 15/02/2024 | 29/02/2024 | 28/03/2024 | 15/04/2024 | Revised | 28/03/2024 | 15/04/2024 | 16/04/2024 | 30/04/2024 | 2024-07-05 | 21/05/2024 | N/A | N/A | N/A | Revised | 23/05/2024 |  | 30/05/2024 | 15/07/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to support institutionalisation of FIU, Anti- corruption agency and PPA | QCBS | LS | 120.301 | Prior | Plan | 13/05/2023 | 31/05/2023 | 29/04/2023 | 2023-12-05 | 2023-07-05 | 22/07/2023 | Plan | 2023-07-05 | 22/07/2023 | 24/07/2023 | 24/08/2023 | 31/08/2023 | 2023-11-09 | 14/09/2023 | 20/09/2023 | 29/09/2023 | Plan | 2023-10-10 |  | 25/10/2023 | 30/04/2024
|  | QCBS | LS | 120.301 | Prior | Revised | 16/08/2023 | 2023-01-09 | 2023-04-08 | 15/08/2023 | 2023-08-09 | 22/09/2023 | Revised | 2023-08-09 | 22/09/2023 | 25/09/2023 | 20/10/2023 | 27/10/2023 | 2023-10-11 | 14/11/2023 | 20/11/2023 | 27/11/2023 | Revised | 30/11/2023 |  | 2023-05-12 | 31/05/2024
|  | QCBS | LS | 120.301 | Prior | Revised | 16/08/2023 | 2023-01-09 | 2023-04-08 | 15/08/2023 | 2023-08-09 | 22/09/2023 | Revised | 2023-08-09 | 22/09/2023 | 25/09/2023 | 20/10/2023 | 27/10/2023 | 2023-10-11 | 14/11/2023 | 20/11/2023 | 27/11/2023 | Revised | 30/11/2023 |  | 2023-05-12 | 31/05/2024
[6 empty] | Actual |  |  | 26/10/2024 |  |  |  | Actual | [9 empty] | Actual
Bank | Various Trainings on Anti- corruption to PPA | TBD | LS | 37.594 | Prior | Plan | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD |  | TBD | 30/09/2023
|  | TBD | LS | 37.594 | Prior | Revised | 30/03/2024 | 15/04/2024 | 2024-01-03 | 15/03/2024 | 20/04/2024 | 2024-10-05 | Revised | 20/04/2024 | 2024-10-05 | 15/05/2024 | 30/05/2024 | 2024-10-06 | 14/06/2024 | N/A | N/A | N/A | Revised | 15/06/2024 |  | 16/06/2024 | 15/07/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA-Individual to review and update the design of the Public Procurement Authority Building and develop the related Specifications, Bill of Quantity,ESIA, etc | SHL | LS | 60.15 | Prior | Plan | 2023-02-05 | 18/05/2023 | 17/04/2023 | 28/04/2023 | 26/05/2023 | 2023-06-06 | Plan | 26/05/2023 | 2023-06-06 | 2023-07-06 | 30/06/2023 | 2023-06-07 | 18/07/2023 | 20/07/2023 | 28/07/2023 | 2023-11-08 | Plan | 21/08/2023 |  | 25/08/2023 | 31/10/2023
|  | SHL | LS | 60.15 | Prior | Revised | 15/08/2023 | 31/08/2023 | 2023-01-08 | 14/08/2023 | 2023-08-09 | 20/09/2023 | Revised | 2023-08-09 | 20/09/2023 | 21/09/2023 | 16/10/2023 | 20/10/2023 | 2023-03-11 | 2023-08-11 | 15/11/2023 | 24/11/2023 | Revised | 28/11/2023 |  | 30/11/2023 | 28/02/2024
[6 empty] | Actual |  |  | 26/10/2024 |  |  |  | Actual | [9 empty] | Actual
Bank | Various trainings for staff of Public Procurement Authority | SHL | LS | 38.346 | Prior | Plan | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD |  | TBD | 31/12/2023
|  | SHL | LS | 38.346 | Prior | Revised | 14/03/2024 | 28/03/2024 | 15/02/2024 | 29/02/2024 | 2024-07-04 | 25/04/2024 | Revised | 2024-07-04 | 25/04/2024 | 26/04/2024 | 2024-10-05 | 15/05/2024 | 30/05/2024 | N/A | N/A | N/A | Revised | 31/05/2024 |  | 2024-01-06 | 15/07/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to conduct gap analsis of the regulatory landscape | QCBS | LS | 37.594 | Prior | Plan | 14/02/2024 | 29/02/2024 | 2024-02-02 | 2024-12-02 | 2024-07-03 | 21/03/2024 | Plan | 2024-07-03 | 21/03/2024 | 22/03/2024 | 22/04/2024 | 29/04/2024 | 2024-10-05 | 14/05/2024 | 20/05/2024 | 31/05/2024 | Plan | 2024-10-06 |  | 20/06/2024 | 30/09/2024
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
|  | QCBS | LS | 37.594 | Prior | Actual |  |  | 2023-06-06 | 2024-09-06 | 22/09/2024 | 2024-06-12 | Actual | 23/10/2024 | 2024-06-12 | 13/12/2023 | 30/01/2024 | [5 empty] | Actual
Bank | TA to develop roadmap for South Sudan to join and implement the EITI standards | QCBS | LS | 75.188 | Prior | Plan | 15/02/2025 | 28/02/2025 | 2025-03-02 | 14/02/2025 | 2025-05-03 | 18/03/2025 | Plan | 2025-05-03 | 18/03/205 | 20/03/2025 | 18/04/2025 | 25/04/2025 | 2025-05-05 | 2025-07-05 | 15/05/2025 | 30/05/2025 | Plan | 15/06/2025 |  | 30/06/2025 | 31/10/2025
|  | QCBS | LS | 75.188 | Prior | Revised | 21/05/2024 | 2024-05-06 | 30/04/2024 | 14/05/2024 | 2024-10-06 | 25/06/2024 | Revised | 2024-10-06 | 25/06/2024 | 27/06/2024 | 26/07/2024 | 2024-05-08 | 15/08/2024 | 18/08/2024 | 25/08/2024 | 2024-10-09 | Revised | 2024-12-09 |  | 14/09/2024 | 15/12/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | TA to develop Energy transition strategy for the extractive sector | QCBS | LS | 75.188 | Prior | Plan | 15/06/2023 | 30/06/2023 | 2023-05-06 | 13/06/2023 | 2023-07-07 | 17/07/2023 | Plan | 2023-07-07 | 17/07/2023 | 18/07/2023 | 15/08/2023 | 23/08/2023 | 2023-07-09 | 14/09/2023 | 20/09/2023 | 2023-06-10 | Plan | 20/10/2023 |  | 31/10/2023 | 30/04/2024
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
|  | QCBS | LS | 75.188 | Prior | Actual | 24/06/2023 | 2023-02-08 | 26/05/2023 | 21/6/2023 | 2023-08-08 | 30/10/2023 | Actual | 29/08/2024 | 2023-09-12 | 2023-05-12 | 2024-12-01 | [5 empty] | Actual
Bank | TA to prepare regulation for implementation of the mining law, and strategic framwork to support formalisation of Artisanal and scall scale Mining | QCBS | LS | 60.15 | Prior | Plan | 17/05/2023 | 2023-07-06 | 2023-05-05 | 15/05/2023 | 14/07/2023 | 28/07/2023 | Plan | 14/07/2023 | 28/07/2023 | 31/07/2023 | 30/08/2023 | 2023-05-09 | 15/09/2023 | 18/09/2023 | 22/09/2023 | 2023-06-10 | Plan | 13/10/2023 |  | 20/10/2023 | 28/02/2024
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
|  | QCBS | LS | 60.15 | Prior | Actual | 2023-12-08 | 26/08/2023 | 2023-07-06 | 2023-08-08 | 24/10/2023 | 2023-09-12 | Actual | 29/08/2023 | 2023-09-12 | 13/12/2023 | 30/01/2023 | [5 empty] | Actual
Bank | Capacity Building of MSG and extractive sectors regulators, etc | TBD | LS | 24.812 | TBD | Plan | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD | TBD | TDB | TBD | TBD | TBD | TBD | TBD | TBD | Plan | TBD |  | TBD | 31/10/2023
|  | SHL | LS | 24.812 | TBD | Revised | 20/02/20024 | 2024-06-03 | 2024-01-02 | 15/02/2024 | 2024-10-03 | 25/03/2024 | Revised | 2024-10-03 | 25/03/2024 | 30/03/2024 | 30/04/2024 | 2024-10-05 | 25/05/2024 | N/A | N/A | N/A | Revised | 26/05/2024 |  | 28/05/2024 | 31/07/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Bank | Financial Audit Service | LCS | LS | 56.391 | Prior | Plan | 17/05/2023 | 2023-02-06 | 2023-10-05 | 15/05/2023 | 2023-07-02 | 17/06/2023 | Plan | 2023-07-02 | 17/06/2023 | 19/06/2023 | 20/07/2023 | 27/07/2023 | 2023-07-08 | 2023-09-08 | 14/08/2023 | 25/05/2023 | Plan | 26/08/2023 |  | 31/08/2023 | 31/12/2025
|  | LCS | LS | 56.391 | Prior | Revised | 29/07/2023 | 15/08/2023 | 17/07/2023 | 28/07/2023 | 18/08/2023 | 31/08/2023 | Revised | 18/08/2023 | 31/08/2023 | 2023-01-09 | 29/09/2023 | 2023-06-10 | 19/10/2023 | 23/10/2023 | 30/10/2023 | 2023-10-11 | Revised | 15/11/2023 |  | 23/11/2023 | 31/12/2025
|  | LCS | LS | 56.391 | Prior | Revised | 20/02/2024 | 13/03/2024 | 30/01/2024 | 15/02/2024 | 25/03/2024 | 15/04/2024 | Revised | 25/03/2024 | 15/04/2024 | 20/04/2024 | 20/05/2024 | 26/05/2024 | 15/06/2024 | N/A | N/A | N/A | Revised | 17/06/2024 |  | 19/06/2024 | 30/06/2024
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
[6 empty] | Plan | [6 empty] | Plan | [9 empty] | Plan
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Total Cost |  |  |  | #REF! |  | Plan | [6 empty] | Plan | [9 empty] | Plan
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual